## Sheet1
Transmission Tracking Number (TTN) | Parent Project Number | Parent Project Name | Parent City | Parent County | Parent Project Description | Parent Project Type | Parent Rule Subsection | Parent PUC Control Number | Parent Initial Estimated Cost | Sub Project Number | Sub Project Name | City | County | Sub Project Description | Project Type | Rule Subsection | PUC Control Number | Estimated Start Date | Actual Start Date | Completion Date | Energized Date | Initial Estimated Project Cost | Initial Estimated Substation Cost | Initial Estimated Transmission Cost | Final Estimated Project Cost | Final Estimated Substation Cost | Final Estimated Transmission Cost | Final Actual Project Cost | Final Actual Substation Cost | Final Actual Transmission Cost | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Double Circuit or Single Circuit | Conductor Type, Size & Bundling | Structure Types | Existing ROW Width (Feet) | Existing ROW Width Varies Explanation | Existing ROW Length (Miles) | Existing ROW Length Varies Explanation | New ROW Width (Feet) | New ROW Width Varies Explanation | New ROW Length (Miles) | New ROW Length Varies Explanation | Comments | Report Month
| L24 | BOGGY_Substation 2- 15 Parent | Deer Park 15 test | Harris County | 138 kV Service to BOGGY_Substation within one mile of Ckts. 85C and 88D. This is testing. | Other transmission projects over $250K | 25.83(a)(3) |  | 6000000 | L24A | BOGGY_Substation Sub Project | Deer Park | Harris County | 138 kV Service to BOGGY_Substation within one mile of Ckts. 85C and 88D | Other transmission projects over $250K | 25.83(a)(3) |  | 2020-03-02 | 2020-03-02 | 2023-06-16 | 2022-11-03 | 6000000 | 200000 | 5500000 | 6200000 | 250000 | 5500000 | 6500000 | 500000 | 6000000 | 99 | 138 | 345 | 0.51 | Single | 2-959.6 ACSS | Steel Poles, Steel Towers | 22-30 | Centerline | 0.19 |  | 40-182 |  | 0.24 |  | Construction complete. Actual cost to be paid by Shell. | 2025-05-07