## SUMMARY
WEB Version
Revised: | Revised June 18
MONTHLY ACTIVITY AT A GLANCE
for
APRIL 2004 - Revision 1
TRANSMISSION PROJECTS
A | B | C | D | E | F | G | H | I | J | K | L | M | N | O
UTILITY | TOTAL PROJECTS REPORTED =Utility!AA102 | ESTIMATED COST FOR ALL REPORTED PROJECTS =Utility!AA100 | NEW PROJECTS COUNT THIS MONTH Manual Entry | 1st ESTIMATE COST FOR NEW PROJECTS Manual Entry | COMPLETED PROJECTS COUNT THIS MONTH =Utility!Y102 | COMPLETED PROJECTS (FINAL ACTUAL COSTS) =Utility!X100 | COMPLETED PROJECTS (FINAL ESTIMATED COSTS) =Utility!Y100 | ONGOING PROJECT COUNT = B - F | ONGOING PROJECT COST ESTIMATE (THIS MONTH) = C - H | ONGOING PROJECT COST ESTIMATE (FROM LAST MONTH) Linked or Manual | NET ONGOING PROJECT CHANGE FROM LAST MONTH = J - K | DIFFERENCE: NEW PROJECTS LESS COMPLETED PROJECTS = E - H | CALCULATED COST ADJUSTMENT TO EXISTING PROJECTS = L - M | EXPLANATION OR COMMENT
BEPC | 20 | 103511991 | 1 | 3860000 | 0 | 0 | 0 | 20 | 103511991 | 99651991 | 3860000 | 3860000 | 0
CNP | 26 | 96649000 | 1 | 700000 | 4 | 9761799 | 10310000 | 22 | 86339000 | 95849000 | -9510000 | -9610000 | 100000 | Cost Revision to 1 project
AEPC | 18 | 84734183 | 1 | 1352003 | 0 | 0 | 0 | 18 | 84734183 | 83382180 | 1352003 | 1352003 | 0
EGSI | 13 | 53214846 | 0 | 0 | 0 | 0 | 0 | 13 | 53214846 | 53214846 | 0 | 0 | 0
EPE | 5 | 12211528.61 | 2 | 1050000 | 0 | 0 | 0 | 5 | 12211528.61 | 11161528.61 | 1050000 | 1050000 | 0
LCRA | 38 | 172792987.4879 | 3 | 729000 | 4 | 5885589 | 6446900 | 34 | 166346087.4879 | 172380757.4879 | -6034670 | -5717900 | -316770 | Cost Revision to 2 projects
LEA E.C. |  | 0 | [7 empty] | 0
MVEC | 3 | 6760000 | 0 | 0 | 0 | 0 | 0 | 3 | 6760000 | 6760000 | 0 | 0 | 0 |  | Oncor
ONCOR | 91 | 215024353.36 | 5 | 540349 | 4 | 3882311 | 3447660 | 87 | 211576693.36 | 209751558.36 | 1825135 | -2907311 | 4732446 | Cost Revision to 4 Projects. | 4732446
PEC | 3 | 8463881 | 0 | 0 | 1 | 0 | 0 | 2 | 8463881 | 10733289 | -2269408 | 0 | -2269408 | CCN 11014 was vacated & dismissed. | 4742446
SPS | 4 | 11063689 | 0 | 0 | 0 | 0 | 0 | 4 | 11063689 | 11063689 | 0 | 0 | 0 |  | -10000
STEC | 30 | 10026562 | 0 | 0 | 3 | 1027932.38 | 1088062 | 27 | 8938500 | 10026562.33 | -1088062.33 | -1088062 | -0.33
SULP | 1 | 3978000 | 0 | 0 | 0 | 0 | 0 | 1 | 3978000 | 3978000 | 0 | 0 | 0 |  | -10000
SWEPCO | 2 | 17695000 | 0 | 0 | 0 | 0 | 0 | 2 | 17695000 | 17695000 | 0 | 0 | 0
TNMP | 6 | 26047000 | 1 | 1270000 | 0 | 0 | 0 | 6 | 26047000 | 24777000 | 1270000 | 1270000 | 0
AEPN | 19 | 72603311 | 2 | 851000 | 0 | 0 | 0 | 19 | 72603311 | 71752311 | 851000 | 851000 | 0
TOTAL | 279 | 894776332.4579 | 16 | 10352352 | 16 | 20557631.38 | 21292622 | 263 | 873483710.4579 | 882177712.7879 | -8694002.33 | -10940270 | 2246267.67
|  | Ongoing Project Count Check: | 263 | Correct |  |  | LAST MONTH ONGOING COUNT: | 263
Note on A12: aboling: FORMERLY CPE.
Note on A13: aboling: FORMERLY CPL.
Note on A23: aboling: SHARYLAND UTILITIES
Note on A26: aboling: FORMERLY WTU
Note on F10: aboling: A COMPLETE PROJECT IS DEFINED AS ONE FOR WHICH THE CONSTRUCTION IS COMPLETE AND THE FINAL ACTUAL PROJECT COST HAS BEEN ENTERED.
Note on I10: aboling: ACTIVE PROJECTS INCLUDE NEW PROJECTS BUT NOT COMPLETED PROJECTS.

## AEPC
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost (Total) | Final Estimated Project Cost (Total) | Final Actual Project Cost (Total) | % Variance | Percent Complete | Existing Voltage | Upgraded or New Voltage | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS | Estimated OR Actual Project Cost (SUBSTATION) |  | Last Month: | Current minus last month: | Cumulative Sum
21071518 | Coleto Creek-Pawnee 345 kV | Goliad & Karnes Counties | New 345 kV line between Coleto Creek Power Station and new STEC Pawnee Switching Station | 2001-08-25 | 2003-09-30 | 2003-01-07 | 37887000 |  |  |  | 99% |  | 345kV | 107.8mi | Double Crkt 1590 MCM bundled | Steel Lattice Towers |  |  | 160 ft | 53.9 mi |  | Docket #21741 Final Order 6/18/01. Delay due to rain and US Fish & Wildlife restrictions. | 37887000 | 0 | 37887000 |  |  | 37887000 | 0 | 0
21722984 | Citgo NOP-Lon Hill 138 kV | Corpus Christi, Nueces County | Construct a new 138 kV transmission line from Citgo NOP to Lon Hill Sub in three secgments, 1.6 miles of single circuit single pole, 2.8 miles of double circuit single pole and 10. Miles of single circuit single pole. | 2002-04-18 | 2002-12-31 | 2003-01-14 | Transmission $9,369,033 Substation $4,663,624 |  |  |  | 99% |  | 138kV | 14.7 | 2-795 kcmil ACSR |  |  |  | 60' | 11.9 Mi |  | Docket #22338 Approved. STM approved to transfer 138kV transmission line only to LCRA in Docket #25774. Estimated cost of Transmission line to LCRA $9,667,731. Transmission portion listed in initial estimate includes ROW, which was not transferred to LCRA in the amount of $525,245. |  | 0 | 0 | 4663624 |  | 0 | 0 | 0
21722970 | Citgo NOP-Nueces Bay 138 kV cable | Corpus Christi, Nueces County | Install 0.6 miles of underground cable from Citgo NOP substation to Nueces Bay Substation in conduit, 138 kV, 2-1000 kcmil Cu per phase in 4 conduits. | 2002-08-01 | 2002-02-01 | 2002-02-01 | Transmission $1,510,500 Substation $8,700,034 |  |  |  | 99% |  | 138kV | 0.6 Mi | 2-1000 kcmil Cu per phase in 4 Conduits | Cable |  |  | 20 | 0.6 Mi |  | Docket #22340 Approved. STM approved to transfer 138kV cable to LCRA in Docket #25774. Estimated cost of cable to LCRA $5,377,489. Transmission portion listed in initial estimate column includes ROW, which was not transferred to LCRA in the amount of $13,000. |  | 0 | 0 | 8700034 |  | 0 | 0 | 0
21723002 | Lon Hill Power Station to Nueces Bay Power Station | Corpus Christi, Nueces County | Install a new 138 kV line in four segments from Lon C Hill Power Plant to Nueces Bay Power Plant. Segment 1-5.4 miles of double circuit single pole, Segment 2-0.2 miles of single circuit single pole, Segment 3-3.2 Miles of single circuit single pole, Segment 4-8.4 miles of double-circuit single pole, all constructed with 2-795 kcmil ACSR. | 2002-05-15 | 2002-05-15 | 2003-06-20 | Transmission $13,815,827 Substation $5,237,415 |  |  |  | 99% |  | 138kV | 17.2 | 2-795 kcmil ACSR | Single Pole With Davit Arm |  |  | 60' and 100' | 8.8 Mi |  | Docket #22339, CCN Approved. STM approved to transfer 138kV transmission line only to LCRA approved in Docket #25774. Estimated cost of transmission line to LCRA $26,300,779. Transmission portion listed in initial estimate column includes ROW, which was not transferred to LCRA in the amount of $13,000. |  |  |  | 5237415 |  | 0 | 0 | 0
22169896 | Falfurrias- Rachal 138 kV Line Reconductor | Brooks County, Tx | Reconductor and rebuild approximately 25.1 miles of existing 138kV transmission line from Falfurrias Substation to Rachal Substation. The old line is 477 MCM Aluminum conductor on wood H frame structures and will be reconductored with 795 MCM aluminum conductor on steel poles | 2001-03-15 | 2002-02-22 | 2003-03-01 | 5919000 |  |  |  | 99% | 138kV | 138kV | 25.1 mi. | 795 MCM & 7#8 Alumoweld | Steel Single Poles | Ceterline Defined | 25.1 mi. |  |  | Sub Rule 25.101 (c) (2) (C) (ii) | Line located in CPL single certified service area. | 5919000 | 0 | 5919000 | 5237415 |  | 5919000 | 0 | 0
22169662 | Falcon-Lopeno 138 kV Line Reconductor | Starr & Zapata Counties, Texas | Reconductor and rebuild approximately 10 miles of existing 138kV transmission line from Falcon Substation to Lopeno Substation. The old line is 336.4 MCM Aluminum conductor on wood H frame structures and will be reconductored with 795 MCM ACSR conductors on steel poles. | 2001-12-15 | 2002-02-15 |  | 2140875 |  |  |  | 95% | 138kV | 138kV | 10 mi. | 795 MCM ACSR & 7#8 Alumoweld | Steel Single Poles | Ceterline Defined | 10 mi. |  |  | Sub Rule 25.101 (c) (2) (C) (ii) | The line is located in MEC single certified service area. | 2140875 | 0 | 2140875 |  |  | 2140875 | 0 | 0
22169585 | Garza- Falcon 138 kV Line Reconductor | Starr County, Texas | Reconductor and rebuild approximately 27.3 miles of existing 138kV transmission line from Garza Substation to Falcon Substation. The old line is 336 MCM Aluminum conductor on wood H frame structures and will be reconductored with 795 MCM aluminum conductor on steel poles. | 2002-03-10 | 2002-10-10 |  | 5577000 |  |  |  | 95% | 138kV | 138kV | 27.3 mi. | 795 MCM & 7#8 Alumoweld Static | Steel Single Poles | Ceterline Defined | 27.3 mi. |  |  | Sub Rule 25.101 (c) (2) (C) (ii) | This line is located in MEC (Medina Electric Coop) single certified service area. | 5577000 | 0 | 5577000 |  |  | 5577000 | 0 | 0
22169873 | North Edinburg- Rachal 138 kV Line Reconductor | Brooks & Hildago Counties, Texas | Reconductor and rebuild approximately 37.8 miles of existing 138kV transmission line from North Edinburg Substation to Rachal Substation. The old line is 477 MCM Aluminum conductor on wood H frame structures and will be reconductored with 795 MCM aluminum conductor on steel poles. | 2002-03-10 | 2003-03-10 | 2003-03-18 | 8261000 |  |  |  | 99% | 138kV | 138kV | 37.8 mi. | 795 MCM & 7#8 Alumoweld Static | Steel Single Poles | Ceterline Defined | 37.8 mi. |  |  | Sub Rule 25.101 (c) (2) (C) (ii) & Sub Rule 25.101 (c) (2) (C) (iii) | This line is located in TCC single certified service area and MVEC (Magic Valley) single certified service area and TCC/MVEC dual certified service areas. A 13-mile portion of this line will be relocated at the request and expense of an existing property owner. All current and relocated facilities are located on the property owner who is making request. The segment is located just south of Rachal Substation. | 8261000 | 0 | 8261000 |  |  | 8261000 | 0 | 0
22169764 | Lopeno-Zapata 138 kV Line Reconductor | Zapata County, Texas | Reconductor and rebuild approximately 20.3 miles of existing 138kV transmission line from Zapata Substation to Lopeno Substation. The old line is 336.4 MCM Aluminum conductor on wood H frame structures and will be reconductored with 795 MCM ACSR conductors on steel poles. | 2002-02-22 | 2003-01-30 | 2003-01-31 | 4168000 |  |  |  | 95% | 138kV | 138kV | 20.3 mi. | 795 MCM ACSR & 7#8 Alumoweld | Steel Single Poles | Ceterline Defined | 20.3 mi. |  |  | Sub Rule 25.101 (c) (2) (C) (ii) | The line is located in MEC single certified service area. | 4168000 | 0 | 4168000 |  |  | 4168000 | 0 | 0
22169796 | Rio Bravo-Zapata 138 kV Line Reconductor | Zapata & Webb Counties, Texas | Reconductor and rebuild approximately 30.8 miles of existing 138kV transmission line from Zapata Substation to Rio Bravo Substation. The old line is 336.4 MCM Aluminum conductor on wood H frame structures and will be reconductored with 795 MCM ACSR conductors on steel poles. | 2002-05-15 | 2003-04-15 |  | 6308000 |  |  |  | 95% | 138kV | 138kV | 30.8 mi. | 795 MCM ACSR & 7#8 Alumoweld | Steel Single Poles | Ceterline Defined | 30.8 mi. |  |  | Sub Rule 25.101 (c) (2) (C) (ii) | The line is located in MEC single certified & TCC single certified service areas. | 6308000 | 0 | 6308000 |  |  | 6308000 | 0 | 0
22169830 | Wormser-Rio Bravo 138kV Reconductor | Webb County, Texas | Reconductor and rebuild approximately 9.6 miles of existing 138kV transmission line from Rio Bravo Substation to Wormser Substation. The old line is 336.4 MCM Aluminum conductor on wood H frame structures and will be reconductored with 795 MCM ACSR conductors on steel poles. | 2002-06-15 | 2003-05-15 |  | 2201000 |  |  |  | 95% | 138kV | 138kV | 9.6 mi. | 795 MCM ACSR & 7#8 Alumoweld | Steel Single Poles | Center line Defined | 29.6 mi. |  |  | Sub Rule 25.101 (c) (2) (C) (ii) | The line is located in MEC single certified & TCC single certified service areas. | 2201000 | 0 | 2201000 |  |  | 2201000 | 0 | 0
24853426 | 138kV Nueces Bay / Whitepoint West (Dupont Ingleside) | Corpus Christi, Nueces County | Relocate one mile of line nearest Nueces Bay Sub | 2002-09-30 | 2003-04-02 |  | 355000 |  |  |  | 90% |  |  | 1 mi | 795 MOM ACSR | Tubular Steel |  |  |  |  | SUB R. 25.101(c)(2)(C)(iv) | Permit extending from Docket No. 22339 | 355000 | 0 | 355000 |  |  | 355000 | 0 | 0
24853427 | 138kV Nueces Bay / Whitepoint East (Portland) | Corpus Christi, Nueces County | Relocate .5 mile of line nearest Nueces Bay | 2002-09-30 | 2002-04-02 |  | 240000 |  |  |  | 90% |  |  | .5 mi | 795 MOM ACSR | Tubular Steel |  |  |  |  | SUB R. 25.101(c)(2)(C)(iv) | Permit extending from Docket No. 22339 | 240000 | 0 | 240000 |  |  | 240000 | 0 | 0
40097398 | Los Fresnos to Brownsville | Cameron County, TX | Relocate approximately 600' of the Los Fresnos to Brownsville 69 kV line for a new subdivision of the City of Brownsville | 2003-01-02 | 2003-01-31 |  | 155000 |  |  |  | 0% | 69kV | 69kV | 750' | 4/0 ACSR 6/1 | Single Pole | Centerline Defined | 600' | 40' | 750 | 25.101(c)(2)(C)(iii) | The City of Brownsville is paying for the relocation | 155000 | 0 | 155000 |  |  | 155000 | 0 | 0
40015548 | Hidalgo - Southeast Edinburg 6.3 mile 138kv transmission line reconductor | Hidalgo County, Texas | Reconductor the approximately 6.3 miles of existing 138kv from Hidalgo to Southeast Edinburg. The old line is 795 ACSR conductor and the new line will be 795 ACSS conductor. Poles will remain the same. | 2003-02-10 | 2003-12-12 | 2003-12-12 | 1446315 |  |  |  | 95% | 138kV | 138kV | 6.3 miles | Drake 795 MCM ACSS | Wood Single Poles | Centerline Defined | 6.3 miles |  |  | Sub Rule 25.101 (c) (5) (B) | The line is located in TCC single certified and in TCC / MVEC (Magic Valley) dual certified areas | 1446315 | 0 | 1446315 |  |  | 1446315 | 0 | 0
40083321 | Southeast Edinburg - Magic Valley Pharr 1.62 mile 138kv transmission line reconductor | Hidalgo County, Texas | Reconductor the approximately 1.62 miles of existing 138kv from Southeast Edinburg to Magic Valley Pharr. The old line is 795 ACSR conductor and the new line will be 795 ACSS conductor. Poles will remain the same. | 2003-03-31 | 2003-10-25 | 2003-10-10 | 414987 |  |  |  | 98% | 138kV | 138kV | 1.62 miles | Drake 795 MCM ACSS | Wood Single Poles | Centerline Defined | 1.62 miles |  |  | Sub Rule 25.101 (c) (5) (B) | The line is located in TCC single certified and in TCC / MVEC (Magic Valley) dual certified areas | 414987 | 0 | 414987 |  |  | 414987 | 0 | 0
AE007181 | South Mission - South McAllen 69kv to 138kv transmission line rebuild | Hidalgo County, Texas | Rebuild the existing South Mission to South McAllen 69kv transmission line to a 138kv single circuit, double circuit capable, 6 mile line using bundled 1590 MCM ACSS on steel or concrete single pole structures | 2004-06-01 | 2004-12-01 |  | 2916000 |  |  |  | 20% | 69kV | 138kV | 6 miles | 1590 MCM ACSS | Concrete or steel single pole | Centerline Defined | 6 miles |  |  | Sub Rule 25.101 (c) (5) (B) | The line is located in TCC single certified and in MVEC (Magic Valley) single certified areas | 2916000 | 0 | 2916000 |  |  | 2916000 | 0 | 0
AE007171 | Bates - South Mission 69kv to 138kv line rebuild and termination relocation | Hidalgo County, Texas | Rebuild the existing 4.18 mile 69kv Bates to South Mission transmission line to a 138kv line using 1590 MCM ACSS on steel or concrete single pole structures, and relocate the West end of the line termination point from Bates 500' to the south to the Frontera switching station | 2004-06-01 | 2004-12-01 |  | 2127000 |  |  |  | 15% | 69kV | 138kV | 4.18 miles | 1590 MCM ACSS | Concrete or steel single pole | Centerline Defined | 4.18 miles |  |  | Sub Rule 25.101 (c) (5) (B) | The line is located in TCC single certified areas | 2127000 | 0 | 2127000 |  |  | 2127000 | 0 | 0
4024695101 | North Edinburg - Hidalgo 2.8 mile 138kv transmission line reconductor | Hidalgo County, Texas | Reconductor the approximately 2.8 miles of existing 138kv from North Edinburg to Hidalgo. The old line is 795 ACSR conductor and the new line will be 795 ACSS conductor. Existing single pole structures will be replace with new single pole structures as needed. | 2004-03-15 | 2004-05-02 |  | 1352003 |  |  |  | 50% | 138 kV |  | 2.8 miles | Drake 795 MCM ACSS | Concrete or steel single pole | Centerline Defined | 2.8 miles |  |  | Sub Rule 25.101 (c) (5) (B) | The line is located in TCC single certified and in TCC / MVEC (Magic Valley) dual certified areas | 1352003 | 0 | 1352003 |  |  | 1352003 | 0 | 0
4024691301 | McColl - North McAllen 6.8 mile 138kv transmission line reconductor | Hidalgo County, Texas | Reconductor the approximately 6.8 miles of existing 138kv and convert the existing 69kv to 138kv which will result in a double circuit 138kv from McColl to North McAllen. The old line is 795 ACSR conductor and the new line will be 795 ACSS conductor. Poles will remain the same. | 2004-01-19 | 2004-05-30 |  | 1914000 |  |  |  | 10% | 138 kV and 69 kV | 138 kV both circuits | 6.8 miles | Drake 795 MCM ACSS | Wood Single Poles | Centerline Defined | 6.8 miles |  |  | Sub Rule 25.101 (c) (5) (B) | The line is located in TCC single certified area. On hold due to landowner opposition and City of McAllen concerns. | 1914000 | 0 | 1914000 |  |  | 1914000 | 0 | 0
4024696001 | Polk - Hall Acres 2.73 mile 138-kV transmission line rebuild and reconductor | Hidalgo County, Texas | Reuild and reconductor the approximately 2.73 miles of existing 138-kV from Polk Ave. to Hall Acres. The old conductor is 336 ACSR and the new conductor will be 795 ACSS. Wood structures will be replaced with steel structures. | 2004-09-15 | 2004-12-15 |  | 1352003 |  |  |  | 0% | 138 kV |  | 2.73 miles | Drake 795 MCM ACSS | Steel single pole | Centerline Defined | 2.73 miles |  |  | Sub Rule 25.101 (c) (5) (B) | The line is located in AEP-TCC single certified and in AEP-TCC / MVEC dual certified territory | 1352003 | 0 | 1352003 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0
| new projects: | 1352003 | [20 empty] | 0 | 0 | 0
[23 empty] | Actual Cost of Projects Completed This Month (Will Not Appear on Next Month Report): | Estimated Cost of Projects Completed This Month: | Estimated Cost of Projects Remaining Active This Month: | Total Estimated Cost of Projects Appearing in This Report:
[23 empty] | 0 | 0 | 84734183 | 84734183
[24 empty] | 0 | 18 | 18 | Project Count
[24 empty] | Completed | Active | Total
Note on H1: aboling: Please enter only a single integer, if possible.
Note on I1: aboling: Please enter only a single integer, if possible.
Note on M1: aboling: If applicable.
Note on N1: aboling: If applicable.
Note on X3: aboling: PUC Staff: LCRA July report shows this project 100% complete. Formula deleted to reflect that report. Projects remain only for informational purposes.
Note on X4: aboling: PUC Staff: LCRA July report shows this project 100% complete. Formula deleted to reflect that report. Projects remain only for informational purposes.

## BEPC
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost (Total) | Final Estimated Project Cost (Total) | Final Actual Project Cost (Total) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS | Estimated OR Actual Project Cost (SUBSTATION) |  | Last Month: | Current minus last month: | Cumulative Sum
00002 | Booneville to Hearne | Robertson & Brazos County | Rebuilding of approx. 23 miles of 138 kV 795 MCM line from existing Booneville sub. to existing Hearne sub. | 2003-06-01 | 2003-08-15 |  | 7989950 |  |  |  | 0% | 138 |  | 23 | 795 MCM | Single Pole Concrete | 60 | 23 |  |  | 25.101(c)(2)(C)(ii) |  | 7989950 | 0 | 7989950 |  |  | 7989950 | 0 | 0
91037 | Bridgeport - Crafton | Wise County | Construct 8.4 miles of SC & DC line built for 138kV but operated at 69kV. Constructed to avoid mining operations. | 2003-04-01 | 2003-08-25 |  | 3231600 |  |  |  | 0% | 69 | 138 | 8.4 | 4/0 ACSR | Single Pole Concrete | 60 | 5.1 |  |  | Docket No. 25288 |  | 3231600 | 0 | 3231600 |  |  | 3231600 | 0 | 0
01005 | Bunker - Waples | Hood County | Rebuild approx. 12 miles of existing 69 kV transmission line with single pole 138 kV, 795 MCM ACSR construction. | 2003-09-05 | 2004-02-25 |  | 5049300 | 4622290 |  |  | 90% | 69 | 138 | 12 | 795 MCM | Single Pole Concrete or Steel | 60 | 12 |  |  | 25.101(c)(2)(C)(ii) |  | 4622290 | 0 | 4622290 |  |  | 4622290 | 0 | 0
01006 | North Texas - Cottondale | Parker & Wise County | Rebuild approx. 26.8 miles of existing H-frame 4/0 ACSR 69 kV line with single pole 138 kV, 795 MCM ACSR construction. In addition, BEPC's Willow substation will be converted to 138 kV operation. | 2004-03-01 | 2004-06-01 |  | 7081200 |  |  |  | 50% | 69 | 138 | 26.8 | 795 MCM | Single Pole Concrete or Steel | 60 | 26.8 |  |  | 25.101(c)(2)(C)(ii) |  | 7081200 | 0 | 7081200 |  |  | 7081200 | 0 | 0
00019 | Sardis Switching Station | Ellis County | Construct a 138/69 kV switching station and rebuild approximately 6 miles of 69 kv H-frame transmission line with 138 kv single pole concrete x-line. | 2003-08-01 | 2003-11-25 |  | 5236200 | 5236200 |  |  | 100% | 69 | 138 | 6 | 795 MCM | Single Pole Concrete or Steel | 60 | 6 |  |  | 25.101(c)(5)(B) | Affidavit and easements are attached with filing | 5236200 | 0 | 5236200 |  |  | 5236200 | 0 | 0
98051 | Cedar Valley | Bell County | Construct a new single-pole concrete and/or steel 138 kV 795 MCM transmission line and in-line 138/25 9375 kVA substation with two 3-phase bays and one spare bay. | 2005-02-01 | 2005-06-17 |  | 6372650 |  |  |  | 0% | NA | 138 | 13.8 | 795 ACSR double circuit | Single Pole Concrete or Steel | NA | NA | 70 | 6.9 | Docket No. 27894 | CCN Application Filed on June 5, 2003 | 6372650 | 0 | 6372650 |  |  | 6372650 | 0 | 0
0208445 | Reno - Cottondale Switch | Wise and Parker County | Rebuild approx. 19.25 miles of existing 69 kV line with 138 kV 959 ACSS conductor. Convert Keeter 69 kV sub. to 138 kV. | 2004-02-16 | 2004-07-15 |  | 10821550 |  |  |  | 5% | 69 | 138 | 19.25 | 959 ACSS | Single Pole Concrete or Steel | 60 & 100 | 19.25 |  |  | 25.101(c)(5)(B)(i) | Affidavit attached with filing. | 10821550 | 0 | 10821550 |  |  | 10821550 | 0 | 0
01012 | Whitney - Powell | Bosque County | Rebuild approx. 14.5 miles of existing wood single pole 69 kV line with 138 kV 795 mcm construction. | 2003-09-25 | 2004-02-20 |  | 3859950 |  |  |  | 100% | 69 | 138 | 14.5 | 795 MCM | Single Pole Concrete or Steel | 60 | 14.5 |  |  | 25.101(c)(5)(B)(i) | Affidavit and landowner notice letter and list attached with filing. | 3859950 | 0 | 3859950 |  |  | 3859950 | 0 | 0
02012 | Fairview - Aledo | Hood & Parker County | Construct approximately 26 miles of new single-pole 138 kV 795 MCM transmission line from the existing radial fed BEPC Fairview substation to the existing radial fed BEPC Aledo substation. In addition, this project will include rebuilding approximately 5.8 miles of existing transmission line from the BEPC Waples substation to the BEPC Fairview substation. Also, included in the project is the construction of a switching station at Dicey and the addition of a 138 kV breaker at Waples substation. | 2005-06-15 | 2006-02-15 |  | 10752500 |  |  |  | 0% | NA | 138 | 26 | 795 MCM | Single Pole Concrete or Steel | NA | NA | 70 | 26 | Docket No. 28254 | CCN Application Filed on August 15, 2003 | 10752500 | 0 | 10752500 |  |  | 10752500 | 0 | 0
00005 | Cross Timbers | Denton County | Construct approx. 4.0 miles of 138 kV double circuit 1590 ACSR single pole concrete structures adjacent to Oncor Transmission's existing 345 kV line west of Grapevine Lake near the town of Flower Mound, Texas to connect teh proposed Cross Timbers Substation to the Brazos System | 2004-02-02 | 2004-07-31 |  | 8082900 |  |  |  | 0% | NA | 138 | 8 | 1590 ACSR | Single Pole Concrete or Steel | NA | NA | 70 or as needed | 4 | Docket No. 27144 | CCN Filed Dec. 20, 2002. I apparently failed to include this in previous construction rpts. | 8082900 | 0 | 8082900 |  |  | 8082900 | 0 | 0
02079 | Tin Top to Brock | Parker County | Rebuild approx. 8.7 miles of existing 69 kV line from Tin Top sub to Brock sub. | 2004-12-01 | 2005-06-01 |  | 2650450 |  |  |  | 0% | 69 | 138 | 8.70 mi | 795 MCM | Single Pole Concrete or Steel | 60-100 | 8.7 |  |  | 25.101(c)(5)(B) | Affidavit attached with filing. | 2650450 | 0 | 2650450 |  |  | 2650450 | 0 | 0
02084 | Bowie - St. Jo | Montague & Cooke County | Reconductor approximately 19 miles of existing 4/0 ACSR 138 kV transmission line with 795 mcm conductor. Upgrade Bowie and St. Jo to accommodate larger conductor. Replace Hardy Tap GOAB | 2004-02-15 | 2004-05-15 |  | 6007250 |  |  |  | 5% | 138 |  | 19 | 795 MCM | Single Pole Concrete or Steel | 60 & 100 | 19 |  |  | 25.101(c)(5)(B) | Affidavit attached with filing. | 6007250 | 0 | 6007250 |  |  | 6007250 | 0 | 0
96023 | Ben Hur to Perry and Ben Hur to Prairie Hill | Limestone & Falls | Rebuild approx. 11.4 miles of existing 69 kV from Ben Hur to Prairie Hill. Reconductor approx. 12.1 miles of existing 69 kV from Ben Hur to Perry and operater at 138 kV. Convert Ben Hur, Perry, and Prairie Hill to 138 kV operation. SCADA and Comm equip and motor operated switches at Dawson. | 2003-12-30 | 2004-06-01 |  | 7374350 |  |  |  | 5% | 69 | 138 | 23.50 mi | 795 MCM | Single Pole Concrete or Steel | 60-100 | 23.5 |  |  | 25.101(c)(5)(B) | Affidavit attached with filing. | 7374350 | 0 | 7374350 |  |  | 7374350 | 0 | 0
0160003 | Hwy. 114 Re-route | Wise County | Relocate approx. 2.14 miles of existing 69 kV single circuit line for widening of State Hwy. 114 at TxDOT's request | 2004-02-15 | 2004-04-30 |  | 815726 |  |  |  | 5% | 69 | 138 | 2.14 | 1/0F CWC | Single Pole Wood | 60 | 2.14 | 40 & 70 | 2.3 | 25.101(c)(5)(F) | Affidavit attached with filing. Portion of 40 foot ROW overhangs TxDOT easement | 815726 | 0 | 815726 |  |  | 815726 | 0 | 0
0208432 | Generation Plant to Wise Co. Switch | Jack and Wise | Construct a new single-pole concrete and/or steel single circuit 138 kV 959 MCM ACSS line from the new Jack Co. Generation Plant to a new Wise County Switch. The line is approximately 20 miles in length. | 2005-04-15 | 2005-08-15 |  | 7531850 |  |  |  | 0% | NA | 138 | 20 | 959 MCM ACSS | Single Pole Concrete or Steel | NA | NA | 70 | 20 | Docket No. 29020 | CCN Filed Jan. 7, 2004 | 7531850 | 0 | 7531850 |  |  | 7531850 | 0 | 0
0208426 | Generation Plant to Willow | Jack and Wise | Construct a new single-pole concrete and/or steel single circuit 138 kV 959 MCM ACSS line from the new Jack Co. Generation Plant to BEPC's existing Willow Substation with a 70 foot ROW for approx. 8.2 miles | 2004-08-15 | 2004-12-20 |  | 2268575 |  |  |  | 0% | NA | 138 | 8.2 | 959 MCM ACSS | Single Pole Concrete or Steel | NA | NA | 70 | 8.2 | Docket No. 29158 | Brazos has purchased options on easements for this project and attached to CCN application filed on Jan15, 2004 | 2268575 | 0 | 2268575 |  |  | 2268575 | 0 | 0
0208430 | Generation Plant to Joplin | Jack County | Construct a new single-pole concrete and/or steel, single circuit 138kV 795 MCM ACSR line from the Jack Co. Generating Plant to BEPC's existing Joplin Substation. The line is approximately 3.20 miles in length. | 2004-08-23 | 2004-12-10 |  | 990100 |  |  |  | 0% | 69 | 138 | 3.20 mi | 795 MCM ACSR | Single Pole Concrete or Steel | 60 | 3.2 | 70 | 3.2 | Docket No. 29198 | Brazos is purchasing options on easements for this project and will include them in this application. The CCN was filed on Jan 30, 2004. | 990100 | 0 | 990100 |  |  | 990100 | 0 | 0
0208431 | Generation Plant to Cottondale Switch | Jack & Wise | Construct a new single-pole, concrete and/or steel, single circuit 138kV 959MCM ACSS line from the Jack Co. Generating Plant to BEPC's existing Cottondale Switch. The line is approximately 5.20 miles in length. | 2005-05-02 | 2005-10-14 |  | 1981450 |  |  |  | 0% | NA | 138 | 5.2 | 959 MCM ACSS | Single Pole Concrete or Steel | NA | 5.2 | 110 | 5.2 | Docket No. 29186 | Brazos has pirchased options for easements for this project and they where included in the application. This CCN was filed on Feb 13, 2004 | 1981450 | 0 | 1981450 |  |  | 1981450 | 0 | 0
0208428 | Generation Plant to Cottondale Sw Rebuild | Jack & Wise | Rebuild approximately 5.20 miles of 138kV line from the Jack Co. Generating Plan to BEPC's existing Cottondale SW. with single concrete and/or steel poles. | 2005-05-02 | 2005-10-05 |  | 1981450 |  |  |  | 0% | 69 | 138 | 5.20 mi. | 959 MCM ACSS | Single Pole Concrete or Steel | 70 | 5.2 | 70 | 5.2 | 25.101(c)(5)(B) | Affidavit at a later date closer to scheduled construction start | 1981450 | 0 | 1981450 |  |  | 1981450 | 0 | 0
201120 | Grandview to Happy Hills Switch | Johnson | Rebuild 9.8 Miles of line from Grandview to Happy Hill Switch with 1033 MCM conductor 138kv single circuit construction | 2004-12-01 | 2005-05-01 |  | 3860000 |  |  |  | 0% | 69 | 138 | 9.8 mi. | 1033 MCM ACSR | Single Pole Concrete or Steel | NA | 9.8 | 70 | 9.8 | 25.101(c)(5)(B) | Affidavit at a later date closer to scheduled construction start | 3860000 | 0 | 3860000
|  | NEW | 3860000 | [19 empty] | 0 | 0 | 0
[23 empty] | Actual Cost of Projects Completed This Month (Will Not Appear on Next Month Report): | Estimated Cost of Projects Completed This Month: | Estimated Cost of Projects Remaining Active This Month: | Total Estimated Cost of Projects Appearing in This Report:
[23 empty] | 0 | 0 | 103511991 | 103511991
[24 empty] | 0 | 20 | 20 | Project Count
[24 empty] | Completed | Active | Total
Note on H1: aboling: Please enter only a single integer, if possible.
Note on I1: aboling: Please enter only a single integer, if possible.
Note on M1: aboling: If applicable.
Note on N1: aboling: If applicable.

## LCRA
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost (Total) | Final Estimated Project Cost (Total) | Final Actual Project Cost (Total) | % Variance | Percent Complete | Existing Voltage | Upgraded or New Voltage | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS | Estimated OR Actual Project Cost (SUBSTATION) |  | Last Month: | Current minus last month: | Cumulative Sum
1001776, 1001840 | Kunitz-Wink | Culberson, Reeves, Loving, Winkler | New 138 kV transmission line from wind plant at Kunitz to TXU Wink Substation | 2004-06-05 | 2004-11-01 |  | 30212829 |  |  |  | 0% |  | 138 | 101.5 | 3x2-795 kcmil ACSR "Drake" | Single Pole & H-frame | na | na | 100 - 160 | 101.5 | CCN Docket No. 22762 approved 7/13/01 |  | 30212829 | 0 | 30212829 |  |  | 30212829 | 0 | 0
1002622, 243801W77032 | Macedonia-Hockley TL Addition | Harris, Waller | New 138 kV transmission line and upgrade of an existing line segment from single to double-circuit, connecting the existing Macedonia Substation to a tie with ReliantHL&P near Hockley Substation | 2003-10-13 | 2004-05-15 |  | 4066464 | 4066464 |  |  | 35% | 138 | 138 | 11.98 | 3x1-959 kcmil ACSS/TW "Suwannee" | Steel and Concrete Single Pole | 60 | 2.78 | 80 | 9.2 | CCN Docket No. 24380 approved 7/5/02 | Project in two phases, first segment on existing ROW near Macedonia | 4066464 | 0 | 4066464 |  |  | 4066464 | 0 | 0
1003159 1003161 | Zorn-McCarty Lane Transmission Line Upgrade West Circuit T205 | Hays, Guadalupe | Reconductor and upgrade the Zorn-McCarty Lane, 138 kV transmission line | 2003-03-10 | 2003-12-30 | 2003-12-12 | 4802000 | 4802000 |  |  | 100% | 138 | 138 | 8.5 | 3x1-1433.6 kcmil ACSS/TW "Merrimack" | Lattice Tower | 100 | 8.53 | na | na | 25.101(c)(2)(C)(ii) | This project will be constructed in two pieces. One portion will be completed in June 03. The balance will be completed in Jan. 04. | 4802000 | 0 | 4802000 |  |  | 4802000 | 0 | 0
1004030 | Canyon-San Marcos | Hays, Guadalupe | Upgrade existing circuit from 69 kV to 138 kV, by rebuilding and reconductoring with 3x1- 795 ACSR, and tie into San Marcos Substation - scope change to 3x2-795 ACSR | 2004-02-23 | 2004-05-31 |  | 1179430 | 4283444 |  |  | 38% | 69 | 138 | 3.48 | 3x2-795 kcmil ACSR "Drake" | Single Pole | 60 | 3.48 | na | na | 25.101(c)(2)(C)(ii) and 25.101(c)(2)(C)(i) | ROW varies, centerline and 60-ft | 4283444 | 0 | 4283444 |  |  | 4283444 | 0 | 0
1003408 | North McCamey/Southwest Mesa Tap | Upton | New double-circuit capable 138 kV transmission line from North McCamey to the Southwest Mesa Tap | 2003-09-19 | 2004-05-30 |  | 2707960 | 2726238 |  |  | 98% |  | 138 | 5.6534 | 3x2-795 kcmil ACSR "Drake" (second circuit at later date) | Single Pole | na | na | 80 | 5.65 | Joint CCN w/AEP-WTU Docket No. 26758 approved 1/9/03 |  | 2726238 | 0 | 2726238 |  |  | 2726238 | 0 | 0
1003048 | Fort Lancaster/Friend Ranch | Crockett, Pecos, Terrell | New double-circuit capable 138 kV transmission line from Fort Lancaster to Friend Ranch | 2004-06-25 | 2005-06-03 |  | 20189177 |  |  |  | 0% |  | 138 | 43.37 | 3x2-795 kcmil ACSR "Drake" (second circuit at later date) | Single Pole | na | na | 80 | 43.37 | Joint CCN w/AEP-WTU Docket No. 27015 approved 3/21/03 |  | 20189177 | 0 | 20189177 |  |  | 20189177 | 0 | 0
1002908 | Twin Buttes (from Big Lake) Cut-in to Twin Buttes | Tom Green | New double-circuit capable, 138 kV transmission line from Twin Buttes Switching Station to a cut-in point on the Big Lake/SAPS transmission line and route deviation of previously approved Morgran Creek-Twin Buttes-Red Creek-Comanche 345 kV line | 2004-04-02 | 2004-07-17 |  | 8511520 | 8674000 |  |  | 0% |  | 138 | 14.6 | 3x2-795 kcmil ACSR "Drake" (second circuit at later date) | Single Pole Tangents, Multi-pole angles and deadends Lattice towers on route deviation | na | na | 80 | 7.3 | Joint CCN w/AEP-WTU Docket No. 27180 approved 9/26/03 |  | 8674000 | 0 | 8674000 |  |  | 8511520 | 162480 | 162480
1002552 1002553 | McNeil/Round Rock TL Upgrade | Travis, Williamson | Reconductor and bundle existing circuit from single 795 ACSR to bundled (two per phase) 795 ACSR, by (a) rebuilding and replacing existing construction in certain areas and (b) converting existing lattice tower segment from double-circuit to single-circuit operation using split-bundle conductors (two per phase) and relocating one existing single-795 ACSR 138 kV circuit position to an open position on adjacent poles within the same right-of-way. | 2003-12-04 | 2003-12-06 | 2003-12-06 | 2450000 | 2450000 |  |  | 100% | 138 | 138 | 11.41 | 3x2-795 kcmil, 3x1-795 kcmil ACSR "Drake" | Single Pole, Lattice Tower | 80 | 8.71 | na | na | 25.101(c)(5)(B) | ROW width varies from 80 to 100 feet This project will be constructed in two pieces. One portion be completed in June 03. The balance will be completed in Dec. 03. | 2450000 | 0 | 2450000 |  |  | 2450000 | 0 | 162480
1001709 1004792 1005095 | HiCross-to-Marshall Ford TL Addition T-142 | Travis, City of Austin | Rebuild existing line and reconductor with bundled 795 ACSR and single 959 ACSS Suwannee | 2003-03-08 | 2005-06-30 |  | 5790529.4879 | 5790529.4879 |  |  | 64% | 138 | 138 | 16.52 | 795 kcmil ACSR "Drake" | Steel , Lattice Tower, Concrete | 100 | 16.52 | 0 | 0 | 25.101(c)(5)(B) | This project will be constructed in two phases. One portion be completed in June 03. The balance will be completed in June 04. | 5790529.4879 | 0 | 5790529.4879 |  |  | 5790529.4879 | 0 | 162480
1004036 | Buttercup-to-Avery Ranch TL T-386 | Williamson | Cut in for the new Avery Ranch Substation | 2003-06-23 | 2004-01-23 | 2004-01-23 | 175000 | 175000 |  |  | 100% | 138 | 138 | 0.1 | Bundled 795 kcmil ACSR "Drake" | Single Pole, Double Circuit | na | na | na | 0.1 | 25.101(C)(5)(A) | On substation property | 175000 | 0 | 175000 |  |  | 175000 | 0 | 162480
1004037 | Avery Ranch-to-Jollyville TL T-483 | Williamson | Cut in for the new Avery Ranch Substation | 2003-06-23 | 2004-01-23 | 2004-01-23 | 175000 | 175000 |  |  | 100% | 138 | 138 | 0.1 | Bundled 795 kcmil ACSR "Drake" | Single Pole, Double Circuit | na | na | na | 0.1 | 25.101(C)(5)(A) | On substation property | 175000 | 0 | 175000 |  |  | 175000 | 0 | 162480
1004323 1005413 | TxDot-FM973 TL Relocation | Travis | T146: Adjust TL at FM973 crossing by moving one structure out of new TXDOT ROW along existing ROW. T-421: Adjust TL at FM973 crossing to increase line clearance over FM973 by replacing existing structures on either side of TXDOT ROW with taller structures. | 2003-12-15 | 2004-01-05 | 2004-01-05 | 467000 | 467000 |  |  | 100% | 138 | 138 | 0.1 | 795, 3X1 | Single Pole- Concrete, Lattice Tower | 100 | 0.1 | na | na | 25.101(C)(5)(B) and (F) |  | 467000 | 0 | 467000 |  |  | 467000 | 0 | 162480
1004068 | Salem-to-Hwy 36 TL Addition T-105 | Washington | Upgrade existing transmission line from 69 kV to 138 kV, reconductor with 959 ACSS/TW conductor, cut into new Highway 36 station, no new ROW required | 2003-07-07 | 2003-10-30 | 2003-11-14 | 1127392.3958 | 1127392 | 1161507 | 3.026% | 100% | 69 | 138 | 3 | 3x1-959 kcmil ACSS/TW "Suwannee" | Single-Pole | 100 | 3 | na | 0 | 25.101(C)(5)(B) | Line energized when Hwy 36 Substation completed Nov. 03. | 1127392 | 1127392 | 0 |  |  | 1127392 | 0 | 162480
1003590 | Hwy 36-to-Bellville N. TL Addition T-467 | Austin, Washington | Upgrade existing transmission line from 69 kV to 138 kV, reconductor with 959 ACSS/TW conductor, cut into new Highway 36 station, no new ROW required | 2003-07-07 | 2003-10-03 | 2003-11-14 | 5069508 | 5069508 | 4563545 | -9.981% | 100% | 69 | 138 | 13.49 | 3x1-959 kcmil ACSS/TW "Suwannee" | Single-Pole, H-frame | Centerline | 13.49 | na | 0 | 25.101(C)(5)(B) | Construction costs were less than expected. | 5069508 | 5069508 | 0 |  |  | 5069508 | 0 | 162480
1004719 | Bellville N.-to-Bellville S. TL Addition T-467 | Bellville/Austin | Upgrade existing transmission line from 69 kV to 138 kV, reconductor with 959 ACSS/TW conductor, no new ROW required | 2003-11-17 | 2004-01-31 | 2004-01-31 | 1153698 | 1867250 |  |  | 100% | 69 | 138 | 3.07 | 3x1-959 kcmil ACSS/TW "Suwannee" | Single-Pole, H-frame | Centerline | 3.07 | na | 0 | 25.101(C)(5)(B) | This project has been broken down into two pieces to reflect the way the work will occur (see project 1003590) | 1867250 | 0 | 1867250 |  |  | 1867250 | 0 | 162480
1003883 | Crane-Midkiff 69 kV Line, Rebuild and Convert to 138 kV | Crane, Upton | Rebuild existing 69 kV wood H-Frame line with new 138 kV single pole sutructures and one circuit of 1233.6 kcm ACSS/TW conductor | 2003-05-22 | 2003-11-07 | 2003-11-07 | 9800000 | 9800000 |  |  | 100% | 138 | na | 34.2 | 1233.6 kcm ACSS/TW | Single Circuit Single Pole Concrete | 50 | 34.2 | na | na | 25.101(c)(2)(C)(ii) | Transferred from Oncor Docket 25829 | 9800000 | 0 | 9800000 |  |  | 9800000 | 0 | 162480
1003884 | Crane-Odessa EHV 138 kV line, Rebuild and Upgrade Capacity | Crane, Ector | Rebuild existing wood H-Frame line with new 138 kV single Pole structures and one circuit of 1233.6 kcm ACSS/TW conductor, and extend line less than one mile to new Crane LCRA station | 2003-08-04 | 2004-04-01 |  | 8100000 | 8100000 |  |  | 100% | 138 | na | 31.9 | 1233.6 kcm ACSS/TW | Single Circuit Single Pole Concrete | 75 | 31.95 | 60 | 0.05 | 25.101(c)(2)(C)(ii), 25.101(C)(5)(A) and 25.101(C)(5)(B) | Transferred from Oncor Docket 25829, plus extension to Crane LCRA, one of Rio Pecos Wind Generation 138 kV Transmission Line Upgrade projects currently under construction by LCRA, Oncor and AEP. | 8100000 | 0 | 8100000 |  |  | 8100000 | 0 | 162480
1003515 | Breakoff Structure-to-Peters TL Upgrade T-217 | Austin | Rebuild and upgrade from 795 ACSR to 959 ACSS/TW | 2003-09-22 | 2003-12-12 | 2003-12-12 | 675000 | 1800000 |  |  | 100% | 138 | 138 | 5.59 | 3x1-959 kcmil ACSS/TW "Suwannee" | Single-pole | 100 | 5.59 | na | na | 25.101(C)(5)(B) |  | 1800000 | 0 | 1800000 |  |  | 1800000 | 0 | 162480
1003586 | Brenham-to-Salem TL Add T-199 | Washington | Rebuild and upgrade from 795 ACSR to 959 ACSS/TW | 2003-12-01 | 2004-01-16 | 2004-01-16 | 1235202.9121 | 1819250 |  |  | 100% | 138 | 138 | 3.2 | 3x1-959 kcmil ACSS/TW "Suwannee" | H-frame, Steel | Varies, CL - 100 | 3.2 | na | na | 25.101(C)(5)(B) |  | 1819250 | 0 | 1819250 |  |  | 1819250 | 0 | 162480
1004229 | N. McCamey-to-McElroy/N. McCamey Cut-In 2nd Ckt Addition | Crane, Upton | Add a second 138-kV circuit to the existing North McCamey to McElroy/North McCamey Cut-In transmission line | 2004-05-15 | 2004-09-07 |  | 5210242 |  |  |  | 0% | na | 138 | 25.5 mi | Bundled 795 kcmil ACSR | Single Pole, Steel or Concrete | Varies, CL - 80 | 25.5 mi | 80 | na | CCN Docket No. 27762 | Amending certain easements to 80-ft width | 5210242 | 0 | 5210242 |  |  | 5210242 | 0 | 162480
1004230 | N. McCamey-to-Rio Pecos 2nd Ckt Addition | Crane, Crockett, Upton | Add a second 138-kV circuit to the existing North McCamey to Rio Pecos transmission line | 2004-03-08 | 2004-05-28 |  | 4438050 | 2646000 |  |  | 25% | na | 138 | 9.67 | Bundled 795 kcmil ACSR | Single Pole, Steel or Concrete | Varies, CL - 80 | 9.67 | 80 | na | CCN Docket No. 27764 - approved 10/31/03 | Amending certain easements to 80-ft width | 2646000 | 0 | 2646000 |  |  | 2646000 | 0 | 162480
1005023 | Hallettsville-Yoakum City Overhaul T140 | Lavaca, DeWitt | Transmission Line Overhaul | 2003-11-17 | 2004-05-30 |  | 416424 | 416424 |  |  | 50% | 138 | 138 | 9.67 | 336 kcmil ACSR | H-frame, Wood | 100 | 16.02 | 100 | na | 25.101(C)(3) | Outage ended early; rescheduled for 1/5/04 through 3/31/03. | 416424 | 0 | 416424 |  |  | 416424 | 0 | 162480
1005027 | Lampasas-Copperas Cove Overhaul T154 | Lampasas | Transmission Line Overhaul | 2004-04-05 | 2004-06-04 |  | 271085 | 271085 |  |  | 0% | 138 | 138 | 9.67 | 795 kcmil ACSR | H-frame, Wood | 100 | 14.6 | 100 | na | 25.101(C)(3) |  | 271085 | 0 | 271085 |  |  | 271085 | 0 | 162480
1005205 | Hwy 36 (T215) Cut-in | Washington | Modify existing transmission line to split into and connect new Highway 36 station. Install one deadend structure and one doube-circuit span all on utility station property. No landowners crossed. | 2003-09-24 | 2003-10-25 | 2003-10-25 | 150000 | 150000 | 89130 | -40.58% | 100% | 138 | 138 | 0.06 | 6x1-959 kcmil ACSS/TW "Suwannee" | Single Pole, Steel | CL | 0 | na | 0.06 | 25.101(C)(5)(A) | Construction costs were less than estimated; mobilization savings realized by utilizing contract crews already in area. | 150000 | 150000 | 0 |  |  | 150000 | 0 | 162480
1004494 | San Saba-Goldthwaite TL Add T138 | San Saba | Relocate new deadend structures at San Saba station in order to clear spot to install mobile transformer to carry load for station upgrade to breaker station | 2003-09-30 | 2003-11-06 | 2003-11-06 | 150000 | 100000 | 71407 | -28.59% | 100% | 69 | 69 | 0.11 | 3x1-4/0 ACSR | Lattice Tower | CL | 0.11 | na | na | 25.101(C)(5)(B) | Labor and material costs were less than estimated. | 100000 | 100000 | 0 |  |  | 100000 | 0 | 162480
1003882 | Spraberry-Midkiff 138 kV Line, Rebuild and Upgrade Capacity | Midland, Upton | Rebuild approximately 26.2 miles of existing wood H-Frame line with new 138 kV single pole sutructures and one circuit of 1233.6 kcm ACSS/TW conductor | 2003-07-29 | 2004-01-23 | 2004-01-23 | 6850000 | 6850000 |  |  | 100% | 138 | 138 | 26.2 | 3x1-1233.6 kcmil ACSS/TW | Concrete poles | 75 | 26.2 | na | na | 25.101(c)(2)(C)(ii) | STM w/Oncor Docket No. 25829 approved 12/20/02; purchase completed 8/03. | 6850000 | 0 | 6850000 |  |  | 6850000 | 0 | 162480
1004003 | Kendall-to-Kerrville Stadium TL Add T-123 | Kendall, Kerr | Reconductor and uprate including structure modification or replacement, retensioning and replacing hardware as needed to operate at full line rating and meet or exceed electrical clearances | 11/17/03 | 2004-05-01 |  | 2374958 | 2374958 |  |  | 80% | 138 | 138 | 16.7 | 3x1-795 kcmil ACSR | Lattice Tower, Double Circuit | Varies, CL - 100 | 16.7 | N/A | N/A | 25.101(C)(5)(B) |  | 2374958 | 0 | 2374958 |  |  | 2374958 | 0 | 162480
1003958 | Comfort-to-Verde Creek TL Add T-122 | Kendall, Kerr | Reconductor the existing circuit with single 795 ACSR and new hardware. Replace or modify structures as needed (approximately 20). | 2003-11-17 | 2004-05-01 |  | 787080 | 787080 |  |  | 80% | 138 | 138 | 13.3 | 3x1-336 kcmil ACSR | Lattice Tower, Double Circuit | Varies, CL - 100 | 13.3 | N/A | N/A | 25.101(C)(5)(B) |  | 787080 | 0 | 787080 |  |  | 787080 | 0 | 162480 | 0
1005041 | Bellville South-Peters Brk-Off Structure | Austin | Reconductor from 795 ACSR to 959 ACSS/TW | 2004-02-03 | 2004-04-30 |  | 300000 | 500000 |  |  | 15% | 138 | 138 | 2.99 | 3x1-959 kcmil ACSS/TW "Suwannee" | Lattice Tower | Varies | 2.99 | na | na | 25.101(C)(5)(B) |  | 500000 | 0 | 500000 |  |  | 500000 | 0 | 162480
1003859 | SH 130 McNeil-to-Gilleland Creek TL Upgrd T147 | Travis | Transmission line relocation to accommodate the new State Highway 130 being constructed by TXDOT from Georgetown to Seguin. | 2004-06-01 | 2004-07-30 |  | 562407 |  |  |  |  | 138 | 138 | 0.47 | 795 ACSR | Steel H | 100 | 0.47 | 0 | 0 | 25.101(C)(5)(B) and (F) |  | 562407 | 0 | 562407 |  |  | 562407 | 0 | 162480
241201W76922 | Glasscock-to-Andice TL Add T413 | Williamson | Add a new 138 kV transmission line from the Glasscock substation to the Andice substation | 2005-02-01 | 2005-06-30 |  | 7459000 |  |  |  |  | N/A | 138 | 13.3 | 795 ACSR | single pole, steel or concrete | N/A | N/A | 80 | 13.3 | CCN Docket No. 28450 filed 12/22/03 |  | 7459000 | 0 | 7459000 |  |  | 7459000 | 0 | 162480
1003588 | Brenham-to-Hwy 36 TL Add T468 | Washington | Rebuild and upgrade from 795 ACSR to 959 ACSS/TW | 2004-04-19 | 2004-06-18 |  | 1819250 | 1340000 |  |  | 0% | 138 | 138 | 2.3 | 3x1-959 kcmil ACSS/TW "Suwannee" | H-frame, steel | CL | 2.3 | na | na | 25.101(C)(5)(B) |  | 1340000 | 0 | 1340000 |  |  | 1819250 | -479250 | -316770
1003552 1003553 | Kendall-to-CPS Cagnon Road Transmission Line Addition | Kendall | New 345/138 kV from CPS Cagnon Tie Point at the Kendall/Bexar county line to the Kendall Substation | 2005-06-01 | 2006-06-30 |  | 28856400 |  |  |  | 0% |  | 345 | 20 | 1590 kcmil 54/19 "Falcon | Tubular Steel Structures | 100 | 20.4 | 110-150 | 20.4 | CCN Docket No. 29065 - filed 1/30/04 | The proposed route takes advantage of existing 100 foot wide right-of-way for its entire length. However, the new facilities will require that the existing right-of-way be widened an additional 10 to 50 feet depending on the length of the span between structures. | 28856400 | 0 | 28856400 |  |  | 28856400 | 0 | -316770
1005524 | Upgrade T136 Scofield/Metric | City of Austin, Travis | Alter an existing 138 transmission line, circuit T136 McNeil-Round Rock, due to the requirements of govermental body, to accommodate installation of a traffic signal by the City of Austin. | 2004-04-26 | 2004-04-29 |  | 80000 | 80000 |  |  | 0% | 138 | 138 | 0.36 | 795 ACSR DRAKE SPLIT BUNDLE | Lattice Tower | 120 | 0.36 | na | 0 | 25.101(C)(5)(F) |  | 80000 | 0 | 80000 |  |  | 80000 | 0 | -316770
1005107 | Alcoa Sim Gideon - Elgin TL Reloc | Bastrop | Relocate circuit T260 Sim Gideon-Elgin, between structures 7/6 and 9/5, at expense of and on ROW provided by requesting party. This will accommodate the landowner's (Alcoa's) Three Oaks Mine project and involves the removal of 1.78 miles of existing line. | 2004-05-17 | 2004-06-11 |  | 865310 |  |  |  | 0% | 138 | 138 | 2.35 | 795 ACSR DRAKE | Wood H-frame Tangents, 3-Pole Steel Deadend, 3-Pole Guyed Wood Deadend & Angle | na | 0 | 80 | 2.35 | 25.101(C)(5)(D) |  | 865310 | 0 | 865310 |  |  | 865310 | 0 | -316770
1004648 | Ferguson-Pitsburg TL T-193 | Llano, City of Llano | Extend transmission line to new installation within substation; modify and replace existing segment of transmission line located within the Pitsburg Substation to accommodate substation expansion. | 2004-03-08 | 2004-05-07 |  | 200000 | 200000 |  |  | 68% | 13800% | 13800% | 0.073295 | 3x1-795 ACSR "Drake" | Single Pole, Steel and Concrete | substation property | 0.026136 | substation property | 0.047159 | 25.101(C)(5)(A) and 25.101(C)(5)(B) | Inadvertantly left off January 2004 and subsequent Monthly CPR's. Affidavit of landowner notification not required. Work located inside substation on recently purchased property. Work began in March. | 200000 | 0 | 200000 |  |  | #N/A | #N/A | #N/A
1005012 | Yoakum-to-Flatonia TL Reloc | DeWitt, City of Yoakum | Relocate an existing transmission line segment (LCRA TSC Circuit T134), due to requirements of the City of Yoakum and Yoakum ISD | 2004-06-01 | 2004-09-15 |  | 409000 |  |  |  | 0% | 6900% | 6900% | 0.29 | 3x1-336 ACSR "Linnet" | Single Pole, Steel | CL | 0.19 | 60 | 0.29 | 25.101(C)(5)(F) |  | 409000 | 0 | 409000 |  |  | #N/A | #N/A | #N/A
1005709 | Luling-to-Flatonia TL Add | Gonzales | Modify existing transmission line segment and replace conductor segment to accommodate PWT upgrade at Harwood Substation. | 2004-06-01 | 2004-07-30 |  | 120000 |  |  |  | 0% | 6900% | 6900% | 0.24545 | 3x1-4/0 ACSR "Penguin" | H, Lattice, Pole; Wood and Steel | 100 | 0.25 | na | na | 25.101(C)(5)(A) and 25.101(C)(5)(B) |  | 120000 | 0 | 120000 |  |  | #N/A | #N/A | #N/A
|  | NEW: | 729000 | [19 empty] | 0 | 0
[23 empty] | Actual Cost of Projects Completed This Month (Will Not Appear on Next Month Report): | Estimated Cost of Projects Completed This Month: | Estimated Cost of Projects Remaining Active This Month: | Total Estimated Cost of Projects Appearing in This Report:
[23 empty] | 5885589 | 6446900 | 166346087.4879 | 172792987.4879
[24 empty] | 4 | 34 | 38 | Project Count
[24 empty] | Completed | Active | Total
Note on H1: aboling: Please enter only a single integer, if possible.
Note on I1: aboling: Please enter only a single integer, if possible.
Note on M1: aboling: If applicable.
Note on N1: aboling: If applicable.

## EPE
[13 empty] | RIGHT OF WAY | [9 empty] | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS
EPE PROJECT NUMBER | PROJECT NAME | LOCATION | DESCRIPTION | START DATE | FINISH DATE | ESTIMATED | FINAL | VAR. (%) | % COM | Length | CONDUCTOR | STRUCTURE | W | L | W | L | RULE SECTION AND/OR PUC CONTROL NUMBER | COMMENTS | COMPLETED PROJECTS | ACTIVE PROJECTS | DATE APPROVED | REQUESTED ADDITIONAL INFORMATION | VAR. (%) | VAR. (%) | 0
1240 | Montwood to Coyote 115kV Line (12600 Line) | El Paso County | As a part of the overall Eastside Expansion Plan, a new line is to be constructed between Montwood and Coyote Substations. The new line will be constructed utilizing single pole steel structures. The preferred route is approximately 7.8 miles in length. | 2002-04-01 | 2005-04-30 | 2689462.61 |  |  |  | 7.84 Miles | 954 ACSR | 90' galvanized steel single pole structures. | 120' platted road rights of way | 0.29 miles | 100', 10 to15' | 2.94 mile, 4.61mi. (overhang) | 24666 | Right of Way acquisition complete. Work Orders to be updated and materials ordered. Construction scheduled to begin in 2005 |  | 2689462.61 |  |  |  | 0
1251 | Rio Bosque Substation & 8400 Line Tap | El Paso County | Construct approximately 0.68 mile of double circuit 69kV transmission line on single pole structures to provide service to the proposed Rio Bosque Substation. The project is intended to serve new load growth and facilitate the retirement of an existing substation. | 2003-06-18 | 2004-05-24 | 2697136 |  |  | 97% | 1.36 miles | 954 ACSR | 95' galvanized steel single pole structures. | various platted road rights of way, existing 79' EPE Right of Way | 0.023 mile, 0.102 mile | 60', 50', 30' | 0.10 mile, 0.227 mile, 0.225 mile | 26230 | Finishing communications work. Distribution contractor to begin installing getaway ducts 4/19. Expect getaways to be installed by 5/21/04. Testing to begin week of 5/17/04. |  | 2697136 |  |  |  |  | 0
1161 | Santa Teresa - Montoya 115 kV Line | El Paso County & Dona Ana County, New Mexico | Construct approximately 7.19 miles of 115kV transmission line on single pole structures to complete an electrical loop between Santa Teresa Substation (Dona Ana County, NM.) and Montoya Substation (El Paso County, TX). The project is intended to improve service reliability and provide for future electrical load growth in the project area. | 2006-01-11 | 2006-06-30 | 5774930 |  |  |  | 7.19 miles | 954 ACSR | 95' galvanized steel single pole structures. | various platted road rights of way adjacent to proposed centerline | 2.29 miles | 25', 50', 100' | 2.29 miles, 4.76 miles, 0.14 mile | 26670 | Corrected typo on start date. Date was listed as 11/1/2006. ROW and easments being acquired. |  | 5774930 |  |  |  | 0
1133 | Rio Grande - Sunset 5500/5600 Line Rebuild | El Paso County | A significant portion of these lines currently traverse an active quarry area. EPE and the property owner have discussed the possibility of relocating lines through this property, but it will be some time before the preferred location is suitable for placing permanent structures. In the meantime, EPE will replace wood structures with steel structures at critical points along the existing line route. A portion of the replacements will take place in 2004, the remainder in the first half of 2005. | 2004-06-21 | 2005-05-30 | 436000 |  |  |  | (A) 5500 Line 4.78 miles (B) 5600 Line 5.32 miles | 4/0 Copper | 65' to 95' galvanized steel structures. Some will be replacement H-Frame structures, others will be replaced with monopole structures. | 50' | (A) 4.78 miles (B) 5.32 miles | N/A | N/A | 25.101(c)(5)(B) |  |  | 436000 |  |  | 0 | 0 | 0
1279 | Ascarate - Sunset North 19500 Line Rebuild | El Paso County | Replace existing wood structures with steel monopole structures. | 2004-08-02 | 2004-10-29 | 614000 |  |  |  | 7.98 miles | 556 ACSR | Existing single pole wood structures range from 65' to 75' in height. Structures will be replaced with 85' to 95' steel single pole structures. | Varies. Majority of line built in and along dedicated streets and alleys. Overhang and crossing permits previously obtained for original line construction. | 7.98 miles |  |  | 25.101(c)(5)(B) |  |  | 614000 |  |  | 0 | 0 | 0
|  | NEW: | 1050000 | [16 empty] | 0 |  |  |  | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[19 empty] | 0 | 12211528.61 | 12211528.61
NEW
EXISTING
CONSTRUCTION COSTS
NEW
EXISTING
CONSTRUCTION COSTS

## EGSI
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost (Total) | Final Estimated Project Cost (Total) | Final Actual Project Cost (Total) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS | Estimated OR Actual Project Cost (SUBSTATION) |  | Last Month: | Current minus last month: | Cumulative Sum
CEA TL3429 | Line 820 - 138 kV Transmission line between Conroe Bulk and Forest Substations | Montgomery County | Construct a 138 kV Transmission Line 820 from Conroe Bulk to the site of the new Forest Substation to support load growth in Montgomery County, Texas | 2002-02-01 | 2002-06-01 |  | 3837000 | [5 empty] | 138 | 5.6 | 666 ACSR Bundled | Concrete or Steel Single Pole Structures |  |  | 80 | 5.6 | PUCT Docket No. 23429 | Union Pacific RR is installing mitigation grounding to address concrens about signaling. R/W clearing and Construction have begun. A temporary injuction has been issued for the section of L-820 adjacent to Harper's Landing Subdivision. A court Date of May 10, 2004 has been set for the trial on the permanent injunction. | 3837000 | 0 | 3837000 |  |  | 3837000 | 0 | 0
TL-3622 | Kinder-Morgan - Copeland Switch Station Line-571 Tap | Montgomery County, TX | Cut Line 571 into and out of new Copeland Switchyard | 2002-10-02 | 2003-04-09 |  | 401888 |  |  |  | 40% | 138 |  | 0.21 | 666 ACSR Bundled | 5 Concrete Poles | 100 | 0.1 |  |  | §25.101(c)(2)(C)(i) | This project has been cancelled. The line configuration has changed and will be reported on a later monthly report when the enginering and estimates are complete. Working on finalizing the costs for this project. | 401888 | 0 | 401888 |  |  | 401888 | 0 | 0
TL3560 | L-822 China to Porter 230KV Line | Jefferson, Liberty, Harris and Montgomery Counties | Construct 230KV single pole line from China Substation to the new proposed Porter Substation | 2004-04-01 | 2005-05-01 |  | 26953590 | [5 empty] | 230 | 65 | 954 ACSR | Concrete or Steel Poles | 212 | 65 |  |  | Docket No. 27145 | CCN Application filed 12-20-03 CCN approved on 03-25-03 | 26953590 | 0 | 26953590 |  |  | 26953590 | 0 | 0
TL3608 | L-422 Amelia to Helbig Rebuild 10.27 Mi. of 230KV | Jefferson County, Texas | Replace 71 structures and reconductor 7.4 miles of 795AA with bundled 666 ACSR | 2003-05-08 |  |  | 3638796 |  |  |  | 100% | 230 |  | 7.4 | 666ACSR Bundled | 71 Steel poles | 150 & 185 | 10.27 |  |  | 25.101(c)(5)(B)(i) | Working on finalizing the costs. | 3638796 | 0 | 3638796 |  |  | 3638796 | 0 | 0
TL3602 | L-6 Amelia to Sour Lake Rebuild a section of line | Hardin County | Replace 65 Structures and reconductor 8.4 Miles of 2/0 CU w/ 666 ACSR. | 2003-07-15 |  |  | 1713311 |  |  |  | 100% | 69 |  | 8.4 | 666 ACSR | 65 Concrete |  | 8.4 |  |  | 25.101(c)(5)(B)(i) |  | 1713311 | 0 | 1713311 |  |  | 1713311 | 0 | 0
| NGPL (Kinder Morgan) to Devers 138 kV Line | Liberty County | Build a 4 mile long 138 kV Transmission Line which will tie into existing L-424 and will provide a dual feed into the new Devers Marsh Switchyard | 2004-01-05 | 2004-04-30 |  | 2333000 | [5 empty] | 138 | 8 | 1272 ACSR (Bittern) | Concrete or Steel |  |  | 100 | 4 | Docket No. 27607 | CCN Application approved July 11th, 2003 ROW Clearing and Construction to begin on week of 3/22/2004 | 2333000 | 0 | 2333000 |  |  | #N/A | #N/A | #N/A
TL4370 | Air Products cut-in L-427 | Jefferson County, Texas | Construct .2 Miles of single pole double circuit 69kV to the new Pine Street Substation to serve Air Products. | 2003-10-01 | 2003-12-10 |  | 519000 |  |  |  | 100% | 69 |  | 0.2 | 795AA | Steel |  |  | 50 | 0.2 | 25.101(c)(5)(A)(i) | Working on finalizing the costs. | 519000 | 0 | 519000 |  |  | 519000 | 0 | #N/A
TL4371 | Alligator Bayou Cut-in | Jefferson County, TX | Cut 69kV line 473 into new customer owned substation. | 2003-11-24 | 11-31-03 |  | 182414 |  |  |  | 100% | 69 |  | 0.03 | 954ACSR | 3 Concrete Poles |  |  | 200 | 0.03 | 25.101(c)(5)(A)(i)(ii) | Working on finalizing the costs. | 182414 | 0 | 182414 |  |  | 182414 | 0 | #N/A
TL4372 | L-473 & L-805 Reroute | Jefferson County, TX | Rconfigure L-473 & L-805 where the two lines intersect | 2003-11-11 | 2003-11-14 |  | 361202 |  |  |  | 100% | 69 |  | 0.01 | 795AA | 1 Concrete Pole | 50 | 0.01 |  |  | 25.101(c)(5)(B)(i) & | Working on finalizing the costs. | 361202 | 0 | 361202 |  |  | 361202 | 0 | #N/A
TL4373 | L-473 & L-805 Reroute | Jefferson County, TX | Rconfigure L-473 & L-805 where the two lines intersect | 2003-11-11 | 2003-11-14 |  | 178788 |  |  |  | 100% | 69 |  | 0.01 | 795AA | 1 Concrete Pole | 50 | 0.01 |  |  | 25.101(c)(5)(B)(i) | Working on finalizing the costs. | 178788 | 0 | 178788 |  |  | 178788 | 0 | #N/A
TL4398 | L-828 Rebuild and Reconductor | Jefferson County, TX | Rebuild & reconductor 138kV L-828 from Str. 12 to Str. 34. Relocate a section inside the ExxonMobil Refinery to make room for the cut-in of L-457 into Carroll Street Park Sub. | 2004-02-01 |  |  | 1025857 |  |  |  |  | 138 |  | 1.25 | 1590ACSR | 23 Concrete and Steel Poles | 50 | 0.3 | 50 | 0.95 | 25.101(c)(5)(B)(i) and 25.101(c)(5)(D)(i)(ii) | This project involves two Phases. Phase I will start 2-1-04 and Phase II will start 11-1-04. All new R/W is entirely on ExxonMobil property. | 1025857 | 0 | 1025857 |  |  | 1025857 | 0 | #N/A
GS0148 | Dayton-Gordon Construct New 138kV transmission line. | Liberty County, TX | Construct new 138kV single pole single circuit transmission line for Coastal Water Authority to their Trinity River Pumping Station | 2005-12-15 |  |  | 10370000 | [5 empty] | 138 | 11.4 | 666ACSR | Concrete and Steel Poles |  |  | 100 | 11.4 | Docket No. 28938 | CCN Application Filed 1-9-04. Docket was sent to SOAH. Interveners have signed a settlment agreement. | 10370000 | 0 | 10370000 |  |  | 10370000 | 0 | #N/A
TL4397 | Cut 138kV L-457 into and out of Carroll Street Park Switching Station | Jefferson County | Construct 1.57 miles of single pole double circuit 138kV transmission line from existing L-457 to Carroll Street Park Switching Station for ExxonMobil. This project is entirely on ExxonMobil property. | 2004-05-03 |  |  | 1700000 |  |  |  |  | 138 |  | 3.14 | 1590ACSR | 35 Concrete & Steel Poles |  |  | 80 | 1.57 | Docket No. 29079 | CCN Application Filed 1-30-04. One intervener is still in the case. A prehearing conference is set for 4-19-04. | 1700000 | 0 | 1700000 |  |  | 1700000 | 0 | #N/A
[8 empty] | 0 | [14 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[8 empty] | 0 | [14 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
0
0
0
0
0
0
0
[23 empty] | Actual Cost of Projects Completed This Month (Will Not Appear on Next Month Report): | Estimated Cost of Projects Completed This Month: | Estimated Cost of Projects Remaining Active This Month: | Total Estimated Cost of Projects Appearing in This Report:
[23 empty] | 0 | 0 | 53214846 | 53214846
[24 empty] | 0 | 13 | 13 | Project Count
[24 empty] | Completed | Active | Total
Note on H1: aboling: Please enter only a single integer, if possible.
Note on I1: aboling: Please enter only a single integer, if possible.
Note on M1: aboling: If applicable.
Note on N1: aboling: If applicable.

## MVEC
MVEC PROJECT NUMBER | PROJECT NAME | LOCATION | DESCRIPTION | START DATE | FINISH DATE | ESTIMATED | FINAL | VAR. (%) | % COM | Length | CONDUCTOR | STRUCTURE | W | L | W | L | RULE SECTION AND/OR PUC CONTROL NUMBER | COMMENTS | COMPLETED PROJECTS | ACTIVE PROJECTS | DATE APPROVED
| Alton 138kV Circuit Tie Line | Hidalgo | 2.4 Miles 138kv Transmission Line | Delayed - April 1, 2004 | Delayed - Dec. 1, 2004 | 2610000 |  |  | 0% | 2.4 miles | 795 ACSS | Single pole - concrete pole |  |  | 50' | 6336' | 28895 | Approved by PUC on March 15, 2004 |  | 2610000
| North Edinburg to West Edinburg 138kV Line Rebuild and Second Circuit | Hidalgo | 9.1 Miles 138kv Transmission Line | Sept. 1, 2004 | Feb. 1, 2005 | 2600000 |  |  | 0% | 9.1 miles | 795 ACSS | Single pole - concrete pole |  |  | 50' | 29040 | 29225 | CCN Filed on March 2004 |  | 2600000
1972336 | Kenaf Plant | Willacy | 6.5 Miles 138kv Transmission Line | Delayed - May not be built | Delayed - May not be built | 1550000 |  |  | 0% | 6.5 miles | 795 ACSR | Single pole - concrete pole with steel davit arms |  |  | 25' | 3600' | 19577 | No change during the past month - MVEC has stopped all work related to this line until the Cooperative has assurances that the new load is going to materialize |  | 1550000
0
0
0
0
0
0
0
0
0
0
[19 empty] | 0 | 6760000 | 6760000
NEW
EXISTING
CONSTRUCTION COSTS
NEW
EXISTING
CONSTRUCTION COSTS

## ONCOR
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost (Total) | Final Estimated Project Cost (Total) | Final Actual Project Cost (Total) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS | Estimated OR Actual Project Cost (SUBSTATION) |  | Sort | Last Month: | Current minus last month: | Cumulative Sum
00T64047 RP | N. Herty-E. Lufkin 138 kV Reconductor Project | City of Lufkin | Reconductor 138 kV circuit from North Herty Switch Station to East Lufkin Substation with 1590 kcmil ACSR. Replace steel poles with hybrid concrete/steel poles. H-Frame portion will be rebuilt with single pole concrete construction. Steel lattice portion of the line will be analyzed for the addition of a second circuit | 2005-01-02 | 2005-05-15 |  | 2033323 |  |  |  | 0 | 138 | na | 9.5 | 1590 kcmil ACSR | Concrete Poles | 100 | 9.5 | na | na | 25.101(c)(2)(C)(ii) | Oncor has determined that this project will not be needed until approximately 2005. | 2033323 | 0 | 2033323 |  |  | 1 | 2033323 | 0 | 0
02T65054 BW/SEI | Singleton Blvd. West Levee-West Dallas 138 kV | City of Dallas, Dallas County | Relocate and replace 39 wood poles with concrete poles to accommodate widening of Singleton by Dallas Co. | 2003-06-16 | 2004-02-02 | 2004-02-02 | 534772 | 534772 |  |  | 100 | 138 | na | 1.82 | 652.4 kcmil AAC | Concrete Poles | na | na | na | na | 25.101(c)(2)(C)(v) | On City of Dallas property by permit. Final costs accumulating. | 534772 | 0 | 534772 |  |  | 2 | 534772 | 0 | 0
03T62017 RP/FC | Everman-Handley 138 kV, NE Circuit Rebuild | City of Ft. Worth, Tarrant County | Rebuild 8.94 miles of 138 kV with bundled 1033.5 kcmil ACSR. Replace lattice towers, add LDS switches at Oak Hill, Tate Springs, and Bowen Taps | 2003-01-15 | 2004-02-10 | 2004-02-10 | 7083801 | 7083801 |  |  | 100 | 138 | na | 8.94 | 1033.5 kcmil ACSR Bundled | Steel Poles and Concrete Poles | 75 | 8.94 | na | na | 25.101(c)(2)(C)(ii) | Interim Report filed 12/13/02. Final costs accumulating. | 7083801 | 0 | 7083801 |  |  | 3 | 7083801 | 0 | 0
03T62018 RP/FC | Everman-Handley 138 kV, SW Circuit Rebuild | City of Ft. Worth, Tarrant County | Reconductor 8.94 miles of 138 kV with bundled 1033.5 kcmil ACSR, add 1 LDS Switch at Oak Hill Tap and 1 at Tate Springs Tap | 2003-01-15 | 2004-02-10 | 2004-02-10 | 3500551 | 3500551 |  |  | 100 | 138 | na | 8.94 | 1033.5 kcmil ACSR Bundled | Use Single Pole DC Tangents from WA 03T62017 | 75 | 8.94 | na | na | 25.101(c)(2)(C)(ii) | Interim Report filed 12/13/02. Final costs accumulating. | 3500551 | 0 | 3500551 |  |  | 4 | 3500551 | 0 | 0
02T65022 RC | Greenville Avenue-Blackwell 138 kV Line | City of Dallas, Dallas County | Rebuild 1.9 miles of Greenville ave.-Blackwell 138 kV Line using bundled 1033.5 kcmil ACSR conductors | 2003-08-18 | 2003-11-14 | 2003-11-14 | 1227392 | 2389972 |  |  | 100 | 138 | na | 3.8 | 1033.5 kcmil ACSR Bundled | Steel Poles and Concrete Poles | 60 | 1.9 | na | na | 25.101(c)(2)(C)(ii) | Final costs accumulating. | 2389972 | 0 | 2389972 |  |  | 5 | 2389972 | 0 | 0
02T63031 ALK | Sun-Brand 138 kV line, Relocate at Sun Substation | Scurry County | Remove 100 feet of transmission line & a multipole angle structure outside of the Sun Substation to accommodate the relocation of a dead end structure. | 2003-10-14 | 2003-10-21 | 2003-10-21 | 71612 | 71612 |  |  | 100 | 138 | na | na | 636 kcmil ACSR | Wood Poles | 75 | na | na | na | 25.101(c)(2)(C)(i) | Final costs accumulating. | 71612 | 0 | 71612 |  |  | 6 | 71612 | 0 | 0
03T65029 WB | Liggett-Norwood 138 kV Double Circuit line: Reconductor with ACSS/TW | Dallas County | Reconductor 6.5 miles of double circuit 138 kV line with 959.6 kcmil ACSS/TW and raise 10 structures for elevated temperature operation. | 2003-04-01 | 2003-10-03 | 2003-10-03 | 1545700 | 1545700 | 1684842 | 9.0019 | 100 | 138 | na | 13 | 959.6 kcmil ACSS/TW | Steel Towers | 50 | 6.5 | na | na | 25.101(c)(2)(C)(ii) |  | 1545700 | 1545700 | 0 |  |  | 7 | 1545700 | 0 | 0
02T65027 ALK | Calumet - West Dallas 138 kV: Connect Westmoreland North Substation | City of Dallas, Dallas County | Relocate one existing steel pole and connect new substation. | 2005-04-15 | 2005-05-15 |  | 74400 |  |  |  | 0 | 138 | na | 0.2 | 795 kcmil ACSR | Steel Poles | 80 | 0.2 | na | na | 25.101(c)(5)(A) |  | 74400 | 0 | 74400 |  |  | 8 | 74400 | 0 | 0
02T61036 SEI/BW | Holliday-Dundee 69kV / US 277 Holliday Bypass | City of Holliday, Archer County. | Remove 4 wood poles and replace with 5 new concrete poles to reroute line across new TXDOT 400' ROW | 2003-12-15 | 2003-12-20 | 2003-12-20 | 96599 | 96599 |  |  | 100 | 69 | na | 0.17746 | 4/0 ACSR | Concrete Poles | na | na | 100 | 0.1017 | 25.101(c)(5)(F) | .08 miles installed with permit. Final costs accumulating. | 96599 | 0 | 96599 |  |  | 9 | 96599 | 0 | 0
03T61002 BJP/BW | Cleburne-Ft. Worth 138 kv Line: Tower Relocations for the City of Burleson | City of Burleson, Johnson County | Relocate and raise in height 3 steel lattice towers. | 2003-10-01 | 2003-11-14 | 2003-11-14 | 218000 | 164000 |  |  | 100 | 138 | na | 0.5 | 795 kcmil ACSR | Steel Towers | 100 | 0.5 | na | na | 25.101(c)(5)(F) | This project is at the request of the City of Burleson to enable road construction. Final costs accumulating. | 164000 | 0 | 164000 |  |  | 10 | 164000 | 0 | 0
03T65019 RC/TW | Denton Dr.-Morrison 138 kV Transmission Line Rebuild Project | City of Dallas, Dallas County | Rebuild existing double circuit steel tower line. Replace steel towers with single steel poles to accomodate a larger conductor. Line to be rebuilt on the existing centerline within the existing ROW. | 2003-08-18 | 2004-04-20 |  | 4500000 | 6103518 |  |  | 90 | 138 | na | 6.6 | 1033.5 kcmil ACSR Bundled | Steel Poles | 100 | 3.3 | na | na | 25.101(c)(5)(B) |  | 6103518 | 0 | 6103518 |  |  | 11 | 6103518 | 0 | 0
03T65022 WB | Cumby-Cumby Tap 69 kV Transmission Line Rebuild Project | Hopkins County | Rebuild existing single circuit wood pole line. Replace single wood poles with concrete poles to accomodate a larger conductor. Line to be rebuilt within the existing right-of-way. | 2003-09-15 | 2003-11-15 | 2003-11-15 | 1700000 | 1280000 |  |  | 100 | 69 | na | 4.61 | 336.4 kcmil ACSR | Steel Poles | 100 | 4.61 | na | na | 25.101(c)(5)(B) | Final costs accumulating. | 1280000 | 0 | 1280000 |  |  | 12 | 1280000 | 0 | 0
03T6011 SEI/BW | Coppell-Apollo Rd 69kV | City of Carrollton, Dallas County | Remove two poles and conductor for NTTA construction of President George Bush Turnpike and remaining poles and conductor at request of Sandy Lake Park owner. | 2003-11-03 | 2003-12-10 | 2003-12-10 | 35155 | 35155 |  |  | 100 | 69 | na | 0.81061 | 4/0 ACSR | Wood Poles | 70 | 0.81061 | na | na | 25.101(c)(5)(F) | Final costs accumulating. | 35155 | 0 | 35155 |  |  | 13 | 35155 | 0 | 0
02T65106 MM | East Levee-Indusrial 138 kV: Reconductor | City of Dallas, Dallas County | Reconductor the E. Levee-Industrial 138 kV with 959.6 kcmil ACSS/TW conductor | 2003-09-01 | 2003-12-30 | 2003-12-30 | 203300 | 1050114 |  |  | 100 | 138 | na | 3.03 | 959.6 kcmil ACSS/TW | Steel Towers | 100 | 3.03 | na | na | 25.101(c)(5)(B) | Final costs accumulating. | 1050114 | 0 | 1050114 |  |  | 14 | 1050114 | 0 | 0
03T62053 MM | Brownwood-Bangs 69 kV | Coleman County | Reconstruct approximately 15.56 miles of existing single circuit 69 kV wood pole transmission line utilizing double circuit steel and concrete poles. Add new 138 kV circuit to rebuilt structures. | 2003-08-05 | 2004-03-05 | 2004-03-05 | 5312626 | 4238100 |  |  | 100 | 69 | 138 | 15.56 | 795 kcmil ACSR | Steel Poles and Concrete Poles | 30+/- | 15.56 | 15 | 2.03 | 25.101(c)(5)(B) and (C) | Additional 15' ROW width acquired for a distance of .47 miles. Final costs accumulating. | 4238100 | 0 | 4238100 |  |  | 15 | 4238100 | 0 | 0
02T65124 BJP/MM | Paris-Clarksville 69 kV line rebuild | Red River County | This transmission line is being rebuilt in two sections. The first section extended from Bagwell to Clarksville and was completed during 2003. The second section will extend from Lamar Blossom to Bagwell and will be complete by the end of 2004. The construction will consist of wood poles, 336.4 kcmil ACSR conductor with no static. | 2003-06-01 | 2004-12-31 |  | 1604667 | 1604667 |  |  | 50 | 69 | na | 19.11 | 336.4 kcmil ACSR | Wood Poles | na | 19.11 | na | na | 25.101(c)(5)(B) | The scope of this project has changed to include the extension of this rebuild to an additional section of this transmission line. Initial Estimated Project Cost has been revised. | 1604667 | 0 | 1604667 |  |  | 16 | 399943 | 1204724 | 1204724
03T62075 JB | Primrose - Wedgewood 138 kV: Upgrade Capacity | City of Fort Worth,Tarrant County | Rebuild and upgrade the capacity of the existing line. | 2003-10-09 | 2003-12-23 | 2003-12-30 | 1972000 | 2200000 |  |  | 100 | 138 | na | 2.15 | 1033.5 kcmil ACSR Bundled | Steel Poles and Concrete Poles | 50+/- | 2.15 | na | na | 25.101(c)(5)(B) | No new easements required. Interim Report filed 6/27/2003. Final costs accumulating. | 2200000 | 0 | 2200000 |  |  | 17 | 2200000 | 0 | 1204724
03T63049 DRC | Morgan Cr. - Mulberry Cr. 345 kV: Line Changes for LCRA Bitter Cr. Sw. Station | Nolan County | Connect the existing 345 kV circuit to two new steel angle towers and relocate one existing steel pole. | 2003-09-15 | 2003-10-31 | 2003-10-31 | 175000 | 175000 | 87096 | -50.2309 | 100 | 345 | na | 0.1 | 795 kcmil ACSR Bundled | Steel Poles | 150 | 0.1 | na | na | 25.101(c)(5)(A) |  | 175000 | 175000 | 0 |  |  | 18 | 175000 | 0 | 1204724
03T65121 MM | Parkdale-Cedar Crest and Sargent Rd.-Watermill 138 kV | City of Dallas, Dallas County | Rearrange circuits at tap point in the Parkdale-Sargent Rd. 138 kV Line to eliminate wood poles which will improve reliability and operational safety. | 2004-03-01 | 2004-03-18 | 2004-03-18 | 66810 | 66810 |  |  | 100 | 138 | na | 0.01 | 927.2 kcmil ACAR | Steel Tower | 100 | 0.01 | na | na | 25.101(c)(2)(C)(ii) | Final costs accumulating. | 66810 | 0 | 66810 |  |  | 19 | 66810 | 0 | 1204724
03T65118 MM | Industrial-Sargent Rd. 138 kV: Reconductor | City of Dallas, Dallas County | Reconductor a portion of the existing 138 kV circuit from Industrial Switching Station to the proposed Sargent Road Switching Station with 959.6 kcmil ACSS/TW conductor. Also, modify the line to provide service to the proposed Sargent Road Switching Station. All line modifications will occur on property owned by Oncor. | 2003-10-01 | 2004-03-18 | 2004-03-18 | 400904 | 405200 |  |  | 100 | 138 | na | 0.6 | 959.6 kcmil ACSS/TW | Steel Tower | 100 | 0.6 | na | na | 25.101(c)(2)(C)(i), 25.101(c)(2)(C)(ii) | Final costs accumulating. | 405200 | 0 | 405200 |  |  | 20 | 405200 | 0 | 1204724
03T65109 BM | Valley Switch-Anna Switch 345 kV Upgrade for elevated temperature operation | Collin County, Grayson County, and Fannin County | Construction consists of reconductoring approximately 26.5 miles of an existing bundled 345 kV single circuit steel transmission line between the Valley Switching Station and the Anna Switching Station with be 959.6 kcmil ACSS/TW bundled and designed to operate at 180 degrees C. Additionally approximately 30 lattice towers will need to be either raised or relocated to maintain adequate clearances. | 2003-08-18 | 2003-11-15 | 2003-11-15 | 6341000 | 5753953 |  |  | 100 | 345 | na | 26.5 | 959.6 kcmil ACSS/TW Bundled | Steel Towers | 170 | 26.5 | na | na | 25.101(c)(5)(B) | Interim Report filed 07/03/2003. Final costs accumulating. | 5753953 | 0 | 5753953 |  |  | 21 | 5753953 | 0 | 1204724
03T64044 FC | Round Rock - Round Rock Westinghouse 138kV | City of Round Rock, Williamson County | Reconductor 2.50 miles of existing 336 kcmil ACSR conductor on wood H-frames with 959.6 kcmil ACSS/TW. | 2003-10-20 | 2003-10-31 | 2003-10-31 | 1343000 | 675473 |  |  | 100 | 138 | na | 2.5 | 959.6 kcmil ACSS/TW | Concrete Poles | 85 | 2.5 | na | na | 25.101(c)(5)(B) | Final costs accumulating. | 675473 | 0 | 675473 |  |  | 22 | 675473 | 0 | 1204724
03T63003 TP | Eskota - S. Abilene 138 kV: Rebuild | Nolan County | Rebuild the 5.61 Eskota - S. Abilene 138kV line using concrete H-Frame structures, and 795 kcmil ACSR conductor. | 2003-09-01 | 2003-10-12 | 2003-10-12 | 1201960 | 1201960 | 1379437 | 14.7656 | 100 | 138 | na | 5.61 | 795 kcmil ACSR | Concrete H-Frames | na | 5.61 | na | na | 25.101(c)(5)(B) | Labor estimate did not adequately cover long distance mobilizations. | 1201960 | 1201960 | 0 |  |  | 23 | 1201960 | 0 | 1204724
03T62072 BM | Handley Switch-Haltom 138 kV Reconductor for elevated temperature operation | City of Fort Worth,Tarrant County | Construction will consist of reconductoring approximately 9.9 miles of an existing 138 kV single circuit line on double circuit steel towers between the Handley Switching Station and the Haltom Sub Tap. The new conductor will be 1233.6 kcmil ACSS/TW and designed to operate at 180 degrees C. | 2003-09-22 | 2003-12-15 | 2003-12-15 | 1437910 | 1553311 |  |  | 100 | 138 | na | 9.9 | 1233.6 kcmil ACSS/TW | Steel Towers | 75 | 9.9 | na | na | 25.101(c)(5)(B) | Final costs accumulating. | 1553311 | 0 | 1553311 |  |  | 24 | 1553311 | 0 | 1204724
03T65116 ALK | Cedar Hill-Sterrett 138 kV Loop into BEPC Sardis Switching Station | Ellis County | Construction will consist of removing one W-H-F, installing two guyed concrete poles and looping the conductor into the new BEPC Sardis Switching Station. | 2003-12-15 | 2003-12-23 | 2003-12-23 | 92432 | 53314 |  |  | 100 | 138 | na | 0.11 | 795 kcmil ACSR | Concrete Poles | 100 | 0.01 | 150 | 0.045 | 25.101(c)(5)(A) & 25.101(c)(5)(B) | Final costs accumulating. | 53314 | 0 | 53314 |  |  | 25 | 53314 | 0 | 1204724
03T65099 TW | E. Richardson-Rowlett 138kV Rebuild | Dallas County | Project in two phases. First phase of construction will consist of rebuilding the existing 138kV section from E. Richardson to Struct. 5/1. section, which includes 4 miles of single circuit and 1.2 miles of double circuit. The 2nd phase of construction consists of rebuilding the existing 138 kV section from Struct. 5/1 to Rowlett which includes 8.7 miles of single circuit and begins 12/01/03. | 2003-10-24 | 2004-12-15 |  | 16147581 | 15575553 |  |  | 20 | 138 | na | 13.9 | 1033.5 kcmil ACSR Bundled | Steel Poles | 80 | 12.7 | na | na | 25.101(c)(5)(B) | This project will be completed in 2 phases. | 15575553 | 0 | 15575553 |  |  | 26 | 15575553 | 0 | 1204724
03T61013 BW/BM | Norwood - Carrollton NW 138 kV: Relocation for the city of Farmers Branch | City of Dallas, Dallas County | The city of Farmers Branch has requested that a section of the Norwood - Carrollton NW 138 kV double circuit line be relocated for new city facility. This relocation will include the addition of 2 double dead end structures, 1 angle structure, and 1 double dead end angle structure and 7500 feet of new conductor. New easement to be provided by City. | 2003-12-20 | 2004-02-27 | 2004-02-27 | 750000 | 525000 |  |  | 100 | 138 | na | 0.56 | 1033.5 kcmil ACSR | Steel Poles | 75 | 0.16 | 45 | 0.28 | 25.101(c)(5)(F) | Existing ROW will deed back to city after completion of project. New ROW of 0.28 miles has been approved by Oncor and City of Farmers Branch. Final costs accumulating. | 525000 | 0 | 525000 |  |  | 27 | 525000 | 0 | 1204724
03T65117 MM | Parkdale-Sargent Rd. 138 kV: Reconductor | City of Dallas, Dallas County | Reconductor 138 kV circuit from Parkdale SES to the proposed Sargent Rd. Switching Station with 1233.6 kcmil ACSS/TW conductor. Modify and upgrade various existing steel towers to support the larger conductor. Also, modify the line to provide service to the proposed Sargent Road Switching Station. Line extension to switching station will be two spans or less. All line modifications will occur on property owned by Oncor. | 2003-10-08 | 2004-03-18 | 2004-03-18 | 1874200 | 1688989 |  |  | 100 | 138 | na | 4.94 | 1233.6 kcmil ACSS/TW | Steel Tower | 100 | 4.94 | na | na | 25.101(c)(5)(B) | Final costs accumulating. | 1688989 | 0 | 1688989 |  |  | 28 | 1688989 | 0 | 1204724
03T65098 RC | Payne-Sherman Line Material-Whitesboro Jordan 138 kV Transmission Line Rebuild/Reconductor Project | Grayson County | Sherman Line Material-Whitesboro Jordan: Rebuild existing single circuit wood pole line. Replace H-frame poles with single concrete poles to accomodate a larger conductor. Line to be rebuilt within the existing right-of-way. Payne-Sherman LIne Material: Reconductor existing line to a larger conductor. | 2003-10-01 | 2003-12-19 | 2003-12-19 | 4000000 | 3100000 |  |  | 100 | 138 | na | 15.8 | 1233.6 kcmil ACSS | Concrete Poles | 100 | 15.8 | na | na | 25.101(c)(5)(B) | Final costs accumulating. | 3100000 | 0 | 3100000 |  |  | 29 | 3100000 | 0 | 1204724
03T64045 EH/JB | Whitney - Walnut Springs 138kV | City of Whitney, Bosque County | Rebuild 17.5 miles of existing 336 kcmil ACSR conductor on wood H-frames with 795 kcmil ACSR on single concrete poles. | 2004-09-01 | 2004-12-31 |  | 4266000 |  |  |  | 0 | 138 | na | 17.5 | 795 kcmil ACSR | Concrete Poles | 100 | 17.5 | na | na | 25.101(c)(5)(B) |  | 4266000 | 0 | 4266000 |  |  | 30 | 4266000 | 0 | 1204724
02T61011 AK | Forest Grove-Canton Switch 138 kV: Connect Rayburn Country Explorer Pipeline Substation | Van Zandt County | Install concrete-H-frame switch structure with three switches and three concrete dead end poles for tap to Explorer Pipeline Substation. | 2003-12-15 | 2003-12-22 | 2003-12-22 | 189425 | 145993 |  |  | 100 | 138 | na | na | 1033.5 kcmil ACSR | Concrete Poles | 100 | na | na | na | 25.101(c)(5)(A) | Final costs accumulating. | 145993 | 0 | 145993 |  |  | 31 | 145993 | 0 | 1204724
03T65106 AK | Collin-Payne 138 kV: Connect GCEC Celina Substation | Collin County | Install concrete-H-frame switch structure with three switches and three concrete dead end poles for tap to GCEC Celina Substation. | 2004-04-26 | 2004-05-10 |  | 240431 |  |  |  | 0 | 138 | na | na | 795 kcmil ACSR | Concrete Poles | 100 | na | na | na | 25.101(c)(5)(A) |  | 240431 | 0 | 240431 |  |  | 32 | 240431 | 0 | 1204724
03T65142 AK | Payne-Bonham 69 kV: Replace switches and switch structure at the Ector Substation tap point. | Fannin County | Remove wood switch structure and switches and replace with one single concrete pole switch structure with three switches. | 2004-04-26 | 2004-05-10 |  | 114546 |  |  |  | 0 | 69 | na | na | 336.4 kcmil ACSR | Concrete Pole | 130 | na | na | na | 25.101(c)(5)(B) |  | 114546 | 0 | 114546 |  |  | 33 | 114546 | 0 | 1204724
02T64029 AK | East Waco - West Waco 138 kV: Construct tap to Baylor Substation | McLennan County | Install concrete switch structure with 3 switches, 3 concrete tap poles, 2 concrete-H-frames and 1 self supporting steel-H-frame dead end structure. | 2004-03-15 | 2004-04-30 |  | 307023 | 626000 |  |  | 80 | 138 | na | 0.29 | 795 kcmil ACSR | Steel Poles | 100 | 0.01 | 100 | 0.15 | 25.101(c)(5)(A) | .13 miles obtained by permit from the Corp of Engineers. Large estimate increase due to steel poles supported on anchor bolt foundations being used instead of concrete poles. Poor soil conditions resulting in large foundation and labor expenses. | 626000 | 0 | 626000 |  |  | 34 | 307023 | 318977 | 1523701
03T65026 SEI/BW | Denton Dr-Maple Ave 69kV: Replace Structure at Harry Hines Blvd and Lovers Lane | City of Dallas, Dallas County | Remove one wood pole and install new pole 50' south. | 2004-04-16 | 2004-04-30 |  | 17192 |  |  |  | 0 | 69 | na | 0.04072 | 636 kcmil ACSR | Wood Pole | City ROW | 0.04072 | na | na | 25.101(c)(5)(F) | Relocation at request of City of Dallas for widening of Lovers Lane. Project not reimbursible. | 17192 | 0 | 17192 |  |  | 35 | 17192 | 0 | 1523701
03T61018 SEI/BW | Collin-Renner 138kV: Relocate Structures at SH 121 and Lebanon Sub | City of Frisco, Collin County | Relocate and replace 2 wood H-Frames with new wood H-Frames | 2004-01-12 | 2004-01-23 | 2004-01-23 | 60739 | 47212 |  |  | 100 | 138 | na | 0.2911 | 795 kcmil ACSR | Wood H-Frame | 100 | 0.2911 | na | na | 25.101(c)(5)(F) | Relocation for TxDOT widening of SH 121. Project is 100% reimbursible. Final costs accumulating. | 47212 | 0 | 47212 |  |  | 36 | 47212 | 0 | 1523701
03T61014 SEI/BW | Liggett-Norwood 345kV: Relocate and Raise Structures at MacArthur Blvd | Dallas County | Relocate to new foundations and raise two 345kV steel towers. | 2003-12-15 | 2003-12-31 | 2003-12-31 | 145572 | 192934 |  |  | 100 | 345 North Circuit/138 South Circuit | na | 1.1837 | 1590 kcmil ACSR Bundled, 795 kcmil ACSR | Steel Towers | 230 | 0.59186 | na | na | 25.101(c)(5)(F) | Relocation for Dallas County widening and raising MacArthur Blvd at Bear Creek. Project is 100% reimbursible. Final costs accumulating. | 192934 | 0 | 192934 |  |  | 37 | 192934 | 0 | 1523701
03T65160 SEI/TW | Terrell - Willspoint 69 kV Line: Rebuild | City of Terrell, City of Wills Point and the City of Kaufman. Kaufman County and Van Zandt County | 69 kV Rebuild. Replace the static, remove cross arms and replace with stand-off insulators, replace and straighten select poles as needed | 2003-11-17 | 2004-04-26 |  | 866927 | 988000 |  |  | 80 | 69 | na | 15 | #1 HDCU 3 Strand | Wood Poles | na | 15 | na | na | 25.101(c)(5)(B) |  | 988000 | 0 | 988000 |  |  | 38 | 988000 | 0 | 1523701
03T63053 ALK | Sun - Cielo 138 kV: Construct tie to Cielo Wind Power transmission line. | Scurry County | Install one span of 1033.5 kcmil ACSR conductor to connect the Cielo Wind Power 138 kV Transmission Line to the Oncor system at the Sun Substation. | 2003-12-15 | 2003-12-22 | 2003-12-22 | 7773 | 7773 |  |  | 100 | na | 138 | 0.05 | 1033.5 kcmil ACSR | Wood Poles | 75 | 0.05 | na | na | 25.101(c)(5)(A) | This new span will utilize existing Oncor right of way. Final costs accumulating. | 7773 | 0 | 7773 |  |  | 39 | 7773 | 0 | 1523701
03T63037 DRC/JE | Rebuild Big Spring-Cosden-Falcon Seaboard COGEN 138 kV Transmission | City of Big Spring, Howard County | Replace existing structures, shield wire and conductors to provide a summer long term emergency rating of 1365 amperes per planning department requirements. |  |  |  | 1414596 |  |  |  | 0 | 138 | na | 1.29 | 1590 kcmil ACSR | Concrete Poles and Steel Poles | 50-60 | 1.29 | na | na | 25.101(c)(5)(B) | Deferred indefinitely due to ongoing negotiations with the customer concerning ownership of certain facilities. | 1414596 | 0 | 1414596 |  |  | 40 | 1414596 | 0 | 1523701
03T63039, 03T63040 DRC/JE | Rebuild Odessa EHV - Odessa Substation - Glenhaven Substation138 kV Transmission | City of Odessa, Ector County | Replace existing structures, shield wire and conductors to provide a summer long term emergency rating of 1365 amperes per planning department requirements. | 2004-01-24 | 2004-04-16 |  | 3843316.99 | 3843317 |  |  | 95 | 138 | na | 6.86 | 1590 kcmil ACSR | Concrete Poles, Concrete H-Frames and Steel Poles | 50-100 | 6.86 | na | na | 25.101(c)(5)(B) |  | 3843317 | 0 | 3843317 |  |  | 41 | 3843317 | 0 | 1523701
03T64050 VZ/BW | Temple - North Temple 138kV Line | City of Temple, Bell County | Reconductor approximately 4.6 miles of 138kV transmission line from existing Temple Substation to the existing North Temple Substation | 2004-03-23 | 2004-05-17 |  | 663544 | 663544 |  |  | 20 | 138 | na | 4.6 | 795 kcmil ACSS/TW | Steel Poles and Steel Towers | 100 | 4.6 | na | na | 25.101(c)(5)(B) |  | 663544 | 0 | 663544 |  |  | 42 | 663544 | 0 | 1523701
03T64049 RC/BW | Minerva-Robertson 138kV Transmission Line Rebuild Project | Robertson County, Milam County | Project in two phases. First phase of construction will consist of rebulding the existing 138kV section from Minerva Substation to Milano Substation, which is 6.7 miles of single circuit. The second phase of construction consists of rebuilding the existing 138kV section from Milano Substation to Robertson Substation, which is 20.9 miles of single circuit. | 2004-01-19 | 2004-05-15 |  | 4445000 | 4445000 |  |  | 25 | 138 | na | 27.6 | 795 kcmil ACSR | Steel Poles or Concrete Poles | 100 | 27.6 | na | na | 25.101(c)(5)(B) |  | 4445000 | 0 | 4445000 |  |  | 43 | 4445000 | 0 | 1523701
03T65129 TW/RC | Kirkland Park - TI 138 kV Rebuild | Dallas County | Double circuit, single steel pole,1033 kcmil ACSR conductor, rebuild | 2004-01-19 | 2004-06-15 |  | 4300000 | 3300000 |  |  | 50 | 138 | na | 2.3 mi | 1033.5 kcmil ACSR | Steel Poles | 100 | 2.3 | na | na | 25.101(c)(5)(B) |  | 3300000 | 0 | 3300000 |  |  | 44 | 3300000 | 0 | 1523701
03T64051 BW/BP | Copperas Cove - Copperas Cove (LCRA) 138 kV | City of Copperas Cove, Coryell County | Rebuild 1.90 miles of the Copperas Cove - Copperas Cove (LCRA) section of the Temple Switching Station - Lampasas County 138kV line using concrete h-frame structures, and 959.6 kcmil ACSS/TW conductor. | 2004-02-16 | 2004-03-08 | 2004-03-08 | 375735 | 524437 |  |  | 100 | 138 | na | 1.9 | 959.6 kcmil ACSS/TW | Concrete H-Frames | 100 | 1.9 | na | na | 25.101(c)(5)(B) | Final costs accumulating. | 524437 | 0 | 524437 |  |  | 45 | 524437 | 0 | 1523701
03T64052 SEI/BW | Ft. Hood Tap- Killeen Clear Creek - W. Ft. Hood 138 kV | Bell County | Rebuild the 1.90 mile Ft. Hood Tap- Killeen Clear Creek - W. Ft. Hood section of the Temple Switching Station - Lampasas County 138kV line using concrete h-frame structures, and 959.6 kcmilACSS/TW conductor. | 2003-03-08 | 2004-03-27 | 2004-03-27 | 375735 | 504417 |  |  | 100 | 138 | na | 1.9 | 959.6 kcmil ACSS/TW | Concrete H-Frames | 100 | 1.9 | na | na | 25.101(c)(5)(B) | Final costs accumulating. | 504417 | 0 | 504417 |  |  | 46 | 504417 | 0 | 1523701
03T64053 WB | Shamburger - Tyler N.E. 138 kV Reconductor | Smith County | Reconductor the 2.01 mile Shamburger - Tyler N.E. section of the Tyler N.W. - Tyler N.E 138 kV line with 1233.6 kcmil ACSS/TW conductor. Replace five wood h-frames with concrete h-frames. | 2004-04-19 | 2004-05-15 |  | 757543 |  |  |  | 0 | 138 | na | 2.01 | 1233.6 kcmil ACSS/TW | Steel Poles and Concrete-H-Frames | 100 | 2.01 | na | na | 25.101(c)(5)(B) |  | 757543 | 0 | 757543 |  |  | 47 | 757543 | 0 | 1523701
03T65175 WB/MH | Hackberry - Northlake 138kv Reconductor Project | City of Irving, Dallas County | Reconductor 2.2 mile Hackberry - Valley Ranch 138kV line section and the 2.0 mile Valley Ranch - Northlake 138kV line section using single conductor 1233.6 kcmil ACSS/TW. | 2004-03-01 | 2004-05-15 |  | 763000 | 763000 |  |  | 50 | 138 | na | 4.2 | 1233.6 kcmil ACSS/TW | Steel H-Frames, Steel Poles, Steel Towers. | 100 | 4.2 | na | na | 25.101(c)(5)(B) |  | 763000 | 0 | 763000 |  |  | 48 | 763000 | 0 | 1523701
03T65124 EH/AJ | Convert Paris-Commerce 69kV to 138-kV Operation | City of Commerce, City of Cooper, and the City of Paris, Hunt County, Delta County, Lamar County | Convert the existing 34.1 mile Paris Switch to Commerce Sub 69kV 1033 kcmil ACSR on concrete single poles or H-frame structures to a double circuit 138/69kV with 1033 kcmil ACSR on single concrete poles. Rebuild the existing 2.5 mile Commerce Sub to Commerce Switch 138kV 336 kcmil ACSR on steel towers and wood H-frame structures with 1033 kcmil ACSR on existing steel towers and single concrete poles. | 2004-01-12 | 2004-09-14 |  | 9400000 | 9400000 |  |  | 20 | 69 | 69,138 | 70.7 | 1033.5 kcmil ACSR | Concrete Poles, Steel Towers, Wood H-Frames | 100 | 36.6 | na | na | 25.101(c)(5)(B), 25.101(c)(5)(C) |  | 9400000 | 0 | 9400000 |  |  | 49 | 9400000 | 0 | 1523701
04T62034 WB/BM | Bryan Avenue - Forest Hill 69 kV Line: Rebuild 3.75 miles | City of Fort Worth, Tarrant County | Construction will consist of rebuilding approximately 3.75 miles of an existing 69 kV single circuit lattice steel transmission line between Forest Hill substation and the Bryan Avenue Tap. Project will include removing one cirucit of 336 kcmil ACSR and removing "City" type lattice towers. New line to be constructed 138 kV using 795 kcmil ACSR on concrete poles although line will be re-energized 69 kV. This project will be rebuilt within existing ROW. | 2004-03-08 | 2004-04-30 |  | 1267261 | 1267261 |  |  | 20 | 69 | na | 3.75 | 795 kcmil ACSR | Concrete Poles and Steel Poles | 50 | 3.75 | na | na | 25.101(c)(5)(B) |  | 1267261 | 0 | 1267261 |  |  | 50 |  |  |  | 0
03T65178 MM | Anna Sw Sta - McKinney Sub 138kV | City of McKinney, Collin County | Rebuild 7.50 miles of existing double circuit single 795 kcmil ACSR & single 1033 kcmil ACSS conductor on steel poles & lattice towers with bundled 1233.6 kcmil ACSS/TW on steel poles. | 2004-03-15 | 2004-10-15 |  | 7390000 | 7380323 |  |  | 20 | 138 | na | 15 | 1233.6 kcmil ACSS/TW Bundled | Steel Poles | 100 | 7.5 | na | na | 25.101(c)(5)(B) |  | 7380323 | 0 | 7380323 |  |  | 51 | 7390000 | -9677 | 1514024
03T65177 MM/JB | Allen Sw Sta - McKinney Sub 138kV | City of McKinney, Collin County | Rebuild 13.50 miles of existing double circuit single 795 kcmil ACSR & single 1033 kcmil ACSS conductor on steel poles & lattice towers with bundled 1233.6 kcmil ACSS/TW on steel poles. | 2004-10-15 | 2005-03-15 |  | 13400000 | 13400000 |  |  | 0 | 138 | na | 27 | 1233.6 kcmil ACSS/TW Bundled | Steel Poles | 100 | 13.5 | na | na | 25.101(c)(5)(B) |  | 13400000 | 0 | 13400000 |  |  | 52 | 13400000 | 0 | 1514024
JDM04020 BW/BM | Salado-Roundrock 138 kV lline:Wood-H-Frame Relocation for new West Taylor Substation | Bell County and Williamson County | A new Oncor substation (West Taylor) will be placed in the Salado-Roundrock 138 kV line. The Salado-Roundrock 138 kV line must have two wood-H-frame structures removed and two wood-H-frame structures raised and relocated in order to provide adequate clearances once the new station dead end is installed and distribution feeders constructed. The new structures will be placed within the existing centerline of the existing 138 kV line. No new ROW will be required for relocation of either of the wood-H-frames structures. | 2004-04-22 | 2004-05-10 |  | 75000 |  |  |  | 0 | 138 | na | 0.2 | 795 kcmil ACSR | Wood H-Frames | 100 | 0.2 | na | na | 25.101(c)(5)(A) & 25.101(c)(5)(B) |  | 75000 | 0 | 75000 |  |  | 53 | 75000 | 0 | 1514024
03T61005 BW | Renner - W. Plano 138 kV Line Relocation for Billingsley | City of Plano, Collin County | Relocate a portion (4200 ft.) of the Renner-W. Plano 138 kv Line to accommodate land development by the Crow-Billingsley Investment Company. This relocation consists of removing 8 double circuit steel lattice towers and installing 8 double circuit single steel poles (3400 ft.). This relocation is at the request of Crow-Billingsley Investment Company and is 100% reimburseable. | 2004-02-15 | 2004-05-15 |  | 637148.36 | 637148.36 |  |  | 10 | 138 | na | 1.28 | 1033.5 kcmil ACSR | Steel Poles | 100 | 0.79545 | 70 | 0.64394 | 25.101(c)(5)(D) |  | 637148.36 | 0 | 637148.36 |  |  | 54 | 637148.36 | 0 | 1514024
03T63036 JS/DC | Rebuild Midessa to Midland West 138 kV Transmission Line | City of Midland, Midland County | Replace existing structures, shield wire and conductors to provide a summer long term emergency rating of 1365 amperes per planning department requirements. | 2004-10-25 | 2004-12-14 |  | 1675946 |  |  |  | 0 | 138 | na | 3.81 | 1590 kcmil ACSR | Steel Poles or Concrete Poles | 50-75 | 3.81 | na | na | 25.101(c)(5)(B) |  | 1675946 | 0 | 1675946 |  |  | 55 | 1675946 | 0 | 1514024
04T62024 SEI/WB | Cedar Hill-Venus 345kV, Webb Substation | City of Arlington, Tarrant County | Dead end one circuit of bundled 795 MCM ACSR conductor on new dead end structure and remove 115' steel pole. | 2004-03-06 | 2004-03-18 | 2004-03-18 | 56496 | 56496 |  |  | 100 | 345 | na | 0.0079545 | 795 kcmil ACSR bundled | Steel Tower | na | na | na | na | 25.101(c)(5)(A) | Final costs accumulating. | 56496 | 0 | 56496 |  |  | 56 | 56496 | 0 | 1514024
04T62072 04T62071 BM/BW | Benbrook-Wedgewood 138 kV No. 1 (South): Reconductor with 1233.6 ACSS/TW (04T62072) / Benbrook-Wedgewood 138 kV No.2 (North): Reconductor with 1233.6 ACSS/TW (04T62071) | Tarrant County | The project will consist of reconductoring the South (No.1) & North (No. 2) Circuit of the Benbrook-Forest Hill 138 kV DC line. The existing 795 kcmil ACSR conductor will be removed and new 1233.6 ACSS/TW will be installed. Other work to include the addition of one switch structure and a set of LDS line switches under each circuit. All work to be done within the existing Oncor ROW. No additional ROW will be required for this project. | 2004-03-18 | 2004-05-15 |  | 2149670 | 2149670 |  |  | 15 | 138 | na | 5.65 | 1233.6 kcmil ACSS/TW | Steel Towers | 75 | 5.65 | na | na | 25.101(c)(5)(B) |  | 2149670 | 0 | 2149670 |  |  | 57 | 2149670 | 0 | 1514024
03T42014 BM/BW | Hillsboro - Waco Tap Line to Waco General Tire Substaion 69kV Double Ckt. Line: Relocate Sectionalizing from Waco-General Tire | City of Waco, McLennan County | This project is being constructed to establish a loop point at the Waco Katy Substation Tap. This project will consist of adding 3 switches on 2 Steel Mono-Poles. The new steel mono poles will be installed on the existing 69 kV centerline. No new ROW will be required. | 2004-04-20 | 2004-05-01 |  | 129621 |  |  |  | 0 | 69 | na | 0.0125 | 336.4 kcmil ACSR | Wood Poles and Steel Switch Poles | 70 | 0.01 | na | na | 25.101(c)(5)(B) |  | 129621 | 0 | 129621 |  |  | 58 | 129621 | 0 | 1514024
04T62029 MM | Bowen East 138 kV Tap Line: Replace Structure 2/13 | City of Arlington, Tarrant County | Existing Structure 2/13 in the Bowen East 138 kV Tap Line is a single wood pole supporting one circuit of 336.4 kcmil ACSR conductor and one 3/8'' EHS shield wire located next to a creek/drainage ditch. The creek bank is washing and is placing this structure in jeapordy of falling. The pole will be replaced with a steel pole installed on an anchor bolted foundation capable of enduring encroachment of the creek. | 2004-04-19 | 2004-05-15 |  | 51989 |  |  |  | 0 | 138 | na | 0.12 | 336.4 kcmil ACSR | Steel Pole | 70 | 0.12 | na | na | 25.101(c)(3) |  | 51989 | 0 | 51989 |  |  | 59 | 51989 | 0 | 1514024
04T62028 MM | Bowen West 138 kV Tap Line: Replace Structures 4/2 and 4/3 | City of Arlington, Tarrant County | Existing Structures 4/2 and 4/3 in the Bowen West 138 kV Tap Line are wooden structures. Structure 4/2 is an H-frame and Structure 4/3 is a guyed angle structure. The structures support one circuit of 336.4 kcmil ACSR conductor and two 3/8'' EHS shield wires. These structures are located next to a creek/drainage ditch. The creek bank is washing into the structures and anchors and placing them in jeapordy of failing. The wooden structures will be replaced with single steel poles capable of enduring encroachment of the creek. | 2004-04-19 | 2004-05-15 |  | 248754 |  |  |  | 0 | 138 | na | 0.22 | 336.4 kcmil ACSR | Steel Pole | 70 | 0.22 | na | na | 25.101(c)(3) |  | 248754 | 0 | 248754 |  |  | 60 | 248754 | 0 | 1514024
02T61013 BW/BM | Pflugerville South 138 kV: Reroute for Raw Water Storage | City of Pflugerville, Travis County | The City of Pflugerville has requested that a section of the Pflugerville South 138 kV line be relocated to accommodate their new Raw Water Storage facility. This relocation will involve removing 6 structures and the addition of 8 structures. The City of Pflugerville has granted Oncor an easment for the relocated Transmission line. | 2004-04-19 | 2004-05-14 |  | 840000 |  |  |  | 0 | 138 | na | 0.54 | 1590 kcmil ACSR | Steel Poles | 50 | 0.54 | 50 | 0.54 | 25.101(c)(5)(F) |  | 840000 | 0 | 840000 |  |  | 61 | 840000 | 0 | 1514024
02T61033 SEI/BW | E. Levee-Hwy 356 Jct 138kV, Hampton Viaduct | City of Dallas, Dallas County | Relocate existing towers T-129 and T-130 to new bottom sections and foundations. | 2004-05-03 | 2004-05-28 |  | 111472 |  |  |  | 0 | 138 | na | 0.58 | 927.2 kcmil ACAR | Steel Towers | 100 | 0.29451 | na | na | 25.101(c)(5)(F) | Relocation for TxDOT construction of new higher, wider Hampton Bridge over the Trinity River. | 111472 | 0 | 111472 |  |  | 62 | 111472 | 0 | 1514024
03T61019 SEI/BW | Simsboro Magnolia-Jewett 69kV, Northwestern Resources Co Mine | City of Jewett, Leon County | Reroute line with 16 new concrete poles and remove 14 wood H-Frames for mining activities. | 2004-05-03 | 2004-06-15 |  | 490188 |  |  |  | 0 | 69 | na | 1.2553 | 4/0 ACSR | Wood H-Frames | 100 | 1.2553 | 100 | 1.6392 | 25.101(c)(5)(D) | Relocation at request of Northwestern Resources Co to remove line from area to be strip mined for lignite. | 490188 | 0 | 490188 |  |  | 63 | 490188 | 0 | 1514024
03T61019 SEI/BW | Simsboro Magnolia-Jewett 69kV, Northwestern Resources Co Mine | City of Jewett, Leon County | Emergency reroute of existing line with 5 new wood poles and remove 5 wood H-Frames prior to completion of total reroute | 2004-03-04 | 2004-03-15 | 2004-03-15 | 7500 | 7500 |  |  | 100 | 69 | na | 0.48352 | 4/0 ACSR | Wood H-Frames | 100 | 0.48352 | 100 | 0.51553 | 25.101(c)(D) | Relocation at request of Northwestern Resources Co to remove line from area to be immediately strip mined for lignite. Final costs accumulating. | 7500 | 0 | 7500 |  |  | 64
03T64046 EH/JB | Hillsboro - Whitney 138kV | City of Hillsboro, Hill County | Rebuild 17.5 miles of existing 636 kcmil ACSR conductor on wood H-frames with 1590 kcmil ACSR on single concrete poles. | 2004-01-01 | 2004-05-15 |  | 4660000 | 4660000 |  |  | 60 | 138 | na | 17.5 | 1590 kcmil ACSR | Concrete Poles | 100 | 17.5 | na | na | 25.101(c)(5)(B) |  | 4660000 | 0 | 4660000 |  |  | 65 | 4660000 | 0 | 1514024
03T61015 BW/BM | Brownwood - Goldthwaite 138 kV Line: Relocate Along FM 3064 for TxDOT | Brown County | TxDOT has requested that a section of the Brownwood 138 kV Line be relocated for the widening of FM 3064 (Morris Shepard Drive). This Relocation will consist of relocating the existing 138 kV line approximatley 18' to the south. Five (5) existing wood structures and two (2) guyed steel poles will be removed and Four (4) new tangent concrete and Two (2) self supporting steel poles will be installed. The relocated transmission line will be relocated within Texas Department of Transportation ROW. | 2004-05-01 | 2004-05-22 |  | 375000 |  |  |  | 0 | 138 | na | 0.42 | 636. kcmil ACSR | Concrete Poles and Steel Poles | 50 | 0.42 | 50 | 0.42 | 25.101(c)(5)(F) | TxDOT has given Oncor consent to relocate the transmission line within TxDot ROW. All new ROW obtained is TxDOT ROW. | 375000 | 0 | 375000 |  |  | 66 |  |  |  | 0
03T61010 BW/BM | Temple Switch-Lampasas 138 kV: Relocate for Fort Hood | Bell County | The project will consist of relocating approximately 1500' of the Temple Switch-Lampasas 138 kV single circuit line for Fort Hood. | 2004-04-29 | 2004-05-22 |  | 428450 |  |  |  | 0 | 138 | na | 0.24 | 795 kcmil ACSR | Wood H-Frames and Steel H-Frames | 100 | 0.24 | 100 | 0.26 | 25.101(c)(5)(F) |  | 428450 | 0 | 428450 |  |  | 67 |  |  |  | 0
03T65128 TW/RC | Mountain Creek-Westmoreland 138kV Tap | City of Dallas, Dallas County | Convert the Mountain Creek-Westmoreland 69kV line to 138kV operation using 795 kcmil ACSR conductor and install two switches at the new tap point outside the Mountain Creek SES. | 2004-04-30 | 2004-07-15 |  | 3518260 |  |  |  | 0 | 69 | 138 | 3.65 | 795 kcmil ACSR | Steel Poles | 50 | 3.65 | na | na | 25.101(c)(5)(B) |  | 3518260 | 0 | 3518260 |  |  | 68 |  |  |  | 0
03T65115 TW/JF | Northaven - Alpha Rd. 138kV Reconductor | City of Dallas, Dallas County | This project includes the re-conductor of the existing 138kV section from Northaven substation to Alpha Rd. substation, which includes 2.29 miles of double circuit. | 2004-05-01 | 2004-05-15 |  | 750000 |  |  |  | 0 | 138 | na | 4.58 | 959.6 kcmil ACSS/TW Bundled | Steel Towers and Steel Poles | 80 | 2.29 | na | na | 25.101(c)(5)(B) | Interim Report filed 02/27/2004. | 750000 | 0 | 750000 |  |  | 69 | 750000 | 0 | 1514024
04T61006 BW | W. Waco-Temple 138 kV Line Relocation for Brindley Sub-division | City of Temple, Bell County | Relocate existing single wood pole structure 32/14. | 2004-04-16 | 2004-05-10 |  | 9793 |  |  |  | 0 | 138 | na | 0.0079545 | 795 kcmil ACSR | Wood Pole | 40 | 0.01 | na | na | 25.101(c)(5)(D) | Relocation for developer to accommodate new road being built in a sub-division. This project is reimburseable. Interim Report filed 02/27/2004. | 9793 | 0 | 9793 |  |  | 70 | 9793 | 0 | 1514024
03T62061A JB/EH | Seldon - Walnut Springs 138kV | City of Walnut Springs, Bosque County | This project consists of rebuilding two separate line sections. First, rebuild Johnsville-Walnut Springs section, 12.20 miles of existing 4/0 ACSR conductor on wood H-frames with 795 kcmil ACSR on single concrete poles and concrete H-frames. Second, rebuild Seldon-Johnsville section, 13.2 miles of existing 4/0 ACSR conductor on wood H-frames with 795 kcmil ACSR on single concrete poles & concrete H-frames. | 2004-04-18 | 2004-12-15 |  | 6456872 |  |  |  | 0 | 138 | na | 25.4 | 795 kcmil ACSR | Concrete Poles and Concrete H-Frames | 100 | 25.4 | na | na | 25.101(c)(5)(B) | This project was initially planned to be reported on 2 separate rows on this report, each row representing one rebuilt line section. To appropriately track project costs, it will be reported on one row. Data columns have been updated as necessary. | 6456872 | 0 | 6456872 |  |  | 71 | 3228450 | 3228422 | 4742446
04T65073 MM | Liggett-Norwood 345 kV: Relocate Structure 3/1 | City of Grand Prairie, Dallas County | Existing Structure 3/1 in the Liggett-Norwood 345 kV Line is a double circuit lattice tower supporting one circuit of horizontally bundled 1590 kcmil ACSR conductor operating at 345 kV, one circuit of single conductor 795 kcmil ACSR conductor operating at 138 kV, and two 7/16'' EHS shield wires. A large portion of two of the tower foundations have been exposed by the soil failure, placing this structure in jeapordy of failing. It is proposed to relocate this tower approximately 250 feet west of its existing location and to install an additional 130' tall tower in the line. Structure 3/1 will also be impacted by a proposed TXDOT highway project. All work will be done in a manner to accommodate the proposed highway and will be reimbursible by TXDOT. However, the tower is in need of immediate attention due to the soil failure so the work will be completed as soon as possible. | 2004-04-16 | 2004-05-07 |  | 317186 |  |  |  | 0 | 345 and 138 | na | na | 1590 kcmil ACSR and 795 kcmil ACSR | Steel Towers | 230 | na | na | na | 25.101(c)(5)(E) and 25.101(c)(5)(F) | Interim Report filed 03/04/2004. | 317186 | 0 | 317186 |  |  | 72 | 317186 | 0 | 4742446
03T65159 AK | Kaufman Sw. - Seagoville Sw. !38 kV: Connect Trinity Valley Cooperative's Crandall Substation | Kaufman County | Install concrete-H-frame switch structure with three switches and three concrete dead end poles and one concrete-H-frame for tap to Trinity Valley Electric Cooperative's Crandall Substation. | 2004-04-19 | 2004-04-30 |  | 188892 |  |  |  | 0 | 138 | na | na | 795 kcmil ACSR | Concrete Poles and Concrete H-Frames | 100 | na | na | na | 25.101(c)(5)(A) |  | 188892 | 0 | 188892 |  |  | 73 | 188892 | 0 | 4742446
SEI/BW | Forest Hill-Cresson 69 kV: Pershon Rd. | City of Crowley, Tarrant County | Relocate and replace single wood pole 6/6 for widening of Pershon Rd. | 2004-05-21 | 2004-04-30 |  | 10000 |  |  |  | 0 | 69 | na | 0.10549 | 1/0 ACSR | Single Wood Pole | 50 | 0.10549 | na | na | 25.101(c)(5)(D) | Relocation requested by property developer for new homes. This project is reimbursable by the developer. | 10000 | 0 | 10000 |  |  | 74
04T61004 SEI/BW | Liggett-Collin 138 kV: SH 121 at FM 423 | City of The Colony, Denton County | Relocate and replace 5 wood H-Frames with 4 new concrete H-Frames. | 2004-06-01 | 2004-06-30 |  | 141260 |  |  |  | 0 | 138 | na | 0.48977 | 795 kcmil ACSR | Wood H-Frames and Concrete H-Frames | 100 | 0.48977 | na | na | 25.101(c)(F) | Relocation at request of TxDOT to accommodate widening and reconstruction of SH 121. This project is 100% reimbursable. | 141260 | 0 | 141260 |  |  | 75
SEI/BW | Coppell-Apollo Rd 69 kV: Midway Rd and Keller Springs | City of Addison, Dallas County | Relocate and replace single wood angle pole for intersection improvements. | 2004-05-24 | 2004-05-28 |  | 15000 |  |  |  | 0 | 69 | na | 0.13826 | 336.4 kcmil ACSR | Wood Pole | 0 | 0.13826 | na | na | 25.101(c)(F) | This is a Dallas County CMAQ project. The project is not reimbursable. | 15000 | 0 | 15000 |  |  | 76
04T61003 SEI/BW | Trinidad-Jewett 138 kV: Northwestern Resouces Retention Pond and Haul Road. | City of Jewett, Freestone County | Relocate and replace 10 wood H-Frames with 8 new concrete H-Frames. | 2004-05-21 | 2004-06-04 |  | 224930 |  |  |  | 0 | 138 | na | 1.167 | 795 kcmil ACSR | Wood H-Frames and Concrete H-Frames | 100 | 1.167 | na | na | 25.101(c)(D) | Relocation at request of Northwestern Resources for construction of a sedimentation retention pond and lignite haul road for mine activities. All work to be done on mine property This project is 100% reimbursable. | 224930 | 0 | 224930 |  |  | 77
04T61001 SEI/BW | Hillsboro-Leon 138kV, FM 2214 | City of Eastland, Eastland County | Relocate and replace 5 wood H-Frames with 5 new concrete H-Frames. | 2004-05-21 | 2004-06-04 |  | 139159 |  |  |  | 0 | 138 | na | 0.53674 | 336.4 kcmil ACSR | Wood H-Frames and Concrete H-Frames | 100 | 0.53674 | na | na | 25.101(c)(F) | Relocation at request of TxDOT to accommodate widening and reconstruction of FM 2214. This project is 100% reimbursable. | 139159 | 0 | 139159 |  |  | 78
04T62030 MM | Ft. Worth-Cleburne 69 kV, Forest Hill-Burleson Section: Replace Structure 501 | City of Ft. Worth, Tarrant County | Existing Structure 501 in the Ft. Worth-Cleburne 69 kV Line is a double circuit lattice tower supporting one circuit of 336.4 ACSR conductor and one 3/8'' shield wire. During a recent inspection, it was discovered that one leg of the tower had been broken off by a tractor or some other piece of equipment. This structure will be replaced with a concrete pole. | 2004-04-05 | 2004-04-12 |  | 44680 |  |  |  | 0 | 69 | na | na | 336.4 kcmil ACSR | Concrete Pole | 50 | na | na | na | 25.101(c)(5)(E) | MARCH 4 INTERIM REPORT (ONE OF 6 PROJECTS) NOTE: STAFF ADDED THIS PROJECT TO THE APRIL, MAY AND JUNE REPORTS. | 44680 | 0 | 44680
CCN APPLICATIONS - APPROVED |  | NEW: | 530349 | [19 empty] | 0 | 0 | 0 |  |  | 80
ABCD5 | Cedar Hill-DeSoto 138 kV 2nd Circuit | City of DeSoto, City of Glenn Heights, and the City of Cedar Hill, Dallas County | Remove existing single-circuit 138 kV line on wood H-frames and replace with new double circuit 138 kV line on steel or concrete poles |  | 2005-05-15 |  | 4532000 |  |  |  | 0 | 138 | na | 6.2 | 1590 kcmil ACSR | Steel Poles and Concrete Poles | 75 | 6.2 | na | na | 23604 | Notice of Approval 04/11/01. | 4532000 | 0 | 4532000 |  |  | 81 | 4532000 | 0 | 4742446
03T65096 03T65097 TW | Plano Tennyson 138 kV Loop Line | City of Plano, City of The Colony,and the City of Carrollton, Collin County and Denton County | Construct approx. 5.70 miles of 138 kV transmission line from existing NW Carrollton-Collin SES 138 kV Transmission Line to the existing Plano Tennyson Switching Station | 2003-08-18 | 2003-12-30 | 2003-12-30 | 8967000 | 7204966 |  |  | 100 | na | 138 | 11.4 | 1590 kcmil ACSR | Steel Poles | 170 | 5.7 | 70 | 5.7 | 21664 | Final Order 08/06/01. Final costs accumulating. | 7204966 | 0 | 7204966 |  |  | 82 | 7204966 | 0 | 4742446
02T64034 MM | Ennis - Ennis West 138 kV Transmission Line Project | City of Ennis, Ellis County | Construct approximately 10.7 miles of 138 kV line to the new Ennis West Switching Station. | 2003-01-15 | 2003-07-05 | 2003-07-05 | 7321700 | 7321700 |  |  | 100 | na | 138 | 10.7 | 795 kcmil ACSR | Steel Poles | na | na | 70 | 10.7 | 24798 | Final Order issued 09/17/02. Final costs accumulating. Property owner lawsuits are on going. All legal fees and awards to the property owners will be charged to the project. Final costs will not be available until all lawsuits are settled. | 7321700 | 0 | 7321700 |  |  | 83 | 7321700 | 0 | 4742446
DRC2 | Watermill - Lancaster 138 kV Transmission Line Project | Dallas County | Construct approximately 3.00 miles of 138 kV transmission line from Watermill Switching Station to line section that travels north to Lancaster Substation to vacate 2nd position on 345 kV towers | 2004-10-15 | 2005-05-15 |  | 836190 |  |  |  | 0 | na | 138 | 3 | 1590 kcmil ACSR | Concrete Poles | 100 | 3 | na | na | 25321 | Final Order issued 12/09/02. | 836190 | 0 | 836190 |  |  | 84 | 836190 | 0 | 4742446
03T65046 TW/RC | Collin - Renner 138 kV Transmission Line Project | City of Plano and the City of Frisco, Collin County | Replace single circuit wood H-frame 138 kV line with single steel pole double circuit 138 kV line from Collin plant to Allen Junction to Renner Sw. Station | 2003-02-10 | 2004-12-15 |  | 12414319 | 12414319 |  |  | 25 | 138 | na | 27.8 | 1590 kcmil ACSR | Steel Poles | 100 | 13.9 | na | na | 25179, 25.101(c)(5)(B) | Final Order issued 11/25/02. Will be completed in sections. | 12414319 | 0 | 12414319 |  |  | 85 | 12414319 | 0 | 4742446
ABCD4 | Ennis - Mustang Creek 345 kV Transmission Line Project | City of Ennis, Ellis County | Construct 3.70 miles 345 kV double circuit on single pole from new Ennis-Tractabel Unit II to the proposed Mustang Creek Switching Station | 2004-10-15 | 2004-12-01 |  | 19271683 |  |  |  | 0 | na | 345 | 7.4 | 1590 kcmil ACSR Bundled | Steel Poles | na | na | 100 | 3.7 | 26608 | Final Order issued 12/17/02. Project delayed at the request of the customer. | 19271683 | 0 | 19271683 |  |  | 86 | 19271683 | 0 | 4742446
03T65131 DRC | Watermill - W. Levee 345 kV: Add Second 345 kV Circuit | City of Dallas,Dallas County | Add the second 345 kV circuit to existing structures from Watermill Switching Station to W. Levee Switching Substation. In addition, make the necessary line changes to connect the new Sargent Road Substation to the transmission line. | 2003-10-01 | 2004-05-01 |  | 3975000 | 3975000 |  |  | 86 | 345 | na | 9 | 1590 kcmil ACSR Bundled | Steel Poles | 100 | 9 | na | na | 25.101(b)(3) | CCN previously approved and one circuit already constructed. Interim Report filed 6/27/2003. | 3975000 | 0 | 3975000 |  |  | 87 | 3975000 | 0 | 4742446
03T64043 BW | Round Rock - Round Rock South 138kV | City of Round Rock, Williamson County | Add a second circuit of 795 kcmil ACSR to the existing line (it is currently a double circuit line with only one circuit installed). This work will relieve overloads for contingency conditions in the Round Rock area. | 2003-10-06 | 2003-10-20 | 2003-10-20 | 649000 | 512620 |  |  | 100 | 138 | na | 3 | 795 kcmil ACSR | Steel Poles | 100 | 3 | na | na | 25.101(b)(3) | CCN previously approved and one circuit already constructed. Final costs accumulating. | 512620 | 0 | 512620 |  |  | 88 | 512620 | 0 | 4742446
ABCD1 | Carrollton Country Club 138 kV Transmission Line Project | City of Addison and the City of Carrollton, Dallas County | Construct 1.32 miles 138 kV double circuit on single poles to Carrollton Countly Club Substation | 2005-09-30 | 2006-05-15 |  | 3653273 |  |  |  | 0 | na | 138 | 2.64 | 1590 kcmil ACSR | Steel and/or Concrete Poles | 100 | 1.32 | na | na | 27030 | Application filed 11/27/02. Final Order issued 08/07/03. | 3653273 | 0 | 3653273 |  |  | 89 | 3653273 | 0 | 4742446
ABCD2 | Copperas Cove - Ding Dong 138 kV Transmission Line Project | Bell County, Coryell County | Construct 15.7 miles 138 kV single circuit single pole from Oncor Copperas Cove Substation to BEPC's Ding Dong Substation | 2004-07-01 | 2005-05-13 |  | 7145776 |  |  |  | 0 | na | 138 | 15.7 | 795 kcmil ACSS | Steel and/or Concrete Poles | na | na | 70/100 | 15.7 | 27179 | Application filed 12/31/02. Application approved 01/29/2004. | 7145776 | 0 | 7145776 |  |  | 90 | 7145776 | 0 | 4742446
ABCD3 | Temple Pecan Creek Switch - Temple North Switch 138 kv Transmission Line Project | Bell County | Construct 4.7 miles 138 kV double circuit single pole from new Temple Pecan Switching Station to the new Temple North Switching Station | 2005-01-03 | 2006-05-15 |  | 4788194 |  |  |  | 0 | na | 138 | 9.4 | 1590 kcmil ACSR | Steel and/or Concrete Poles | na | na | 70 | 4.7 | 27173 | Application filed 12/27/02. Application approved 01/15/2004. | 4788194 | 0 | 4788194 |  |  | 91 | 4788194 | 0 | 4742446
| CCN APPLICATIONS - PENDING | [21 empty] | 0 | 0 | 0 |  |  | 92
[23 empty] | 0 | 0 | 0 |  |  | 93
| COMPLETED PROJECTS REMOVED FROM 03/15/2004 REPORT. | [21 empty] | 0 | 0 | 0 |  |  | 94
03T65053 TP | Payne-Royse City 138 kV: White Mound P.O.I. | Grayson County | Replace three concrete H-frame structures and install three 1200 A line sectionalizing switches in the Payne-Royse City 138 kV transmission line. Install three concrete guyed slack span poles to connect the new GCEC White Mound Substation. | 2003-08-01 | 2003-08-05 | 2003-08-05 | 209436 | 209436 | 205936 | -1.671% | 100 | 138 | na | 0.5 | 795 kcmil ACSR | Concrete-H-Frames | 100 | 0.5 | 50 | 0.032 | 25.101(c)(5)(B), 25.101(c)(5)(A)
DRC1 | Preston North-Knoll Trail 138 kV Tap Line to ARCHON Genesis. | City of Dallas, Dallas County | Construct approximately 0.25 Miles of new 138 kV line to serve ARCHON Genesis project. The project consists of constructing new 138 kV Line and to reterminate the existing transmission structure with one circuit 336.4 kcmil ACSR in public ROW and the remaining 150 ft. will be constructed on new ROW easements provided by customer. |  |  |  | 525000 | 525000 | 525000 | 0% | 100 | na | 138 | 0.25 | 336.4 kcmil ACSR | Concrete Pole and Steel Pole | na | na | 70 | 0.03 | 25.101(c)(2)(C)(i) | This project is being removed from report because scope of customer's project has changed and increased capacity is no longer needed. | 525000 | 525000 | 0 |  |  |  | 525000 | 0 | 4742446
[23 empty] | Actual Cost of Projects Completed This Month (Will Not Appear on Next Month Report): | Estimated Cost of Projects Completed This Month: | Estimated Cost of Projects Remaining Active This Month: | Total Estimated Cost of Projects Appearing in This Report:
[23 empty] | 3882311 | 3447660 | 211576693.36 | 215024353.36
[24 empty] | 4 | 87 | 91 | Project Count
[24 empty] | Completed | Active | Total
Note on A82: aboling: THIS PROJECT NUMBER ENTERED BY PUC STAFF TO FACILITATE TROUBLESHOOTING OF THIS REPORT.
Note on A85: aboling: THIS PROJECT NUMBER EDITED BY PUC STAFF TO FACILITATE TROUBLESHOOTING OF THIS REPORT. "DRC" WAS USED TWICE.
Note on A87: aboling: THIS PROJECT NUMBER ENTERED BY PUC STAFF TO FACILITATE TROUBLESHOOTING OF THIS REPORT.
Note on A90: aboling: THIS PROJECT NUMBER ENTERED BY PUC STAFF TO FACILITATE TROUBLESHOOTING OF THIS REPORT.
Note on A91: aboling: THIS PROJECT NUMBER ENTERED BY PUC STAFF TO FACILITATE TROUBLESHOOTING OF THIS REPORT.
Note on A92: aboling: THIS PROJECT NUMBER ENTERED BY PUC STAFF TO FACILITATE TROUBLESHOOTING OF THIS REPORT.
Note on A97: aboling: THIS PROJECT NUMBER EDITED BY PUC STAFF TO FACILITATE TROUBLESHOOTING OF THIS REPORT. "DRC" WAS USED TWICE.
Note on H1: aboling: Please enter only a single integer, if possible.
Note on I1: aboling: Please enter only a single integer, if possible.
Note on M1: aboling: If applicable.
Note on N1: aboling: If applicable.
Note on AD51: aboling: FORMULA DELETED TO ACCOMMODATE PROJECT NUMBER CHANGE.
Note on AD65: aboling: FORMULA DELETED TO ACCOMMODATE DUPLICATION IN PROJECT NUMBERS!!.
Note on AD67: aboling: FORMULA DELETED TO ACCOMMODATE PROJECT NUMBER CHANGE.
Note on AD68: aboling: FORMULA DELETED TO ACCOMMODATE PROJECT NUMBER CHANGE.
Note on AD69: aboling: FORMULA DELETED TO ACCOMMODATE PROJECT NUMBER CHANGE.
Note on AD75: aboling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT.
Note on AD76: aboling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT.
Note on AD77: aboling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT.
Note on AD78: aboling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT.
Note on AD79: aboling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT.
Note on AE51: aboling: FORMULA DELETED TO ACCOMMODATE PROJECT NUMBER CHANGE.
Note on AE65: aboling: FORMULA DELETED TO ACCOMMODATE DUPLICATION IN PROJECT NUMBERS!!.
Note on AE67: aboling: FORMULA DELETED TO ACCOMMODATE PROJECT NUMBER CHANGE.
Note on AE68: aboling: FORMULA DELETED TO ACCOMMODATE PROJECT NUMBER CHANGE.
Note on AE69: aboling: FORMULA DELETED TO ACCOMMODATE PROJECT NUMBER CHANGE.
Note on AE75: aboling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT.
Note on AE76: aboling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT.
Note on AE77: aboling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT.
Note on AE78: aboling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT.
Note on AE79: aboling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT.
Note on AF51: aboling: FORMULA DELETED TO ACCOMMODATE PROJECT NUMBER CHANGE.
Note on AF65: aboling: FORMULA DELETED TO ACCOMMODATE DUPLICATION IN PROJECT NUMBERS!!.
Note on AF67: aboling: FORMULA DELETED TO ACCOMMODATE PROJECT NUMBER CHANGE.
Note on AF68: aboling: FORMULA DELETED TO ACCOMMODATE PROJECT NUMBER CHANGE.
Note on AF69: aboling: FORMULA DELETED TO ACCOMMODATE PROJECT NUMBER CHANGE.
Note on AF75: aboling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT.
Note on AF76: aboling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT.
Note on AF77: aboling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT.
Note on AF78: aboling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT.
Note on AF79: aboling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT.

## PEC
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost (Total) | Final Estimated Project Cost (Total) | Final Actual Project Cost (Total) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS | Estimated OR Actual Project Cost (SUBSTATION) |  | Last Month: | Current minus last month: | Cumulative Sum
CR900910Y | WIMBERLY TO DRIPPING SPRINGS | WIMBERLY, DRIPPING SPRINGS, HAYS COUNTY | CONSTRUCT 138KV FROM WIMBERLY TO DRIPPING SPRINGS | UNKNOWN | UNKNOWN |  | 2269408 |  |  |  | 0% | NA | 138 | 13.9 | 795 ACSR DRAKE,SINGLE | SINGLE WOOD POLE | NA | NA | NA | NA | 11014 | THIS CCN APPLICATION WAS VACATED AND DISMISSED BY THE PUC ON 03/30/04. |  | 0 | 0 |  |  | 2269408 | -2269408 | -2269408
XE974659Y | FRIENDSHIP TO MANCHACA | HAYS, TRAVIS COUNTY | CONSTRUCT 138KV FROM FRIENDSHIP TO MANCHACA SUBS, NEW SUBSTATION IN CIRCLE C | UNKNOWN | UNKNOWN |  | 6863881 |  |  |  | 0% | NA | 138 | 7.8 | 795 ACSR DRAKE,SINGLE | SINGLE POLE, STEEL OR CONCRETE | NA | NA | NA | NA | 18389 | 3700 FEET ACROSS CIRCLE C GOLF COURSE WILL BE UNDERGROUND | 6863881 | 0 | 6863881 |  |  | 6863881 | 0 | -2269408
96-WO3319 | CANYON TO KYLE REBUILD | HAYS, COUNTY | INSTALL NEW STRUCTURES, INSULATORS, AND BUNDLED 795 ACSR CONDUCTORS | 2004-03-15 |  |  | 1600000 |  |  |  | 5% | 69 | 138 | 2.9 mi | 795 ACSR DRAKE, BUNDLE | SINGLE POLE, STEEL AND CONCRETE, WITH 2-H | 60 | 2.9 mi | 60 | 2.9 mi | 25.101(C)(5)(B) | LINE WILL BE ENERGIZED AT 69 KV UNTIL OTHER LINES ARE REBUILT. | 1600000 | 0 | 1600000 |  |  | 1600000 | 0 | -2269408
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
|  | NEW: | [20 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | Actual Cost of Projects Completed This Month (Will Not Appear on Next Month Report): | Estimated Cost of Projects Completed This Month: | Estimated Cost of Projects Remaining Active This Month: | Total Estimated Cost of Projects Appearing in This Report:
[23 empty] | 0 | 0 | 8463881 | 8463881
[24 empty] | 0 | 2 | 2 | Project Count
[24 empty] | Completed | Active | Total
Note on H1: aboling: Please enter only a single integer, if possible.
Note on I1: aboling: Please enter only a single integer, if possible.
Note on M1: aboling: If applicable.
Note on N1: aboling: If applicable.

## CNP
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost (Total) | Final Estimated Project Cost (Total) | Final Actual Project Cost (Total) | % Variance | Percent Complete | Existing Voltage | Upgraded or New Voltage | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS | Estimated OR Actual Project Cost (SUBSTATION) |  | Last Month: | Current minus last month: | Cumulative Sum
423 | Alexander Island Crossing of Houston Ship Channel | Harris | 138 kV Raising of Ckts. 03J & 88B as mandated by the Corps of Engineers for clearance over the Houston Ship Channel | 2002-10-21 | 2004-02-20 |  | 1740000 | 4010000 |  |  | 99% | 138 | NA | 1.6 | 2-959.6 ACSS | Steel Towers | 150 | 0.8 | NA | NA | 25.101(c)(2)(C)(v) | Construction Complete. | 4010000 | 0 | 4010000 |  |  | 4010000 | 0 | 0
412 | North Belt - Intercontinental | Harris | 138 kV Partial Reconductor and Partial Rebuild of Ckts. 67B & 67C | 2003-11-03 | 2004-03-28 |  | 1820000 | 486000 |  |  | 99% | 138 | NA | 3.6 | 2-795 AAC 2-795 ACSR | Steel Towers | 65-150 | 3.6 | NA | NA | 25.101(c)(2)(C)(ii) | Construction Complete. | 486000 | 0 | 486000 |  |  | 486000 | 0 | 0
423.2 | Deepwater Crossing of Houston Ship Channel | Harris | 138 kV Raising of Ckts. 21K, 84C & 94K as mandated by the Corps of Engineers for clearance over the Houston Ship Channel | 2003-10-01 | 2003-11-21 |  | 680000 | 1210000 | 1075127 | -11.15% | 100% | 138 | NA | 3 | 2-959.6 ACSS | Steel Towers | 80 | 1 | NA | NA | 25.101(c)(2)(C)(v) | Last time to report. Overhead allocations were lower than estimated. | 1210000 | 1210000 | 0 |  |  | 1210000 | 0 | 0
468 | Beltway 8 @ S. H. 249 | Harris | Alteration of 69 kV Ckt. 29A, 138 kV Ckts. 67A, 81A, & 95A, and 345 kV Ckt. 97A within 200 feet of the existing facilities as requested by Harris County Toll Road Authority for toll road construction | 2003-03-10 | 2003-12-15 |  | 3110000 | 3110000 | 2616718 | -15.86% | 100% | 69, 138, 345 | NA | 2.1 | 795 AAC, 2-795 ACSR, 3-959.6 ACSS | Steel Poles, Steel Towers | Street, 65-200 | 0.78 | NA | NA | 25.101(c)(2)(C)(v) | Last time to report. Labor cost was lower than estimated because continuous outages were available. Actual cost to be reimbursed by HCTRA. | 3110000 | 3110000 | 0 |  |  | 3110000 | 0 | 0
403 | PHR - Webster | Galveston, Harris | Reconductor and Partial Rebuild of 138 kV Ckt. 93A | 2003-08-27 | 2004-05-01 |  | 2125000 | 3465000 |  |  | 80% | 138 | NA | 11.9 | 2-959.6 ACSS | Steel Towers | Power Plant Property, 40-660 | 11.9 | NA | NA | 25.101(c)(2)(C)(ii) |  | 3465000 | 0 | 3465000 |  |  | 3465000 | 0 | 0
473 | Atascocita - Kingwood Corner | Harris | Reconductor and Rebuild of 138 kV Ckt. 66E | 2003-09-15 | 2004-01-07 |  | 3700000 | 5740000 | 5720148 | -0.3459% | 100% | 138 | NA | 5.1 | 2-959.6 ACSS | Concrete Poles, Steel Poles, Steel Towers | 30-130 | 5.1 | NA | NA | 25.101(c)(2)(C)(ii) | Last time to report. | 5740000 | 5740000 | 0 |  |  | 5740000 | 0 | 0
310 | I-10 Widening | Harris | Alteration of 138 kV Ckts. 73A and 81D within 200 feet of the existing facilities as requested by TxDOT for highway construction | 2003-10-10 | 2006-05-18 |  | 60590000 | 60590000 |  |  | 9% | 138 | NA | 11.6 | 3000 CU, 3500 CU | Steel Poles, Underground Cable | Street, 40 | 5.8 | 0-60 | 0.12 | 25.101(c)(2)(C)(v) | Actual cost to be reimbursed by TxDOT. | 60590000 | 0 | 60590000 |  |  | 60590000 | 0 | 0
404 | Glenwood Corner - King Corner | Harris | Reconductor and Rebuild of 138 kV Ckt. 94A | 2003-12-31 | 2004-03-16 |  | 1375000 | 1700000 |  |  | 99% | 138 | NA | 3.6 | 2-959.6 ACSS | Steel Towers, Concrete Poles | 187-300 | 3.6 | NA | NA | 25.101(c)(2)(C)(ii) | Construction Complete. | 1700000 | 0 | 1700000 |  |  | 1700000 | 0 | 0
544 | South Lane City - Wharton | Wharton | Partial Rebuild of 138 kV Ckt. 60B | 2004-09-01 | 2004-12-31 |  | 2120000 | 600000 |  |  | 0% | 138 | NA | 11.3 | 927 ACAR | Wooden H-Frames, Steel Poles | 40-100 | 11.3 | NA | NA | 25.101(c)(2)(C)(ii) |  | 600000 | 0 | 600000 |  |  | 600000 | 0 | 0
524 | Bertner Road Relocation | Houston, Harris | Alteration of 138 kV Ckt. 08I as requested by the City of Houston for road construction | 2004-04-05 | 2004-04-16 |  | 150000 | 200000 |  |  | 95% | 138 | NA | 0.23 | 2000 AAC, 1433.6 ACSS | Wood Pole, Concrete Poles, Steel Tower | Street, 35-70 | 0.09 | Street, 30-47 | 0.14 | 25.101(c)(5)(F) | Actual cost to be reimbursed by the City of Houston. | 200000 | 0 | 200000 |  |  | 150000 | 50000 | 50000
556 | Fairmont Parkway Relocation | LaPorte, Harris | Alteration of 138 kV Ckts.79B & 96B and 345 kV Ckt. 97D as requested by Port of Houston Authority for highway construction | 2003-12-01 | 2004-01-09 |  | 250000 | 250000 | 349806 | 39.92% | 100% | 138, 345 | NA | 0.27 | 2-795 ACSR | Steel Towers | 120-146 | 0.09 | NA | NA | 25.101(c)(5)(F) | Last time to report. Labor cost was higher than estimated due to increased scope. Actual cost to be reimbursed by POHA. | 250000 | 250000 | 0 |  |  | 250000 | 0 | 50000
361 | Karsten - Manvel Tap | Alvin, Iowa Colony, Manvel, Brazoria | Partial Rebuild of 69 kV Ckt. 53D | 2004-04-07 | 2004-07-15 |  | 1955000 | 2306000 |  |  | 1% | 69 | NA | 5.1 | 1433 ACSS | Steel Towers | 250-360 | 5.1 | NA | NA | 25.101(c)(5)(B) |  | 2306000 | 0 | 2306000 |  |  | 2306000 | 0 | 50000
777 | W.A. Parish - Texas Instruments | Thompsons, Sugar Land, Stafford, Fort Bend | Routine maintenance of 138 kV Ckt. 05G | 2003-12-09 | 2004-04-01 |  | 1100000 | 1100000 |  |  | 99% | 138 | NA | 20.3 | 2-795 AAC, 2-795 ACSR, 2000 AAC, 795 AAC, 795 ACSR | Wooden H-Frames, Steel Towers, Steel Poles | 50-3160 | 20.3 | NA | NA | 25.83 (a)(3) | Construction Complete. | 1100000 | 0 | 1100000 |  |  | 1100000 | 0 | 50000
777.1 | W.A. Parish - Britmoore | Thompsons, Sugar Land, Stafford, Fort Bend, Houston, Harris | Routine maintenance of 138 kV Ckt. 09A | 2003-12-08 | 2004-05-03 |  | 1400000 | 1400000 |  |  | 95% | 138 | NA | 23.6 | 2-795 AAC, 795 ACSR, 2-795 ACSR | Wooden H-Frames, Steel Towers | 150-3160 | 23.6 | NA | NA | 25.83 (a)(3) |  | 1400000 | 0 | 1400000 |  |  | 1400000 | 0 | 50000
242 | CNP - LCRA Interconnection | Harris | LCRA Hockley 138 kV Ckt. T-391 interconnection | 2004-02-25 | 2004-05-15 |  | 800000 | 738000 |  |  | 45% | 138 | NA | 1.6 | 1433 ACSS | Steel Towers, Steel Poles, Concrete Poles | 80 | 1.6 | NA | NA | 25.83 (a)(3) | This project is being added to interconnect a transmission line approved in Docket 24380 for LCRA. | 738000 | 0 | 738000 |  |  | 738000 | 0 | 50000
536 | Willow - Klein | Harris | Reconductor and Partial Rebuild of 138 kV Ckt. 81F | 2004-01-26 | 2004-02-15 |  | 450000 | 450000 |  |  | 99% | 138 | NA | 2.3 | 2-959.6 ACSS | Steel Towers, Concrete Poles | 50-130 | 2.3 | NA | NA | 25.101(c)(5)(B) | Construction Complete. | 450000 | 0 | 450000 |  |  | 450000 | 0 | 50000
888 | Webster - Amoco | Galveston, Brazoria | Routine maintenance of 138 kV Ckt. 04A | 2004-02-24 | 2004-05-01 |  | 350000 | 350000 |  |  | 95% | 138 | NA | 28.3 | 2-795 AAC, 2-795 ACSR, 795 ACSR, 795 AAC, 2-927 ACAR | Steel Towers, Wooden H-Frames | 80-1800 | 28.3 | NA | NA | 25.83 (a)(3) |  | 350000 | 0 | 350000 |  |  | 350000 | 0 | 50000
361.1 | W.A. Parish - Oasis | Thompsons, Arcola, Fort Bend, Alvin, Iowa Colony, Manvel, Brazoria | Bundling, Partial Reconductor, and Partial Rebuild of 345 kV Ckt. 99B | 2004-02-23 | 2004-08-01 |  | 4320000 | 4406000 |  |  | 15% | 345 | NA | 19.8 | 2-795 ACSR, 2-927 ACAR, 2-1433 ACSS | Steel Towers | 200-3275 | 19.8 | NA | NA | 25.101(c)(5)(B) |  | 4406000 | 0 | 4406000 |  |  | 4406000 | 0 | 50000
361.2 | Oasis Substation | Manvel, Brazoria | 345 kV Service to Oasis Substation within one mile of Ckts. 99B and 99A | 2004-02-16 | 2004-10-01 |  | 1830000 | 1622000 |  |  | 15% | 345 | NA | 0.5 | 2-795 ACSR, 2-1433 ACSS | Steel Towers | Substation Property, 200 | 0.2 | NA | NA | 25.101(c)(5)(A) |  | 1622000 | 0 | 1622000 |  |  | 1622000 | 0 | 50000
571 | BNSF Relocations | Pasadena, Harris | Relocation of a portion of 138 kV Ckts. 06C, 35B, 35F, 35C, 94D and 94E at the request of and at the expense of Burlington Northern and Santa Fe Railway Company | 2004-02-19 | 2004-03-11 |  | 155000 | 155000 |  |  | 99% | 138 | NA | 1 | 2-795 AAC, 2-795 ACSR | Steel Towers, Concrete Poles, Wooden H-Frames | 55-150 | 0.6 | NA | NA | 25.101(c)(5)(D) | Construction Complete. Actual cost to be reimbursed by BNSF. | 155000 | 0 | 155000 |  |  | 155000 | 0 | 50000
484 | CNP - TNP Tie | Texas City, Galveston | Reconductor 138 kV Ckt. 01X | 2004-03-01 | 2004-09-01 |  | 120000 | 126000 |  |  | 50% | 138 | NA | 0.4 | 2-959.6 ACSS | Steel Towers | 2400-2500 | 0.4 | NA | NA | 25.101(c)(5)(B) |  | 126000 | 0 | 126000 |  |  | 126000 | 0 | 50000
560 | Polaris Tap - Clear Lake/Genoa Tap | Pasadena, Harris | Partial Rebuild and Partial Reconductor of 138 kV Ckt. 95F | 2004-04-12 | 2004-05-21 |  | 340000 | 390000 |  |  | 1% | 138 | NA | 3.3 | 795 ACSR, 1433 ACSS | Steel Towers | 150 | 3.3 | NA | NA | 25.101(c)(5)(B) |  | 390000 | 0 | 390000 |  |  | 340000 | 50000 | 100000
888.1 | W.A. Parish - West Columbia | Thompsons, Fort Bend, Brazoria | Routine maintenance of 138 kV Ckt. 02B | 2004-03-01 | 2004-04-16 |  | 730000 | 730000 |  |  | 95% | 138 | NA | 30 | 2-795 AAC, 2-795 ACSR, 795 ACSR, 795 AAC | Wooden H-Frames, Steel Towers | 80-3450 | 30 | NA | NA | 25.83 (a)(3) | Construction Complete. | 730000 | 0 | 730000 |  |  | 730000 | 0 | 100000
888.2 | P.H. Robinson - West Galveston | Texas City, Dickinson, League City, Santa Fe, La Marque, Hitchcock, Galveston, Galveston | Routine maintenance of 138 kV Ckt. 93B | 2004-06-28 | 2004-09-01 |  | 500000 |  |  |  | 0% | 138 | NA | 44.3 | 2-795 AAC, 2-795 ACSR, 795 ACSR, 795 AAC, 2-397 ACSR | Steel Towers, Wooden H-Frames, Wood Poles | Street, 50-2500 | 44.3 | NA | NA | 25.83 (a)(3) |  | 500000 | 0 | 500000 |  |  | 500000 | 0 | 100000
888.3 | East Bernard - South Lane City | East Bernard, Wharton, Wharton | Routine maintenance of 138 kV Ckt. 60B | 2004-09-01 | 2004-10-01 |  | 315000 |  |  |  | 0% | 138 | NA | 27.3 | 795 AAC, 927.2 ACAR | Steel Poles, Wooden H-Frames | Street, 25-100 | 27.3 | NA | NA | 25.83 (a)(3) | Revised Existing ROW Length. | 315000 | 0 | 315000 |  |  | 315000 | 0 | 100000
548 | Spring ISD Relocation | Houston, Harris | Relocation of a portion of 138 kV Ckts. 66D & 67C at the request of and at the expense of Spring ISD on ROW provided by Spring ISD | 2004-09-01 | 2004-10-15 |  | 700000 |  |  |  | 0% | 138 | NA | 1.7 | 2-795 AAC, 795 AAC | Concrete Poles | NA | NA | 125 | 0.85 | 25.101(c)(5)(D) | New Project. Actual cost to be reimbursed by Spring ISD. | 700000 | 0 | 700000 |  |  | #N/A | #N/A | #N/A
|  | New: | 700000 | [19 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[8 empty] | 0 | [14 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[8 empty] | 0 | [14 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[8 empty] | 0 | [14 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[8 empty] | 0 | [14 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[8 empty] | 0 | [14 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[8 empty] | 0 | [14 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | Actual Cost of Projects Completed This Month (Will Not Appear on Next Month Report): | Estimated Cost of Projects Completed This Month: | Estimated Cost of Projects Remaining Active This Month: | Total Estimated Cost of Projects Appearing in This Report:
[23 empty] | 9761799 | 10310000 | 86339000 | 96649000
[24 empty] | 4 | 22 | 26 | Project Count
[24 empty] | Completed | Active | Total
Note on H1: aboling: Please enter only a single integer, if possible.
Note on I1: aboling: Please enter only a single integer, if possible.
Note on M1: aboling: If applicable.
Note on N1: aboling: If applicable.

## SPS
RIGHT OF WAY
SPS PROJECT NUMBER | PROJECT NAME | LOCATION | DESCRIPTION | START DATE | FINISH DATE | ESTIMATED | FINAL | VAR. (%) | % COM | Length | CONDUCTOR | STRUCTURE | W | L | W | L | RULE SECTION AND/OR PUC CONTROL NUMBER | COMMENTS | COMPLETED PROJECTS | ACTIVE PROJECTS | DATE APPROVED | REQUESTED ADDITIONAL INFORMATION
J8202697 | Install Switch - Ckt V-1 | Hutchinson | Install 115 kV switch to allow for sectionalizing | 2001-12-26 | 2002-02-15 | 57538 |  |  | 0 | N/A |  | 4-pole wood | N/A | N/A | N/A | N/A | 25.101(c)(2)(C)(ii) the rebuilding, upgrading, bundling of conductors or reconductoring of an existing transmission facility; or the installation of an additional circuit(s) on facilities that were originally certificated for multiple-circuit capacity, provided no additional right of way is required. Activities described in this clause which occur in the certificated area of another electric utility require that utility to be provided notice at least 30 days prior to the start of construction of the new facility. However, if the rebuilding, upgrading, bundling of conductors or reconductoring is being done to serve a utility certificated in the area where those activities are to take place, then no such notice is required. However, within multiply-certificated areas, only notice, not consent, is required. For purposes of this section, "upgrading'' to a higher voltage shall be limited to 230 kV or less and "rebuilding'' work shall be limited to the replacement and/or respacing of structures along an existing route of the transmission line; | Delayed waiting for clearance |  | 57538
10019068 | Amarillo South Interchange |  | Please See Docket No. 26763 | 2003-03-06 | 2003-07-31 | 8387151 | N/A | N/A | [8 empty] | 26763 | project completed, waiting on final cost figures. |  | 8387151
| Amarillo South Interchange | Randall | New 5.5 mile 230kV double circuit line | 2003-03-06 | 2003-07-31 | 3081195 | N/A | N/A | 100% | 29040 | 795 MCM ACSR | Single-Shaft Steel | N/A | N/A | 80 | 29040
| Amarillo South Interchange | Randall | New 0.5 mile 115kV double circuit line | 2003-03-06 | 2003-07-31 | 689529 | N/A | N/A | 100% | 2640 | 397.5 MCM ACSR | Single-Shaft Steel | N/A | N/A | 60 | 2640
| Amarillo South Interchange | Randall | New substation | 2003-03-06 | 2003-07-31 | 4416427 | N/A | N/A | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10229724 | Y-79 Reconductor | Lamb/Hale | Reconductor from 4/0 to 397.5 MCM | 2003-08-04 | 2003-10-06 | 1769000 | N/A | N/A | 25% | 29 miles | 397.5 MCM ACSR | 2-pole wood | 45 ft. | 29miles | N/A | N/A |  |  |  | 1769000
10229735 | Amerada Hess to Doss | Gaines | New 5.5 miles of 115 kV, 397.5 MCM Transmission line. | 2004-07-01 | 2004-12-31 | 850000 | N/A | N/A | 10% | 5.5 miles | 397.5 MCM ACSR | 2-pole wood |  |  | 60ft. | 5.5 miles | 28390 |  |  | 850000
[19 empty] | 0 | 11063689 | 11063689
NEW
EXISTING
CONSTRUCTION COSTS
NEW
EXISTING
CONSTRUCTION COSTS

## STEC
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost (Total) | Final Estimated Project Cost (Total) | Final Actual Project Cost (Total) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS | Estimated OR Actual Project Cost (SUBSTATION) |  | Last Month: | Current minus last month: | Cumulative Sum
702.2048 | Oaks 138kV | Atascosa | Install Breaker, Switch and Capacitor | 5/2001 | 12/2002 | 2004-01-01 | 285000 | 285000 | 257479.01 | -9.656% | 100% | 138 | [8 empty] | 25.101(c) (5)(B)(i) | Closed out. | 285000 | 285000 | 0 |  |  | 285000 | 0 | 0
703.2225, 703.2199, 803.2198, 803.2200, 703.2201 | Hurricane Claudette Damage | Calhoun, Jackson, Victoria, Refugio, Goliad, Karnes, Bee, Live Oak, Wilson, Atascosa, McMullen | Replace poles and equipment on the 69 and 138 kV transmission system and straightem poles on the 69 and 138 kV system damaged by Hurricane Claudette. | 7/2003 | 8/2003 | 2003-08-01 | 613062.33 | 613062 | 613062.33 | 5.383e-05% | 100% | 69&138 |  |  | #4/0 ACSR | [5 empty] | 25.101(c) (3) | Closed out. | 613062 | 613062 | 0 |  |  | 613062.33 | -0.33 | -0.33
703.2065 | Ekstrom Fish Farm | Wharton & Matagorda | Relocate 69 kV line for landowner at landowner expense. | 11/2003 | 12/2003 | 2004-01-01 | 190000 | 190000 | 157391.04 | -17.16% | 100% | 69 |  | 1.7 | #4/0 ACSR | Single pole | 50 | 1.3 | 50 | 1.7 | 25.101(c) (5)(D) | Relocation at Owner's request and expense. | 190000 | 190000 | 0 |  |  | 190000 | 0 | -0.33
701.2050, 7991120, 799-4124, 801.2049 &703.1266 | Calallen Sub Rebuild | Nueces | Rebuild 69 kV Sw. Sta. | 6/2000 | 6/2002 |  | 2950000 | 2950000 |  |  | 100% | [9 empty] | 25.101 (c) (2) (B) | Accounting closing out. | 2950000 | 0 | 2950000 |  |  | 2950000 | 0 | -0.33
700.2394, 700.9262 , 700.9397, 700.4396 &703.4261 | Orange Grove 69 kV | Jim Wells | Exspand substation site for transformer and 69 kV additions. | 12/2000 | 6/2002 |  | 520000 | 520000 |  |  | 98% | [9 empty] | 25.101 (c) (2) (C ) (ii) | Minor work left and clean up. | 520000 | 0 | 520000 |  |  | 520000 | 0 | -0.33
700.4322 &800.4321 | Midfield West Metering | Wharton | Install Interval Metering. | 8/2000 | 10/2002 |  | 7500 | 7500 |  |  | 100% | [9 empty] | 25.101 (c) (2) (C ) (i) | Accounting closing out. | 7500 | 0 | 7500 |  |  | 7500 | 0 | -0.33
700.4382 &800.4381 | Robstown Metering | Nueces | Install Interval Metering. | 12/2000 | 10/2002 |  | 17500 | 17500 |  |  | 100% | [9 empty] | 25.101 (c) (2) (C ) (i) | Accounting closing out. | 17500 | 0 | 17500 |  |  | 17500 | 0 | -0.33
700.4384 &800.4383 | San Diego Metering | Duval | Install Interval Metering. | 12/2000 | 10/2002 |  | 7500 | 7500 |  |  | 100% | [9 empty] | 25.101 (c) (2) (C ) (i) | Accounting closing out. | 7500 | 0 | 7500 |  |  | 7500 | 0 | -0.33
700-4257, 700-6259, 700-9258 &800-4256 | Plainview | Wharton | Install equipment required for substation automation, SCADA & Communications | 8/2000 | 6/2001 |  | 150000 | 150000 |  |  | 100% | [9 empty] | 25.101 (c) (2) (C ) (i) | Closing out. | 150000 | 0 | 150000 |  |  | 150000 | 0 | -0.33
700-6267, 700-9266, 700-4265 &800-4264 | Clemville South | Matagorda | Install equipment required for substation automation, SCADA & Communications | 8/2000 | 6/2001 |  | 150000 | 150000 |  |  | 100% | [9 empty] | 25.101 (c) (2) (C ) (i) | Closing out. | 150000 | 0 | 150000 |  |  | 150000 | 0 | -0.33
700-6191, 700-9190, 700-4189 &800-4188 | Simmons | Live Oak | Install equipment required for substation automation, SCADA & Communications | 8/2000 | 6/2001 |  | 150000 | 150000 |  |  | 100% | [9 empty] | 25.101 (c) (2) (C ) (i) | Accounting closing out. | 150000 | 0 | 150000 |  |  | 150000 | 0 | -0.33
700-6239, 700-9238, 700-4237 &800-4236 | Charco | Goliad | Install equipment required for substation automation, SCADA & Communications | 8/2000 | 6/2001 |  | 150000 | 150000 |  |  | 100% | [9 empty] | 25.101 (c) (2) (C ) (i) | Accounting closing out. | 150000 | 0 | 150000 |  |  | 150000 | 0 | -0.33
700-9250, 700-6251, 700-4249 &800-4248 | Ganado | Jackson | Install equipment required for substation automation, SCADA & Communications | 8/2000 | 6/2001 |  | 150000 | 150000 |  |  | 100% | [9 empty] | 25.101 (c) (2) (C ) (i) | Accounting closing out. | 150000 | 0 | 150000 |  |  | 150000 | 0 | -0.33
700-1028, 700-4129 &800-4128 | Charlotte | Atascosa | Install equipment required for substation automation, & Communications | 8/2000 | 6/2001 |  | 150000 | 150000 |  |  | 100% | [9 empty] | 25.101 (c) (2) (C ) (i) | Accounting closing out. | 150000 | 0 | 150000 |  |  | 150000 | 0 | -0.33
700-4213, 700-6215, 700-9214 &800-4212 | Coy City | Karnes | Install equipment required for substation automation, SCADA & Communications | 8/2000 | 6/2001 |  | 150000 | 150000 |  |  | 100% | [9 empty] | 25.101 (c) (2) (C ) (i) | Accounting closing out. | 150000 | 0 | 150000 |  |  | 150000 | 0 | -0.33
700-9246, 700.6247, 700-4245, &800-4244 | Lolita | Jackson | Install equipment required for substation automation, SCADA & Communications | 8/2000 | 6/2001 |  | 150000 | 150000 |  |  | 100% | [9 empty] | 25.101 (c) (2) (C ) (i) | Accounting closing out. | 150000 | 0 | 150000 |  |  | 150000 | 0 | -0.33
700-4201, 700-9202, 700-6203 &800-4200 | Tilden | McMullen | Install equipment required for substation automation, SCADA & Communications | 8/2000 | 6/2001 |  | 150000 | 150000 |  |  | 100% | [9 empty] | 25.101 (c) (2) (C ) (i) | Accounting closing out. | 150000 | 0 | 150000 |  |  | 150000 | 0 | -0.33
700-4225, 700-6227, 700-9226 &800-4224 | Van Humble | Jackson | Install equipment required for substation automation, SCADA & Communications | 8/2000 | 6/2001 |  | 150000 | 150000 |  |  | 100% | [9 empty] | 25.101 (c) (2) (C ) (i) | Closing out. | 150000 | 0 | 150000 |  |  | 150000 | 0 | -0.33
797-2023, 797-2027 897-2026, 702.2061 &802.2060 | Calliham South Sw. | Live Oak | Install MW, SCADA and MOD | 1/1997 | 12/2002 |  | 80000 | 80000 |  |  | 99% | [9 empty] | 25.101 (c) (2) (C ) (ii) | Closing out. | 80000 | 0 | 80000 |  |  | 80000 | 0 | -0.33
700-6151, 700-4149, 700-9150 &800-4148 | Refugio | Refugio | Install equipment required for substation automation, SCADA & Communications | 8/2000 | 12/2002 |  | 150000 | 150000 |  |  | 100% | [9 empty] | 25.101 (c) (2) (C ) (i) | Closing out. | 150000 | 0 | 150000 |  |  | 150000 | 0 | -0.33
799.1093, 799-2089, 799.4091, 899-2088, 899-1092 899-4090 &799.2087 | Port O'Connor | Calhoun | Expand existing substation | 10/1999 | 10/2002 |  | 850000 | 850000 |  |  | 64% | [9 empty] | 25.101 (c) (2) (C ) (ii) | Dirt work contract ready to let. | 850000 | 0 | 850000 |  |  | 850000 | 0 | -0.33
702.2103 & 802.2102 | Mathis | San Patricio | Install 2 69 kV Breakers, Panels, and Comm. | 6/2001 | 6/2002 |  | 400000 | 400000 |  |  | 65% | [9 empty] | 25.101(c) (5)(B)(i) | Substation house remodeled. | 400000 | 0 | 400000 |  |  | 400000 | 0 | -0.33
700.2393 | Nursery Breakers | Victoria | Install 2 69 kV Breakers and Comm. | 12/2000 | 6/2002 |  | 400000 | 400000 |  |  | 25% | [9 empty] | 25.101(c) (5)(B)(i) | Equipment in. | 400000 | 0 | 400000 |  |  | 400000 | 0 | -0.33
700.2402 | Inez Breakers | Victoria | Install 2 69 kV Breakers and Comm. | 12/2000 | 6/2002 |  | 400000 | 400000 |  |  | 25% | [9 empty] | 25.101(c) (5)(B)(i) | Equipment in. | 400000 | 0 | 400000 |  |  | 400000 | 0 | -0.33
702.2057 | Placedo 69 kV Breaker Addition | Victoria | Install 69 kV Breaker on the Vanderbilt line | 12/2000 | 4/2003 |  | 200000 | 75000 |  |  | 100% | 69 | [8 empty] | 25.101(c) (5)(B)(i) | Minor work left. | 75000 | 0 | 75000 |  |  | 75000 | 0 | -0.33
703.2017 | Olmos Breaker | Bee | Install 2 69 kV Breakers and Comm. | 1/2004 |  |  | 400000 |  |  |  | 60% | 69 | [8 empty] | 25.101(c) (5)(B)(i) | Pads poured. | 400000 | 0 | 400000 |  |  | 400000 | 0 | -0.33
801.2103 701.2104 | Sargent Breakers | Matagorda | Install 2 69 kV Breakers and Comm. | 1/2004 |  |  | 400000 |  |  |  | 60% | 69 | [8 empty] | 25.101(c) (5)(B)(i) | Pads poured. | 400000 | 0 | 400000 |  |  | 400000 | 0 | -0.33
703.2063 | San Miguel 138 kV Recond. | Atascosa | Reconductor #795 to #1590 Kcmil 138 kV segment. | 9/2003 |  |  | 143000 | 143000 |  |  | 99% | 138 |  |  | 1-1590 ACSR | H Frame | 100 | 0.44 |  |  | 25.101(c) (5)(B)(i) | Clean up in process. | 143000 | 0 | 143000 |  |  | 143000 | 0 | -0.33
703.2068, 803.2067 | Bay City to Sargent 69kV Double Arming | Matagorda | Double arming of a portion of the 69 kV system. | 5/2003 | 7/2003 |  | 387000 | 387000 |  |  | 100% | 69 |  |  | #4/0 ACSR | Single pole | 50 | 18.5 |  |  | 25.101(c) (5)(B)(i) | Completed. Waiting on accounting. | 387000 | 0 | 387000 |  |  | 387000 | 0 | -0.33
703.2070,0803.2069 | Vanderbilt to Danevang 138kV Re-insulate | Jackson & Wharton | Replace insulators on a portion of the 138 kV system. | 3/2003 | 5/2003 |  | 251000 | 251000 |  |  | 100% | 138 |  |  | #477 ACSR | H Frame | 100 | 33.09 |  |  | 25.101 (c) (5) (B)(i) | Completed. Waiting on accounting. | 251000 | 0 | 251000 |  |  | 251000 | 0 | -0.33
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | Actual Cost of Projects Completed This Month (Will Not Appear on Next Month Report): | Estimated Cost of Projects Completed This Month: | Estimated Cost of Projects Remaining Active This Month: | Total Estimated Cost of Projects Appearing in This Report:
[23 empty] | 1027932.38 | 1088062 | 8938500 | 10026562
[24 empty] | 3 | 27 | 30 | Project Count
[24 empty] | Completed | Active | Total
Note on H1: aboling: Please enter only a single integer, if possible.
Note on I1: aboling: Please enter only a single integer, if possible.
Note on M1: aboling: If applicable.
Note on N1: aboling: If applicable.

## SULP
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost (Total) | Final Estimated Project Cost (Total) | Final Actual Project Cost (Total) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS | Estimated OR Actual Project Cost (SUBSTATION) |  | Last Month: | Current minus last month: | Cumulative Sum
PR.03.05003.CAP | SULP 138 kV Transmission Lower Loop | Hidalgo County | New 138 kV Transmission line from Bentsen Tap, south to the new Bentsen Substation, west to proposed Railroad Substation and then north to Bryan Road Tap. | 2002-09-01 | 2004-06-04 |  | 3978000 |  |  |  | 23 | na | 138 kV | 4.63 | 1590 acss single conductor | Concrete and steel poles with Davit Arms | na | na | 80 | 4.63 | 24874 | Poles and conductor are on site. Contruction RFP is out. Need to acquire final portion of ROW. | 3978000 | 0 | 3978000 |  |  | 3978000 | 0 | 0
PR.03.05051.CAP | Sharyland DC Interconnect with CFE | Hidalgo County | Install 150 MVA back to back HVDC interconnection with CFE at SU's Railroad Substation. | 2004-07-01 | 2005-12-31 |  | 0 |  |  |  | 0 | na | 138 kV | 0.8 | 795 acss single conductor | Concrete or Steel Poles |  |  | 80 | 0.8 | 28834 | Waiting on CCN approval. | 0 | 0 | 0 |  |  | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | Actual Cost of Projects Completed This Month (Will Not Appear on Next Month Report): | Estimated Cost of Projects Completed This Month: | Estimated Cost of Projects Remaining Active This Month: | Total Estimated Cost of Projects Appearing in This Report:
[23 empty] | 0 | 0 | 3978000 | 3978000
[24 empty] | 0 | 1 | 1 | Project Count
[24 empty] | Completed | Active | Total
Note on H1: aboling: Please enter only a single integer, if possible.
Note on I1: aboling: Please enter only a single integer, if possible.
Note on M1: aboling: If applicable.
Note on N1: aboling: If applicable.

## SWEPCO
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost (Total) | Final Estimated Project Cost (Total) | Final Actual Project Cost (Total) | % Variance | Percent Complete | Existing Voltage | Upgraded or New Voltage | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS | Estimated OR Actual Project Cost (SUBSTATION) |  | Last Month: | Current minus last month: | Cumulative Sum
40022879 | Pittsburg to Winnsboro 138kV Line | Camp, Wood, Franklin | Construct approximately 20 miles of new 138kV transmission line using single pole with davit arm construction. | 2005-09-05 | 2006-03-03 | na | 7426000 |  |  |  |  | na | 138 | 20 | 1590 ACSR with Static | single pole steel or concrete with davit arms | na | na | 100 | 20 | 28104 | The CCN was filed October 20, 2003. | 7426000 | 0 | 7426000 |  |  | 7426000 | 0 | 0
40030820 | Winnsboro to N. Mineola | Wood | Construct approximately 25 miles of new 138kV transmission line using single pole with davit arm construction. | 2005-12-19 | 2006-09-29 | na | 10269000 |  |  |  |  | na | 138 | 25 | 1590 ACSR with Static | single pole steel or concrete with davit arms | na | na | 100 | 25 | na | The CCN is scheduled to be filed July 2004. A full CCN will be required | 10269000 | 0 | 10269000 |  |  | 10269000 | 0 | 0
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[8 empty] | 0 | [14 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[8 empty] | 0 | [14 empty] | 0 | 0 | 0
[8 empty] | 0 | [14 empty] | 0 | 0 | 0
[8 empty] | 0 | [14 empty] | 0 | 0 | 0
[8 empty] | 0 | [14 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | Actual Cost of Projects Completed This Month (Will Not Appear on Next Month Report): | Estimated Cost of Projects Completed This Month: | Estimated Cost of Projects Remaining Active This Month: | Total Estimated Cost of Projects Appearing in This Report:
[23 empty] | 0 | 0 | 17695000 | 17695000
[24 empty] | 0 | 2 | 2 | Project Count
[24 empty] | Completed | Active | Total
Note on H1: aboling: Please enter only a single integer, if possible.
Note on I1: aboling: Please enter only a single integer, if possible.
Note on M1: aboling: If applicable.
Note on N1: aboling: If applicable.

## TNMP
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost (Total) | Final Estimated Project Cost (Total) | Final Actual Project Cost (Total) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS | Estimated OR Actual Project Cost (SUBSTATION) | REQUESTED ADDITIONAL INFORMATION | Last Month: | Current minus last month: | Cumulative Sum
GCEC22514 | Texas City Megaport | Texas City, Texas | Provide 138kV service to Texas City International Terminal by constructing a new 138kV transmission from TNMP Amoco substaion to TCIT substation on Shoal Island. A new breaker position will be built at Amoco. | 2003-01-01 |  |  | 2777000 |  |  |  | 0% | na | 138kV | 4.54 | 795 ACSR | Concrete | na | na | 40 | 4.5 | Rule 25.101(c)(2)(C)(i). | Still on hold pending decision from City of Texas City to mve forward. | 2777000 | 0 | 2777000 |  |  | 2777000 | 0 | 0
GCEC22518 | Valero Coker Expansion | Texas City, Texas | Provide 69Kkv looped service to new Coker plant via the contruction of 2-new 69kV line taps from TNMP Amoco and Terminal Substations. The line to be tapped is 69-D between TC Main and Terminal substations. Service will be terminated in new Valero substation thru 2-new TNMP 69kV breakers. | 2002-09-01 |  |  | 1880000 | 2200000 |  | % | 85% | na | 69kv | 2.4 | 795 ACSR | Concrete | na | na | 40 | 2 | Rule 25.101(c)(2)(C)(i). Docket#25601 | Construction on 69-D1 began 4/12/04 | 2200000 | 0 | 2200000 |  |  | 2200000 | 0 | 0
GCEC22521, GCEC22411 | Bp Amoco Interconection | Texas City, Texas | Contruction of new 138kV, 1-1/2 breaker switchyard and the upgrade of various other TNMP transmission lines and substations to provide for the interconnect of new Cogen to export 480MW onto the ERCOT grid. | 2002-10-01 |  |  | 15000000 |  |  |  | 80% | na | 138kV | 0.6 | 795 ACSS | Concrete | na | na | 50 | 1.7 | Rule 25.101(c)(2)(C)(i). Docket # 25970 | New Greenbelt switching station was energized on May 6 2003. Work continues on line upgrades. The next line scheduled to be completed is 138-7 (Heights- Freeway Park). We have started and are 40% complete with the new line Caddo-Greenbelt. | 15000000 | 0 | 15000000 |  |  | 15000000 | 0 | 0
GCEC24516 | Part of Bp Amoco Interconection | Texas City, Texas | Rebuild circuit 138-1B, Greenbelt to GAF | 2004-09-15 |  |  | 2000000 |  |  |  | 12% | 138kV | n/a | 4 | 636ACSS | Concrete | 40 | 4 | n/a | n/a | Rule 25.83(c)(3) | Line Clearance denied by ERCOT. Work will have to be rescheduled for Fall. | 2000000 | 0 | 2000000 |  |  | 2000000 | 0 | 0
GCEC24517 | Part of Bp Amoco Interconection | Texas City, Texas | Rebuild circuit 138-1A, GAF to PH Robinson | 2004-11-15 |  |  | 2800000 |  |  |  | 0% | 138kV | n/a | 4 | 636ACSS | Concrete | 40 | 6 | n/a | n/a | Rule 25.83(c)(3) | Will move start of work to Fall. | 2800000 | 0 | 2800000 |  |  | 2800000 | 0 | 0
GCEC24512 | rebuild of line 69-C | Texas City, Texas | Rebuild of TNMP 69kv circuit between Amoco and Terminal substations | 2004-05-27 |  |  | 1270000 |  |  |  | 0% | 69kv | na | 0.8 | 795ACSS | Concrete | 30 | 0.8 | n/a | n/a | Rule 25.83(c)(3) |  | 1270000 | 0 | 1270000 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
|  | NEW: | 1270000 |  |  |  |  | 0 | [19 empty] | #N/A | #N/A | #N/A
[23 empty] | Actual Cost of Projects Completed This Month (Will Not Appear on Next Month Report): | Estimated Cost of Projects Completed This Month: | Estimated Cost of Projects Remaining Active This Month: | Total Estimated Cost of Projects Appearing in This Report:
[23 empty] | 0 | 0 | 26047000 | 26047000
[24 empty] | 0 | 6 | 6 | Project Count
[24 empty] | Completed | Active | Total
Note on H1: aboling: Please enter only a single integer, if possible.
Note on I1: aboling: Please enter only a single integer, if possible.
Note on M1: aboling: If applicable.
Note on N1: aboling: If applicable.

## AEPN
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost | Final Estimated Project Cost | Final Actual Project Cost | % Variance | Percent Complete | Existing Voltage | Upgraded or New Voltage | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS | Estimated OR Actual Project Cost (SUBSTATION) |  | Last Month: | Current minus last month: | Cumulative Sum
24028549 24908005 40079168 | N McCamey- McCamey - Tippett | Upton, Crockett, and Pecos Counties | Rebuild 13.46 miles of 69kV line to 138 kV | 2002-08-26 | 2003-02-21 | 2003-02-21 | 4990000 |  |  |  | 99% | 69kV | 69kV | 13.46 mi. | Bundled 795 ACSR | Concrete single pole | center-line | 13.46 |  |  | Exempt per Subst. Rule 25.101(c)(2)(C)(ii) |  | 4990000 | 0 | 4990000 |  |  | 4990000 | 0 | 0
40066293 | N McCamey - LCRA Crane Tap Reconductor | Upton County, Texas | Rebuild 25 miles of existing N McCamey to McElroy 69kV to 138kV | 2003-02-05 | 2003-07-15 | 2003-07-15 | 8748410 |  |  |  | 99% | 69kV | 138kV | 25 mi. | Bundled 795 ACSR | Concrete single pole | center-line | 25 mi. |  |  | Exempt per Subst. Rule 25.101(c)(2)(C)(ii) | Notice sent to SWTEC | 8748410 | 0 | 8748410 |  |  | 8748410 | 0 | 0
24028557 24907990 40079274 | Tippet to W Yates Tap Reconductor | Pecos/Crockett Counties, Texas | Rebuild 9.98 miles of 69kV to 138kV | 2002-12-01 | 2003-05-12 | 2003-05-12 | 3803891 |  |  |  | 99% | 69kV | 138kV | 9.98 mi | Bundled 795 ACSR | Concrete single pole | center-line | 9.98 mi |  |  | Exempt per Subst. Rule 25.101(c)(2)(C)(ii) | Notice sent to Oncor | 3803891 | 0 | 3803891 |  |  | 3803891 | 0 | 0
40078782 | W Yates Tap - West Ytes Pump | Pecos County | Rebuild existing 69kV H-Frame and single pole line with single concrete pole, double circuit, 2-795 ACSR construction. | 2003-06-30 | 2003-08-29 | 2003-08-29 | 2019654 |  |  |  | 99% | 69kV | 69kV | 4.23 | Bundled 795 ACSR | Concrete single pole | center-line | 4.23 |  |  | Exempt per Subst. Rule 25.101(c)(2)(C)(ii) |  | 2019654 | 0 | 2019654 |  |  | 2019654 | 0 | 0
40081686 | W Yates Pump - Mesa View | Pecos County | Install approximately 300' of single circuit 2-795, 138kV line between existing poles, tying the MVS=MV line to the WYS-WYP line. The dead end structures will be installed when the lines are rebuilt. | 2003-11-12 | 2003-12-15 | 2004-01-04 | 200000 |  |  |  | 99% |  | 138kV | 0.1 | Bundled 795 ACSR | Concrete single pole | center-line | 0.1 |  |  | Exempt per Subst. Rule 25.101(c)(2)(C)(ii) | Sectionaliz-ing switches added to design | 200000 | 0 | 200000 |  |  | 200000 | 0 | 0
40079178 | Rio Pecos - Crane 69 kV Rebuild | Crane and Crockett Counties | Rebuild existing 69kV H-Frame and single pole line with single concrete pole, double circuit capable, 2-795 ACSR construction. | 2003-09-08 | 2003-02-23 | 2004-03-26 | 9721600 |  |  |  | 95% | 69kV | 138kV | 23 | Bundled 795 ACSR | Concrete single pole | center-line | 23 |  |  | Exempt per Subst. Rule 25.101(c)(5)(B) | Notice sent SWTEC, Oncor, Crane County Airport and landowners | 9721600 | 0 | 9721600 |  |  | 9721600 | 0 | 0
40079178a | Crane Line Extension | Crane County | Extension of the Rio Pecos - Crane 69 kV rebuild into the new LCRA Transmission Services Corp. Crane Switching Station. | 2003-09-08 | 2004-01-16 | 2004-03-26 | 358768 |  |  |  | 99% | 0 | 138kV | 0.56 | Bundled 795 ACSR | Concrete single pole(double ckt. capable) | 0 | 0 | 70'-80' | 0.56 | Exempt per Subst. Rule 25.101(c)(5)(A) | Consent has been given by the only impacted landowner. | 358768 | 0 | 358768 |  |  | 358768 | 0 | 0
24914185 | S. Abilene to Eskota Reconductor | Tayor/Nolan Counties, Texas | Reconductor and rebuild approximately 25.7 miles of existing 138kV transmission line. The old line is 40 ACRS on wood H-frame structures. The new line will be single pole structure with 795 ACSR conductor. | 2003-09-05 | 2004-03-01 | 2003-12-19 | 9275000 |  |  |  | 99% | 138kV | 138kV | 25.7 | Single 795, MCM ACSR and 3/8 EHS | Concrete Single Poles | Center-line Defined | 25.7 |  |  | Sub Rule 25.101 (c) (2) (C) (ii) | This line is located in dual certified service area with Taylor Electric CoOp. | 9275000 | 0 | 9275000 |  |  | 9275000 | 0 | 0
24907967 | Crane to McElroy Cut-In 69 kV | Crane and Upton Counties | Construct 1.57 miles of 69 kV from Crane to the McElroy/N. McCamey Cut-In | 2004-05-01 | 2004-06-01 |  | 748326 |  |  |  | 0% |  | 69kV | 1.57 | 795 ACSR | Concrete single pole |  |  | 80' | 1.57 |  | Docket No. 27484 | 748326 | 0 | 748326 |  |  | 748326 | 0 | 0
40078850, 24907989 | Mesa View - Mesa View Switch 138kV Line | Pecos County, TX | Rebuild the existing Mesa View - Mesa View Switch 138kV H-Frame line with single concrete pole construction, double circuit capable, 2-795 ACSR drake conductors (One circuit installed initially) | 2004-01-12 | 2004-03-21 | 2004-03-21 | 2267387 |  |  |  | 99% | 138kV | 138kV | 5.7 | Bundled 795 ACSR | Concrete single pole (double ckt. Capable) | center line | 5.7 |  |  | Exempt per Subst. Rule 25.101(c)(5)(B) | Notice sent to SWTEC and landowners | 2267387 | 0 | 2267387 |  |  | 2267387 | 0 | 0
40079259 24028552 24908016 | Rio Pecos - N McCamey | Crane, Crockett, Upton Counties | Rebuild the existing 138kV H-Frame line with single concrete pole construction, double circuit capable, 2-795 ACSR drake conductors | 2004-03-01 | 2004-05-28 |  | 3932021 |  |  |  | 0% | 138 | 138 | 9.67 | Bundled 795 ACSR | Concrete or steel single pole (double ckt. Capable) | center line | 9.67 |  |  | Exempt per Subst. Rule 25.101(c)(5)(B) | Notice to sent to Upton County Commissioners and landowners | 3932021 | 0 | 3932021 |  |  | 3932021 | 0 | 0
40078866 24028551 24908020 | Rio Pecos - Mesa View 138 | Crockett, Pecos Counties | Rebuild the existing 138kV H-Frame line with single concrete pole construction, double circuit capable, 2-795 ACSR drake conductors | 2004-03-15 | 2004-08-01 |  | 11401500 |  |  |  | 0% | 138 | 138 | 27.13 | Bundled 795 ACSR | Concrete or steel single pole (double ckt. Capable) | center line | 27.13 |  |  | Exempt per Subst. Rule 25.101(c)(5)(B) | Notice sent to SWTEC and landowners | 11401500 | 0 | 11401500 |  |  | 11401500 | 0 | 0
40078884 24028553 24908021 | Mesa View - Ft. Lancaster | Pecos County | Rebuild the existing 138kV H-Frame line with single concrete pole construction, double circuit capable, 2-795 ACSR drake conductors | 2004-08-01 | 2005-01-28 |  | 8342686 |  |  |  | 0% | 138 | 138 | 19.8 | Bundled 795 ACSR | Concrete or steel single pole (double ckt. Capable) | center line | 19.8 |  |  | Exempt per Subst. Rule 25.101(c)(5)(B) | Notice sent to SWTEC and landowners | 8342686 | 0 | 8342686 |  |  | 8342686 | 0 | 0
40079205 | Rio Pecos - Crane Line Extension | Crane County | Extend the existing 138kV H-Frame line with single concrete or steel pole construction, double ckt. capable, 2-795 ACSR drake conductors into LCRA Crane Switching Station | 2003-11-17 | 2003-11-21 | 2003-11-21 | 900000 |  |  |  | 99% | 138 | 138 | 0.5 | Bundled 795 ACSR | Concrete or steel single pole (double ckt. Capable) | center line | 0.07 | center line | 0.5 | Exempt per Subst. Rule 25.101(c)(5)(A) | Notice sent to Oncor and Crane County Airport. Landowner consent. | 900000 | 0 | 900000 |  |  | 900000 | 0 | 0
40289972 | Crane Bus-Tie Extension | Crane County | Extend 138kV line with single concrete pole construction, 795 ACSR drake conductors from AEP Texas North Crane Substation to LCRA Crane Switching Station | 2003-11-17 | 2003-11-21 | 2003-11-21 | 200000 |  |  |  | 99% | 138 | 138 | 0.15 | 795 ACSR | Concrete single pole | center line | 0.07 | center line | 0.15 | Exempt per Subst. Rule 25.101(c)(5)(A) | Notice sent to Oncor and Crane County Airport. Landowner consent. | 200000 | 0 | 200000 |  |  | 200000 | 0 | 0
40162899 | Twin Buttes / Big Lake Cut-in Circuit | Tom Green Coiunty | Buid 9.65 mils of bundled 795 ACSR circuit from Twin Buttes Switching Station to cut-in 138kV line from Big Lake Substation. Circuit will be located on LCRA Transmission Services structures | 2004-04-05 | 2004-07-06 |  | 1041462 |  |  |  | 0% |  | 138 | 9.65 | Bundled 795 ACSR | Concrete or steel single pole (double ckt. Capable) |  |  | center line | 9.65 |  | Docket No. 27180 | 1041462 | 0 | 1041462 |  |  | 1041462 | 0 | 0
23426044 | Big Lake/SAPS Cut-in - SAPS rebuild | Tom Green Coiunty | Reconductor and rebuild approximately 7.33 miles of existing 138kV transmission line. The new line will be single pole structure with 2-795 ACSR conductor. | 2004-04-26 | 2004-08-30 |  | 3801606 |  |  |  | 0% | 138 | 138 | 7.33 | Bundled 795 ACSR | Concrete or steel single pole (double ckt. Capable) | center line | 7.33 |  |  | Exempt per Subst. Rule 25.101(c)(5)(B) | Notice sent to CVEC and landowners | 3801606 | 0 | 3801606 |  |  | 3801606 | 0 | 0
40291171 | TEC - Sharp Interconnection | Taylor County | Install tap structure and switches for new Taylor Electric Substation in the S Abilene to Wylie Sub 138kV line | 2004-05-15 | 2004-06-18 |  | 283000 |  |  |  | 0% | 138 | 138 |  |  |  | center line |  |  |  | Exempt per Subst. Rule 25.101(c)(5)(A) |  | 283000 | 0 | 283000 |  |  | #N/A | #N/A | #N/A
24908014 40288951 40288918 40288943 40288953 | Friend Ranch Substation terminal addition | Crockett County | Add terminal at Friend Ranch for new LCRA Ft. Lancaster to Friend Ranch 138kV line | 2004-09-01 | 2004-12-31 |  | 568000 |  |  |  | 0% | [9 empty] | Pursuant to Subst. Rule 25.83 (a)(3) |  | 568000 | 0 | 568000 |  |  | #N/A | #N/A | #N/A
|  | NEW: | 851000
[23 empty] | Actual Cost of Projects Completed This Month (Will Not Appear on Next Month Report): | Estimated Cost of Projects Completed This Month: | Estimated Cost of Projects Remaining Active This Month: | Total Estimated Cost of Projects Appearing in This Report:
[23 empty] | 0 | 0 | 72603311 | 72603311
[24 empty] | 0 | 19 | 19 | Project Count
[24 empty] | Completed | Active | Total
Note on H1: aboling: Please enter only a single integer, if possible.
Note on I1: aboling: Please enter only a single integer, if possible.
Note on M1: aboling: If applicable.
Note on N1: aboling: If applicable.