## SUMMARY
Revised: | 2007-11-14
MONTHLY ACTIVITY AT A GLANCE
for
AUGUST 2007
TRANSMISSION PROJECTS
A | B | C | D | E | F | G | H | I | J | K | L | M | N | O
UTILITY | TOTAL PROJECTS REPORTED =Utility!AA102 | ESTIMATED COST FOR ALL REPORTED PROJECTS =Utility!AA100 | NEW PROJECTS COUNT THIS MONTH Manual Entry | 1st ESTIMATE COST FOR NEW PROJECTS Manual Entry | COMPLETED PROJECTS COUNT THIS MONTH =Utility!Y102 | COMPLETED PROJECTS (FINAL ACTUAL COSTS) =Utility!X100 | COMPLETED PROJECTS (FINAL ESTIMATED COSTS) =Utility!Y100 | ONGOING PROJECT COUNT = B - F | ONGOING PROJECT COST ESTIMATE (THIS MONTH) = C - H | ONGOING PROJECT COST ESTIMATE (FROM LAST MONTH) Linked or Manual | NET ONGOING PROJECT CHANGE FROM LAST MONTH = J - K | DIFFERENCE: NEW PROJECTS LESS COMPLETED PROJECTS = E - H | CALCULATED COST ADJUSTMENT TO EXISTING PROJECTS = L - M | EXPLANATION OR COMMENT
AEPC | 47 | 303348730 | 2 | 40908269 | 8 | 12643831 | 14719757 | 39 | 288628973 | 262440461 | 26188512 | 26188512 | 0
AEPN | 23 | 74603662 | 3 | 28960066 | 0 | 0 | 0 | 23 | 74603662 | 45643596 | 28960066 | 28960066 | 0
BEPC | 19 | 105086950 | 3 | 9100000 | 0 | 0 | 0 | 19 | 105086950 | 95986950 | 9100000 | 9100000 | 0
CNP | 17 | 181241000 | 0 | 0 | 4 | 6830801.37 | 6699000 | 13 | 174542000 | 180933000 | -6391000 | -6699000 | 308000 | Cost Rev 1 Project
DSEC | 2 | 5095000 | 0 | 0 | 0 | 0 | 0 | 2 | 5095000 | 5095000 | 0 | 0 | 0
EGSI | 5 | 42781475 | 0 | 0 | 1 | 8749000 | 11066747 | 4 | 31714728 | 42781475 | -11066747 | -11066747 | 0
EPE | 6 | 15379727 | 0 | 0 | 0 | 0 | 0 | 6 | 15379727 | 15379727 | 0 | 0 | 0
FEC | 2 | 4721500 | 0 | 0 | 0 | 0 | 0 | 2 | 4721500 | 4721500 | 0 | 0 | 0
LCRA | 17 | 246676511 | 1 | 7830000 | 0 | 0 | 0 | 17 | 246676511 | 238846511 | 7830000 | 7830000 | 0
MVEC | 7 | 16984500 | 0 | 0 | 0 | 0 | 0 | 7 | 16984500 | 16984500 | 0 | 0 | 0
LEA E.C. |  |  | 0 | 0
PEC | 2 | 6835000 | 0 | 0 | 0 | 0 | 0 | 2 | 6835000 | 6835000 | 0 | 0 | 0
SHECO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPS | 2 | 15612395 | 0 | 0 | 0 | 0 | 0 | 2 | 15612395 | 15612395 | 0 | 0 | 0
STEC | 11 | 68503412 | 1 | 1640000 | 0 | 0 | 0 | 11 | 68503412 | 67323412 | 1180000 | 1640000 | -460000 | Cost Rev 1 Project
SULP | 1 | 39000000 | 0 | 0 | 0 | 0 | 0 | 1 | 39000000 | 39000000 | 0 | 0 | 0
SWEPCO | 2 | 21088565 | 1 | 3344000 | 0 | 0 | 0 | 2 | 21088565 | 17744565 | 3344000 | 3344000 | 0
TNMP | 2 | 4122000 | 0 | 0 | 0 | 0 | 0 | 2 | 4122000 | 4122000 | 0 | 0 | 0
TVEC | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TXU | 109 | 250953914.25 | 12 | 4935131 | 0 | 0 | 0 | 109 | 250953914.25 | 246018783 | 4935131.25 | 4935131 | 0.25 |  |  | 0 | (From TXU Sheet)
UPSHUR | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WCEC | 2 | 5140000 | 0 | 0 | 0 | 0 | 0 | 2 | 5140000 | 5140000 | 0 | 0 | 0 |  | Less: | 0.25 | (From Calc Cost Adj)
NEW | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEW2 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEW3 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NEW4 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[15 empty] | = | -0.25 | (Difference)
TOTAL | 276 | 1407174341.25 | 23 | 96717466 | 13 | 28223632.37 | 32485504 | 263 | 1374688837.25 | 1310608875 | 64079962.25 | 64231962 | -151999.75
|  | Ongoing Project Count Check: | 263 | Correct |  |  | LAST MONTH ONGOING COUNT: | 253
Note on A11: aboling: FORMERLY CPL.
Note on A12: aboling: FORMERLY WTU
Note on A14: aboling: FORMERLY CPE.
Note on A18: Allen Steven Boling: Farmer's Electric Cooperative AKA Concho Valley EC. CVEC
Note on A26: aboling: SHARYLAND UTILITIES
Note on A30: aboling: "Oncor" changed to TXU Electric Delivery Company.
Note on A32: Allen Steven Boling: Wood County Electric Cooperative
Note on F10: aboling: A COMPLETE PROJECT IS DEFINED AS ONE FOR WHICH THE CONSTRUCTION IS COMPLETE AND THE FINAL ACTUAL PROJECT COST HAS BEEN ENTERED.
Note on I10: aboling: ACTIVE PROJECTS INCLUDE NEW PROJECTS BUT NOT COMPLETED PROJECTS.

## AEPC
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost (Total) | Final Estimated Project Cost (Total) | Final Actual Project Cost (Total) | % Variance | Percent Complete | Existing Voltage | Upgraded or New Voltage | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS | Estimated OR Actual Project Cost (SUBSTATION) |  | Last Month: | Current minus last month: | Cumulative Sum
22169662 | Falcon-Lopeno 138 kV Line Reconductor | Starr & Zapata Counties, Texas | Reconductor and rebuild approximately 10 miles of existing 138kV transmission line from Falcon Substation to Lopeno Substation. The old line is 336.4 MCM Aluminum conductor on wood H frame structures and will be reconductored with 795 MCM ACSR conductors on steel poles. | 2001-12-15 | 2002-02-15 | 2002-02-21 |  | 2140875 |  |  | 100 | 138 | 138 | 10 | 795 MCM ACSR & 7#8 Alumoweld | Steel Single Poles | Ceterline Defined | 10 |  |  | Sub Rule 25.101 (c) (2) (C) (ii) | The line is located in MEC single certified service area. | 2140875 | 0 | 2140875 |  |  | 2140875 | 0 | 0
22169585 | Garza- Falcon 138 kV Line Reconductor | Starr County, Texas | Reconductor and rebuild approximately 27.3 miles of existing 138kV transmission line from Garza Substation to Falcon Substation. The old line is 336 MCM Aluminum conductor on wood H frame structures and will be reconductored with 795 MCM aluminum conductor on steel poles. | 2002-03-10 | 2002-10-10 | 2002-10-10 |  | 5577000 |  |  | 100 | 138 | 138 | 27.3 | 795 MCM & 7#8 Alumoweld Static | Steel Single Poles | Ceterline Defined | 27.3 |  |  | Sub Rule 25.101 (c) (2) (C) (ii) | This line is located in MEC (Medina Electric Coop) single certified service area. | 5577000 | 0 | 5577000 |  |  | 5577000 | 0 | 0
22169764 | Lopeno-Zapata 138 kV Line Reconductor | Zapata County, Texas | Reconductor and rebuild approximately 20.3 miles of existing 138kV transmission line from Zapata Substation to Lopeno Substation. The old line is 336.4 MCM Aluminum conductor on wood H frame structures and will be reconductored with 795 MCM ACSR conductors on steel poles. | 2002-02-22 | 2003-01-30 | 2003-02-01 |  | 4168000 |  |  | 100 | 138 | 138 | 20.3 | 795 MCM ACSR & 7#8 Alumoweld | Steel Single Poles | Ceterline Defined | 20.3 |  |  | Sub Rule 25.101 (c) (2) (C) (ii) | The line is located in MEC single certified service area. | 4168000 | 0 | 4168000 |  |  | 4168000 | 0 | 0
22169796 | Rio Bravo-Zapata 138 kV Line Reconductor | Zapata & Webb Counties, Texas | Reconductor and rebuild approximately 30.8 miles of existing 138kV transmission line from Zapata Substation to Rio Bravo Substation. The old line is 336.4 MCM Aluminum conductor on wood H frame structures and will be reconductored with 795 MCM ACSR conductors on steel poles. | 2002-05-15 | 2003-04-15 | 2003-05-15 |  | 6308000 |  |  | 100 | 138 | 138 | 30.8 | 795 MCM ACSR & 7#8 Alumoweld | Steel Single Poles | Ceterline Defined | 30.8 |  |  | Sub Rule 25.101 (c) (2) (C) (ii) | The line is located in MEC single certified & TCC single certified service areas. | 6308000 | 0 | 6308000 |  |  | 6308000 | 0 | 0
22169830 | Wormser-Rio Bravo 138kV Reconductor | Webb County, Texas | Reconductor and rebuild approximately 9.6 miles of existing 138kV transmission line from Rio Bravo Substation to Wormser Substation. The old line is 336.4 MCM Aluminum conductor on wood H frame structures and will be reconductored with 795 MCM ACSR conductors on steel poles. | 2002-06-15 | 2003-05-15 | 2003-11-19 |  | 2201000 |  |  | 100 | 138 | 138 | 9.6 | 795 MCM ACSR & 7#8 Alumoweld | Steel Single Poles | Center line Defined | 29.6 |  |  | Sub Rule 25.101 (c) (2) (C) (ii) | The line is located in MEC single certified & TCC single certified service areas. | 2201000 | 0 | 2201000 |  |  | 2201000 | 0 | 0
40015548 | Hidalgo - Southeast Edinburg 6.3 mile 138kv transmission line reconductor | Hidalgo County, Texas | Reconductor the approximately 6.3 miles of existing 138kv from Hidalgo to Southeast Edinburg. The old line is 795 ACSR conductor and the new line will be 795 ACSS conductor. Poles will remain the same. | 2003-02-10 | 2003-12-12 |  |  | 1446315 | 1300000 | -10.12% | 100 | 138 | 138 | 6.3 | Drake 795 MCM ACSS | Wood Single Poles | Centerline Defined | 6.3 |  |  | Sub Rule 25.101 (c) (5) (B) | The line is located in TCC single certified and in TCC / MVEC (Magic Valley) dual certified areas. | 1446315 | 1446315 | 0 |  |  | 1446315 | 0 | 0
AE007181 | South Mission - South McAllen 69kv to 138kv transmission line rebuild | Hidalgo County, Texas | Rebuild the existing South Mission to South McAllen 69kv transmission line to a 138kv single circuit, double circuit capable, 6 mile line using bundled 1590 MCM ACSS on steel or concrete single pole structures | 2004-06-01 | 2004-12-01 |  |  | 2916000 | 1700000 | -41.7% | 100 | 69 | 138 | 6 | 1590 MCM ACSS | Concrete or steel single pole | Centerline Defined | 6 |  |  | Sub Rule 25.101 (c) (5) (B) | The line is located in TCC single certified and in MVEC (Magic Valley) single certified areas | 2916000 | 2916000 | 0 |  |  | 2916000 | 0 | 0
AE007171 | Bates - South Mission 69kv to 138kv line rebuild and termination relocation | Hidalgo County, Texas | Rebuild the existing 4.18 mile 69kv Bates to South Mission transmission line to a 138kv line using 1590 MCM ACSS on steel or concrete single pole structures, and relocate the West end of the line termination point from Bates 500' to the south to the Frontera switching station | 2004-06-01 | 2004-12-01 |  |  | 2127000 | 1800000 | -15.37% | 100 | 69 | 138 | 4.18 | 1590 MCM ACSS | Concrete or steel single pole | Centerline Defined | 4.18 |  |  | Sub Rule 25.101 (c) (5) (B) | The line is located in TCC single certified areas | 2127000 | 2127000 | 0 |  |  | 2127000 | 0 | 0
4024691301 | McColl - North McAllen 6.8 mile 138kv transmission line reconductor | Hidalgo County, Texas | Reconductor the approximately 6.8 miles of existing 138kv and convert the existing 69kv to 138kv which will result in a double circuit 138kv from McColl to North McAllen. The old line is 795 ACSR conductor and the new line will be 795 ACSS conductor. Poles will remain the same. | 2004-11-20 | 2004-12-31 |  |  | 1914000 | 1925547 | 0.6033% | 100 | 138 and 69 | 138 both circuits | 6.8 | Drake 795 MCM ACSS | Wood Single Poles | Centerline Defined | 6.8 |  |  | Sub Rule 25.101 (c) (5) (B) | The line is located in TCC single certified area. | 1914000 | 1914000 | 0 |  |  | 1914000 | 0 | 0
4024696001 | Polk - Hall Acres 2.73 mile 138-kV transmission line rebuild and reconductor | Hidalgo County, Texas | Reuild and reconductor the approximately 2.73 miles of existing 138-kV from Polk Ave. to Hall Acres. The old conductor is 336 ACSR and the new conductor will be 795 ACSS. Wood structures will be replaced with steel structures. | 2004-09-15 | 2004-12-15 |  |  | 1352003 | 1084855 | -19.76% | 100 | 138 |  | 2.73 | Drake 795 MCM ACSS | Steel single pole | Centerline Defined | 2.73 |  |  | Sub Rule 25.101 (c) (5) (B) | The line is located in AEP-TCC single certified and in AEP-TCC / MVEC dual certified territory | 1352003 | 1352003 | 0 |  |  | 1352003 | 0 | 0
40389465 | N McAllen - W. McAllen 138kV at FM 2220 | Hidalgo County, Texas | Relocate 16 structures for road improvement | 2004-07-15 | 2004-10-01 |  |  | 418000 |  |  | 5 | 138 |  | 0.76 | 795 AAC 37 strand | Steel pole | Cenerline Defined | 0.76 |  |  | Sub Rule 25.101 (c) (5) (F) | Relocation located in public Right-Of-Way acquired by TXDot | 418000 | 0 | 418000 |  |  | 418000 | 0 | 0
40246954 | Magic Valley Pharr - Pharr 3.57 mile 138-kV transmission line reconductor and upgrade | Hidalgo County, Texas | Reconductor the approximately 3.57 miles of existing 138kv from Magic Valley Pharr to North Pharr. The old line is 795 ACSR conductor and the new line will be 795 ACSS conductor. Most of the poles will remain the same. | 2005-03-24 | 2005-04-27 |  |  | 721169 | 729312 | 1.129% | 100 |  |  | 3.57 | Drake 795 MCM ACSS | Wood Single Poles | Centerline Defined | 3.57 |  |  | Sub. Rule 25.101(c)(5)(B) | The line is located in TCC single certified and in TCC / MVEC (Magic Valley) dual certified areas | 721169 | 721169 | 0 |  |  | 721169 | 0 | 0
40419748 | Rio Hondo to La Palma 138kV Rebuild | Cameron County, Texas | Rebuild approximately 10.1 miles of existing wood H-frame 138kV line. The old line is single 795 ACSR 27/7. The new line will be bundled 795 ACSS with OPGW on new steel single pole structures. | 2005-08-15 | 2005-12-31 | 2005-12-16 |  | 16510075 |  |  | 99 | 138 | 138 | 10.1 | Bundled 795 ACSS | Steel single pole | Centerline Defined | 10.1 |  |  | Pursuant to Subst. Rule 25.101 (c)(5) (B) |  | 16510075 | 0 | 16510075 |  |  | 16510075 | 0 | 0
40246959 | Pharr - Polk 3.56 mile 138kv transmission line reconductor | Hidalgo County, Texas | Reconductor the approximately 3.56 miles of existing 138kv from Pharr to Polk. The old line is 795 ACSR conductor and the new line will be 795 ACSS conductor. Most of the poles will remain the same. | 2005-09-15 | 2005-11-15 |  |  | 724259 | 704117 | -2.781% | 100 | 138 | 138 | 3.56 | Drake 795 MCM ACSS | Wood Single Poles | Centerline Defined | 3.56 |  |  | Sub Rule 25.101 (c) (5) (B) | The line is located in TCC single certified area | 724259 | 724259 | 0 |  |  | 724259 | 0 | 0
40213325 | Airline / Laguna 69 kV Line - Rebuild Line | Corpus Christi, Nueces | Reconductor and rebuild approximately 6.4 miles of existing 69 kV transmission line from Airline Substation to Laguna Substation. The old line is 477 MCM ACSR on wooden H frame structures and will be reconductored with 795 MCM ACSR conductor on steel poles. | 2005-10-24 | 2007-06-01 |  |  | 4799103 |  |  |  | 69 | 69 | 6.4 | 795 ACSR | Steel Monopole | Centerline Defined (50%), Varied width of 15 ft - 45 ft (50%) | 6.4 |  |  | Sub Rule 25.101 (c)(5)(B) | Has section of line that crosses Oso Bay | 4799103 | 0 | 4799103 |  |  | 4799103 | 0 | 0
40213354 | Airline / Naval Base 69 kV Line - Rebuild Line | Corpus Christi, Nueces | Reconductor and rebuild approximately 7.96 miles of existing 69 kV transmission line from Airline Substation to Naval Base Substation. The old line is 477 MCM ACSR on wooden H frame structures and will be reconductored with 795 MCM ACSR conductor on steel poles. | 2005-11-21 | 2007-06-01 |  |  | 5950992 |  |  |  | 69 | 69 | 7.96 | 795 ACSR | Steel Monopole | Centerline Defined (75%), Varied width of 12 ft - 45 ft (25%) | 7.96 |  |  | Sub Rule 25.101 (c)(5)(B) | Has section of line that crosses Oso Bay | 5950992 | 0 | 5950992 |  |  | 5950992 | 0 | 0
4020427101 | North Weslaco - North Mercedes 69kv to 138kv transmission line rebuild | Hidalgo County, Texas | Rebuild the approximately 4.9 miles of existing 69kv and convert to 138kv The old line is 4/0 ACSR conductor and the new line will be 795 ACSS conductor. | 2/30/06 | 2006-08-15 |  |  | 3519011 | 3400000 | -3.382% | 100 | 69 | 138 | 4.9 | Drake 795 MCM ACSS | Concrete or steel single pole | Centerline Defined | 4.9 |  |  | Sub Rule 25.101 (c) (5) (B) | The line is located in TCC single and MVEC (Magic Valley) single certified and in TCC / MVEC dual certified areas | 3519011 | 3519011 | 0 |  |  | 3519011 | 0 | 0
25188819 | Uvalde-Hamilton Road Rebuild | Uvalde, Kinney, Val Verde | Rebuild 67.6 miles of the Uvalde-Hamilton Road transmission line | 2006-01-30 | 2007-05-14 |  |  | 34348277 |  |  | 99 | 138 | 138 | 67.6 | 795 ACSS | single steel pole | 50 minimum or undefined | 67.6 | 50 minimum or undefined |  | Sub.Rule 25.101(c)(5)(B) | The line is located in TCC and Rio Grande Electric Cooperatuve (RGEC) single certificated territories | 34348277 | 0 | 34348277 |  |  | 34348277 | 0 | 0
40616479 | Mustang/Port Aransas 69kV line (Flato Property) - reroute line | Nueces | Reroute 2.6 miles of 69kV line next to Highway 361 (Existing Easement Encroachment) | 2006-02-01 | 2007-05-01 |  |  | 3334427 |  |  | 100 | 69 | 69 | 2.6 | 795 MCM ACSS | Steel monopile | 60' | 2 | 60 | 2.6 | Sub. Rule 25.101 (c)(5)(E) | New ROW provided by landowner. | 3334427 | 0 | 3334427 |  |  | 3334427 | 0 | 0
40601028 | ExxonMobil KRGP 138 kV Hairpin | Kleberg | 138 kV Hairpin of the Falfurrias-Lon Hill transmission line into the ExxonMobil KRGP substation | 2006-01-31 | 2006-04-01 |  |  | 593000 |  |  | 100 | 138 |  | 0.19 | 795 ACSR | single steel pole |  |  | 80 for each circuit of hairpin | 0.19 | Sub.Rule 25.101(c)(5)(A) | Consent provided | 593000 | 0 | 593000 |  |  | 593000 | 0 | 0
40654675 | Wormser to Sierra Vista 138 kV | Webb | Construct approximately 2.7 miles of 138kV transmission line using 795 kcmil ACSR on pre-stressed concrete or steel single pole structures | 2006-10-09 | 2007-04-26 |  | 3241000 |  |  |  | 100 |  |  | 2.7 | 795 kcmil ACSR 26/7 | Centerline |  |  | 100 | 2.7 | 32172 | Line is located in TCC singly certificated territory | 3241000 | 0 | 3241000 |  |  | 3241000 | 0 | 0
40737207 | Laredo Plant to Zacate to Heights 69 kV to 138 kV Conversion | Laredo, Webb | Conversion of the existing 69 kV transmission line to 138 kV operation requiring some change out of insulators and some pole change outs. | 2006-07-17 | 2006-12-31 |  |  | 948200 |  |  |  | 69 | 138 | 8.4 | (1) 795,000 cm AAC 19 Comp | Double ckt. steel and Wood single pole | Centerline Defined | 4.2 | 30 | 0.08 | Sub.Rule 25.101(c)(5)(B) | Double Circuit Line with one side remaining 69kV and the other side converted to 138kV | 948200 | 0 | 948200 |  |  | 948200 | 0 | 0
4073529401 | Dupont SS Victoria / Gohlke 138 kV Line - Tie in Chocolate Bayou Substation | Victoria | 138 kV Double Circuit Hairpin from the Dupont SS Victoria / Gohlke Line to the Chocolate Bayou Substation | 2006-08-07 | 2006-12-15 |  |  | 1279500 |  |  | 100 | 138 | 138 | 0.34 | 795 MCM ACSR | Steel Pole |  |  | 80 | 0.17 | Sub.Rule 25.101(c)(5)(A) | Consent and easements obtained | 1279500 | 0 | 1279500 |  |  | 1279500 | 0 | 0
40787097 | Milo Substation-Laredo 138kV Line (North Laredo to Laredo Plant 138kV Tie to Laredo VFT Station) | Laredo, Webb | Cut in 300 ft tap to Laredo VFT Station and rebuild replace (6) existing spans into Laredo Station with direct embed steel poles and 2 bundle 795,000cm ACSR Conductor | 2006-09-28 | 2006-12-31 |  |  | 579000 |  |  |  | 138 | 138 | 0.52 | (2) 795,000 cm Drake ACSR | Single Circuit Steel Pole | Centerline Defined |  |  |  | Sub.Rules 25.101(c)(5) (A) and (B) | This line Section is located entirely on AEP TCC Property | 579000 | 0 | 579000 |  |  | 579000 | 0 | 0
40787138 | Bruni-Laredo 138kV Line (Falfurrias to Laredo Tie to Laredo VFT Station) | Laredo, Webb | Cut in 500 ft tap to Laredo VFT Station and rebuild replace (4) existing spans into Laredo Station with direct embed steel poles and 2 bundle 795,000cm ACSR Conductor | 2006-09-28 | 2006-12-31 |  |  | 463000 |  |  |  | 138 | 138 | 0.55 | (2) 795,000 cm Drake ACSR | Single Circuit Steel Pole | Centerline Defined |  |  |  | Sub.Rules 25.101(c)(5) (A) and (B) | This line Section is located entirely on AEP TCC Property | 463000 | 0 | 463000 |  |  | 463000 | 0 | 0
40722975 | Laredo VFT-Nuevo Laredo CFE 230kV Line | Laredo, Webb | Conversion of (4) spans of the existing Laredo - Nuevo Laredo CFE 138kV transmission line to double circuit 230kV/138kV operation utilizing (2) bundle 795,000cm ACSS condutor and a new 300 ft termination into Laredo VFT Station. | 2006-09-28 | 2006-12-31 |  |  | 1131000 |  |  |  | 138 | 230 | 0.76 | (2) 795,000 cm Drake ACSS | Double Circuit Steel Pole | 120' |  |  |  | Sub.Rule 25.101(c)(5) (A), (B), and (C) | Rebuild is completely on existing powerplant easement. | 1131000 | 0 | 1131000 |  |  | 1131000 | 0 | 0
40806045 | Laredo-Nuevo Laredo CFE 138kV Line | Laredo, Webb | Rebuild and Replacement of (3) spans of the existing Laredo - Nuevo Laredo CFE 138kV with 795,000cm ACSR and a new 350 ft termination into Laredo VFT Station. | 2006-09-28 | 2006-12-31 |  |  | 311000 |  |  |  | 138 | 138 | 0.24 | (1) 795,000 cm Drake ACSR | Single Circuit Steel Pole | Centerline Defined |  |  |  | Sub.Rule 25.101(c)(5) (A) and (B) | Rebuild is completely on existing powerplant easement. | 311000 | 0 | 311000 |  |  | 311000 | 0 | 0
40737194a | Laredo Anna Street to Laredo Heights 69 kV to 138 kV Conversion | Laredo, Webb | Existing 69 kV single pole double circuit line is insulated for 138 kV operation. One circuit will be converted to 138 kV operation. Some substation work required. | 12/15//06 | 2006-12-31 |  |  | 200000 |  |  |  | 69 | 138 | 1.94 | (1) 795,000 cm AAC 19 Comp | Double ckt. steel and Wood single pole | Centerline Defined | 1.94 |  |  | Sub.Rule 25.101(c)(5)(B) | Double Circuit Line with one side remaining 69kV and the other side converted to 138kV | 200000 | 0 | 200000 |  |  | 200000 | 0 | 0
40636851a | Relocation of a section of the Whitepoint to Dupont 138 kV Line | Nueces | Relocation request results in 0.56 miles of new construction to the Whitepoint to Dupont 138 kV line. Requestor provided funding and easement. | 2006-10-13 | 2007-09-10 |  |  | 665200 |  |  |  | 138 | 138 | 0.56 | 795,000 ACSR | Double ckt. steel |  |  | 80 | 1.12 | Sub.Rule 25.101(c)(5)(D) | Requestor is providing funding and has provided the easement. | 665200 | 0 | 665200 |  |  | 665200 | 0 | 0
40636851 | Whitepoint to Dupont 138 kV Line cut-in to Cargo Substation | Nueces | Construct new 0.9 mile cut-in to new Cargo Substation from the Whitepoint to Dupont 138 kV line. | 2006-10-13 | 2007-10-15 |  |  | 795400 |  |  |  |  | 138 | 0.9 | 795,000 ACSR | Double ckt. Steel |  |  | 80 | 1.8 | Sub.Rule 25.101(c)(5)(A) | Consent and easements obtained | 795400 | 0 | 795400 |  |  | 795400 | 0 | 0
40487094 | San Miguel to Laredo Lobo 345 kV | Atascosa, La Salle, McMullen, Webb | Construct a new 345 kv line from San Miguel to a new Lobo Switching Station near Laredo, Texas | 2007-02-01 | 2010-04-30 |  | 72023400 | [5 empty] | 345 | 102-106 | 2-1590 kcmil ACSR | Double ckt. Capable Steel Monoploe |  |  | 150 | 102-106 | 33033 | Filed CCN on 9/12/2006. Joint line with STEC who has 40% of line cost. CNN approved 6/13/07 | 72023400 | 0 | 72023400 |  |  | 72023400 | 0 | 0
40779294 | Stewart Road 69/138 kV Double Circuit | Hidalgo | Construct approximately 2 miles of 69/138kV double circuit transmission line from new Stewart Road Switching Station to existing S. McAllen to La Palma 69 kV line | 2007-08-15 | 2007-12-15 |  | 2394000 |  |  |  | 100 |  | 69/138 | 4 | 795 kcmil ACSS 26/7 | Concrete or steel single pole |  |  | 100 | 2 | 32857 | Filed CCN on 9/12/2006. Approved on December 5, 2006. | 2394000 | 0 | 2394000 |  |  | 2394000 | 0 | 0
4021289001 | Flato Property / Port Aransas 69 kV Line Rebuild | Port Aransas, Texas | Rebuild line from 4/0 to 795 MCM ACSS | 2006-11-20 | 2007-03-06 |  |  | 4500000 |  |  | 99 | 69 | 69 | 3.3 | 795 MCM ACSR | Steel Pole w/ concrete Butt Sections | Undefined Hwy Right of Way | 3.3 |  |  | Subst. Rule 25.101 (c)(5)(B) | Remains in Hwy Right of Way | 4500000 | 0 | 4500000 |  |  | 4500000 | 0 | 0
4049003701 | Laredo Variable Frequency Transformer (VFT) Station | Webb County, Laredo Texas | Construction of VFT Station allowing Asyncronous Connection for 100 MW transfer with CFE | 2005-11-20 | 2007-02-15 |  |  | 55000000 | [12 empty] | Pursuant to Subst. Rule 25.83(a)(3) |  | 55000000 | 0 | 55000000 |  |  | 55000000 | 0 | 0
4058727201 | City of Robstown to Robstown Tap Rebuild and Reconductor | Nueces, County Robstown, Texas | Rebuild and reconductor of 69 kV line from City of Robstown Utility Sub to Lon Hill to Robstown Subtation Tap (capable of 138 kV operation) | 2005-11-24 | 2007-01-08 |  |  | 956563 |  |  | 100 | 69 |  | 0.82 | 795 ACSR | Single Pole Concrete or Steel | Centerline | 0.82 |  |  | Subst. Rule 25.101(c)(5)(B) |  | 956563 | 0 | 956563 |  |  | 956563 | 0 | 0
4061647901 | Naval Base to N. Padre Tap OPGW Installation | Nueces, County | Addition of OPGW to the Naval Base to N. Padre Tap Transmission line | 2006-10-23 | 2006-12-08 |  |  | 1053781 |  |  | 100 | [9 empty] | Pursuant to Subst. Rule 25.83(a)(3) |  | 1053781 | 0 | 1053781 |  |  | 1053781 | 0 | 0
40737194 | Laredo Plant to Anna Street 69 kV to 138 kV Conversion | Webb County, Texas | Conversion of the existing 69 kV transmission line circuit to 138 kV operation requiring change out of insulators and installation of some structures. | 2007-01-22 | 2007-02-07 |  |  | 686500 |  |  |  | 69 | 138 | 3.1 | (1) 795,000 cm AAC 19 Comp | Double ckt. steel and wood single pole | Centerline Defined | 3.1 |  |  | Sub.Rule 25.101(c)(5)(B) | Double Circuit Line with one side remaining 69kV and the other side converted to 138kV | 686500 | 0 | 686500 |  |  | 686500 | 0 | 0
40737194a | Laredo Plant to Anna Street OPGW Installation | Webb County, Texas | Addition of OPGW to the Laredo Plant to Anna Street Transmission line | 2007-01-22 | 2007-02-07 |  |  | 325565 | [12 empty] | Pursuant to Subst. Rule 25.83(a)(3) |  | 325565 | 0 | 325565 |  |  | 200000 | 125565 | 125565
40780619 | MidValley 69kV to 138kV Conversion | Hidalgo County, Texas | Loop S. McAllen to Weslaco 138 kV line into new Stewart Road Substation with 795 ACSS and OPGW wire | 2007-04-19 | 2007-09-01 |  |  | 650000 |  |  | 20 | 138 | 138 | 0.8 | 795 kcmil ACSS 26/7 | Concrete or steel single pole | - | - | 100 | 0.4 | Sub.Rule 25.101(c)(5)(A) | Consent and easements obtained from landowner | 650000 | 0 | 650000 |  |  | 650000 | 0 | 125565
40780707 | MidValley 69kV to 138kV Conversion | Hidalgo County, Texas | Convert Stewart Rd Tap to MVEC Hi-Line with 795 ACSS and OPGW from 69 kV to 138 kV | 2007-08-01 | 2007-12-31 |  |  | 1886980 |  |  |  | 69 | 138 | 3.2 | 795 kcmil ACSS 26/7 | Concrete or steel single pole | Centerline Defined |  |  |  | Sub.Rule 25.101(c)(5)(B) | The line is located in TCC single certified and in TCC / MVEC (Magic Valley) dual certified areas | 1886980 | 0 | 1886980 |  |  | 1886980 | 0 | 125565
40780682 | MidValley 69kV to 138kV Conversion | Hidalgo County, Texas | Convert MVEC Hi-Line to Hidalgo with 795 ACSS and OPGW from 69 kV to 138 kV | 2007-11-01 | 2008-02-28 |  |  | 1741830 |  |  |  | 69 | 138 | 2.9 | 795 kcmil ACSS 26/7 | Concrete or steel single pole | Centerline Defined |  |  |  | Sub.Rule 25.101(c)(5)(B) | The line is located in TCC single certified and in TCC / MVEC (Magic Valley) dual certified areas | 1741830 | 0 | 1741830 |  |  | 1741830 | 0 | 125565
40780719 | MidValley 69kV to 138kV Conversion | Hidalgo County, Texas | Convert South McAllen to Hidalgo 69 kV to 138 kV with 795 and 1590 ACSS - with OPGW | 2008-01-01 | 2008-05-31 |  |  | 2623212 |  |  |  | 69 | 138 | 3.8 | 795 kcmil ACSS 26/7 | Concrete or steel single pole | Centerline Defined |  |  |  | Sub.Rule 25.101(c)(5)(B) | The line is located in TCC single certified and in TCC / MVEC (Magic Valley) dual certified areas | 2623212 | 0 | 2623212 |  |  | 2623212 | 0 | 125565
40449031 | Tap from N. Edinburg-Palmview 138kV Line to Palmhurst Sub | Hidalgo County | Rebuild approximately 1.7 miles of existing 69kV Bates to Palmhurst transmission line and convert to 138kV and tap into existing Edinburg to Palmview 138 kV line. Retire remaining 69 kV line to Bates. | 2007-04-24 | 2007-05-23 |  |  | 1390000 |  |  | 5 | 69 | 138 | 1.7 | 1272 MCM ACSR | Steel Single Poles | Ceterline Defined | 1.7 |  |  | Sub. Rule 25.101(c) 5 (B) and 25.101(c) 5 (E) | The line is located in AEP TCC single and MVEC (Magic Valley) single certified areas. Some line movement to address encroachments (consent obtained) | 1390000 | 0 | 1390000 |  |  | 1390000 | 0 | 125565
40212890 | Flato Property / Mustang Island 69 kV Line Rebuild | Nueces County, City of Corpus Christi and Port Aransas, Texas | Rebuild and partially relocate 69 kV Line. Reconductor from 4/0 to 795 MCM ACSS. | 2007-05-14 | 2007-06-15 |  |  | 3266153 |  |  | 98 | 69 | 69 | 3.33 | 795 MCM ACSS | Steel Monopile w/ Concrete Pole | 60 | 3.33 | 60 | 2.1 | Pursuant to Subst. Rule 25.101 (c)(5) (B) | Portions of line will be relocated adjacent to SH 381 with landowner consent. | 3266153 | 0 | 3266153 |  |  | 3266153 | 0 | 125565
40212890a | Mustang Island/N. Padre Tap 69 kV Line Rebuild | Nueces County, City of Corpus Christi | Rebuild and relocate 69 kV Line. Reconductor from 4/0 to 795 MCM ACSS. | 2007-06-11 | 2007-07-15 |  |  | 3260671 |  |  | 5 | 69 | 69 | 3.42 | 795 MCM ACSS | Steel Monopile w/ Concrete Pole | 60 | 3.42 | 60 | 3.42 | Pursuant to Subst. Rule 25.101 (c)(5) (B) | Landowner Consent Obtained | 3260671 | 0 | 3260671 |  |  | 3260671 | 0 | 125565
40638212 | El Gato to Goolie 138 kV | Hidalgo County | Construct approximatly 5 miles of 138 kV line on pre-stressed concrete or steel structures, with a portion of the line double circuit capable. | 2008-10-13 | 2009-05-08 |  | 5346624 |  |  |  | 0 |  | 138 | 5 | 795 MCM ACSS | Pre-stressed concrete or steel single pole |  |  | 100 | 5 | 34050 | CCN filed on June 25, 2007. | 5346624 | 0 | 5346624 |  |  | #N/A | #N/A | #N/A
40903730 | Kenedy Ranch 345 kV | Kenedy County | Construct approximatly 22 miles of 345 kV line on single pole steel structures, double circuit capable. | 2007-11-19 | 2008-09-01 |  | 35561645 |  |  |  | 0 |  | 345 | 22 | 2-1590 kcmil ACSR | Steel single pole |  |  | 150 | 22 | 34298 | CCN filed on June 25, 2007. | 35561645 | 0 | 35561645
40908269
|  | 120039000 | 72023400 | Staff note: $72,023,400 is AEPC portion of AEPC/STEC project.
|  | Total | AEPC 60%
[23 empty] | Actual Cost of Projects Completed This Month (Will Not Appear on Next Month Report): | Estimated Cost of Projects Completed This Month: | Estimated Cost of Projects Remaining Active This Month: | Total Estimated Cost of Projects Appearing in This Report:
[23 empty] | 12643831 | 14719757 | 288628973 | 303348730
[24 empty] | 8 | 39 | 47 | Project Count
[24 empty] | Completed | Active | Total
Note on H1: aboling: Please enter only a single integer, if possible.
Note on H32: Allen Steven Boling: T-Line: $102,236,000; Station: $17,713,000. TOTAL: $121,749,000. AEPN - 60% ($72,023,000) STEC - 40% ($48,015,600)
Note on H47: Allen Steven Boling: Line: 5,346,624 Station: 2,594,468
Note on H48: Allen Steven Boling: Line: 35,561,645 Station: 2,594,469
Note on I1: aboling: Please enter only a single integer, if possible.
Note on M1: aboling: If applicable.
Note on N1: aboling: If applicable.

## AEPN
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost | Final Estimated Project Cost | Final Actual Project Cost | % Variance | Percent Complete | Existing Voltage | Upgraded or New Voltage | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS | Estimated OR Actual Project Cost (SUBSTATION) |  | Last Month: | Current minus last month: | Cumulative Sum
40385791 | Munday - Throckmorton | Knox County | One portion of the work required to relocate approximately 40 structures near Munday, TX impacted by the relocation of a section of US 277 | 2004-12-06 | 2005-01-31 | 1/14/085 |  | 490000 |  |  | 99 | 69 |  | 0.424 | 4/0 ACSR 6/1 | single pole, single and double ckt, concrete | center line | 0.424 | 60 | 0.424 | 25.101(c)(5)(F) | 100% consent obtained | 490000 | 0 | 490000 |  |  | 490000 | 0 | 0
40385795 | Munday - Haskell | Knox County | One portion of the work required to relocate approximately 40 structures near Munday, TX impacted by the relocation of a section of US 277 | 2004-12-06 | 2005-01-31 | 2005-01-14 |  | Included in above |  |  | 99 | 69 |  | 0.424 | 4/0 ACSR 6/1 | single pole, single and double ckt, concrete | center line | 0.424 | 60 | 0.424 | 25.101(c)(5)(F) | 100% consent obtained | Included in above | 0 | Included in above
40385983 | East Munday - Munday | Knox County | One portion of the work required to relocate approximately 40 structures near Munday, TX impacted by the relocation of a section of US 277 | 2005-01-06 | 2005-01-31 |  |  | 566000 |  |  | 99 | 138 |  | 0.18 | 795 ACSR 26/7 | concrete, 3 pole, double circuit | center line | 0.18 | 60 | 0.18 | 25.101(c)(5)(F) | 100% consent obtained | 566000 | 0 | 566000 |  |  | 566000 | 0 | 0
40386074A | Munday - Baylor County Line East of Goree | Knox County | One portion of the work required to relocate approximately 40 structures near Munday, TX impacted by the relocation of a section of US 277 | 2004-12-06 | 2005-01-31 | 1/14/085 |  | 242880 |  |  | 99 | 69 |  | 0.25 | 4/0 ACSR 6/1 | single pole, concrete | center line |  | 60 | 0.25 | 25.101(c)(5)(F) | 100% consent obtained | 242880 | 0 | 242880 |  |  | 242880 | 0 | 0
40386074B | Munday - Baylor County Line West of Goree | Knox County | One portion of the work required to relocate approximately 40 structures near Munday, TX impacted by the relocation of a section of US 277 | 2005-02-14 | 2005-03-15 |  |  | 364320 |  |  | 99 | 69 |  | 0.75 | 4/0 ACSR 6/1 | single pole, concrete | center line |  | 60 | 0.75 | 25.101(c)(5)(F) | 100% consent obtained | 364320 | 0 | 364320 |  |  | 364320 | 0 | 0
40386081 | East Munday - Lake Pauline | Knox County | One portion of the work required to relocate approximately 40 structures near Munday, TX impacted by the relocation of a section of US 277 | 2005-01-06 | 2005-02-18 | 2005-02-15 |  | 133100 |  |  | 99 | 138 |  | 0.1 | Bundled 4/0 ACSR 6/1 | concrete h-frame | center line |  |  |  | 25.101(c)(5)(F) | No new ROW required. | 133100 | 0 | 133100 |  |  | 133100 | 0 | 0
40394705 | East Munday - Paducah Clare St. | Knox County | One portion of the work required to relocate approximately 40 structures near Munday, TX impacted by the relocation of a section of US 277 | 2005-01-06 | 2005-02-18 | 2008-02-18 |  | 108000 |  |  | 99 | 138 |  | 0.1 | 477 ACSR 26/7 | concrete h-frame | center line |  |  |  | 25.101(c)(5)(F) | No new ROW required. | 108000 | 0 | 108000 |  |  | 108000 | 0 | 0
40394718 | Munday - Baylor County Line Switch | Knox County | One portion of the work required to relocate approximately 40 structures near Munday, TX impacted by the relocation of a section of US 277 | 2004-12-06 | 2005-01-31 | 2005-01-14 |  | 45000 |  |  | 99 | 69 |  | 0.1 | 4/0 ACSR 6/1 | single pole, concrete | center line |  |  |  | 25.101(c)(5)(F) | No new ROW required. | 45000 | 0 | 45000 |  |  | 45000 | 0 | 0
40386069 | Munday - Baylor County Line at Munday | Knox County | One portion of the work required to relocate approximately 40 structures near Munday, TX impacted by the relocation of a section of US 277 | 2005-01-24 | 2005-02-11 |  |  | 467600 |  |  | 99 | 69 |  | 0.75 | 4/0 ACSR 6/1 & 477 ACSR 26/7 | single pole, concrete | center line |  | 60 | 0.75 | 25.101(c)(5)(F) | 100% consent obtained | 467600 | 0 | 467600 |  |  | 467600 | 0 | 0
40424168 & 40474050 | Santa Anna-Bangs | Coleman County | Rebuild existing 69kV single wood pole line with double circuit 138/69 kV single steel pole construction, 795 ACSR conductor | 2005-01-24 | 2005-06-07 | 2005-06-07 |  | 5148800 |  |  | 96 | 69 | 69 and138 | 7.21 | 795 ACSR | Single Pole Steel, double circuit | center line | 7.21 | center line | 7.21 | 25.101(c)(5)(B) and 25.101(c)(5)(C) | 100% consent obtained | 5148800 | 0 | 5148800 |  |  | 5148800 | 0 | 0
40662798 | Mulberry Creek to Red Creek 345kV hairpin | Taylor County | Hairpin, 2000 ft. of 345kV double circuit line into the Bluff Creek Station. | 2006-03-20 | 2006-05-15 | 2006-06-30 |  | 1851700 |  |  | 99 |  | 345 | 0.8 | bundled 795 ACSR | Steel Single Pole |  |  | 300 | 0.4 | 25.101(c)(5)(A) | 100% consent obtained | 1851700 | 0 | 1851700 |  |  | 1851700 | 0 | 0
40662700 | NW Abilene to Oak Creek line monitors | Coke, Nolan, Runnels, Taylor Counties | Install line monitors; potential pole changeouts | 2006-06-01 | 2006-12-31 |  |  | 1441821 |  |  |  |  | 138 |  | 477 26.7 ACSR | Wooden H-Frame |  |  |  |  | 25.83(a)(3) | No new ROW required. | 1441821 | 0 | 1441821 |  |  | 1441821 | 0 | 0
40662758 | Seawest Buffalo Gap Tap to Bluff Creek | Taylor County | Rebuild existing 2.5 miles of 138kV transmission line with bundled 795 ACSS conductor and OPGW shield wire on single pole structures. | 2006-10-13 | 2007-01-31 | 2007-02-06 |  | 1930047 |  |  | 99 | 138 | 138 | 2.5 | Bundled 795 ACSS | Single Pole concrete |  | 2.5 |  |  | 25.101(c)(5)(B) | No new ROW required. | 1930047 | 0 | 1930047 |  |  | 1930047 | 0 | 0
40817612 | TUEC SYNTX-37th St. Line Replacement of 3 structures for TxDOT | Snyder, Texas / Scurry County | Replacing 3 single pole concrete davit arm structures with taller structures of same type | 2007-01-08 | 2007-01-12 |  |  | 101000 |  |  |  | 69 |  |  |  | Concrete Pole | Undefined Hwy Right of Way |  |  |  | 25.101 (c)(5)(F) | Structures Located in TxDOT Right of Way | 101000 | 0 | 101000 |  |  | 101000 | 0 | 0
40812079 | S Abilene - Seawest Tap | Taylor County | Reconductor with 1020 ACCC. Partial rebuild of existing structures (cross arms and insulators). Replacement of 4 structures for clearance requirements. | 2007-02-19 | 2007-06-01 |  |  | 6658000 |  |  | 99 | 138 |  | 18.15 | 1020 ACCC | Wood Braced H-Frame | Centerline | 18.15 |  |  | 25.101 (c)(5)(B) | No new ROW required. | 6658000 | 0 | 6658000 |  |  | 6658000 | 0 | 0
40769903 | Rebuild Elmdale - Clyde 69-kV line | Taylor, Callahan Co. (City of Clyde) | Rebuild and Reconductor the 69-kV line from Elmdale to Clyde (138-kV double ckt. capable) | 2007-04-27 | 2007-08-31 |  |  | 8468192 |  |  |  | 69 | 69 | 8.5 | 795 ACSR | Single pole steel | centerline | 8.5 | 100 | 7.4 | 25.101(c)(5)(B) | Consent obtained from majority of landowners to supplement existing easement. Where consent not obtained the structure will not be upgradable to 138 kV. | 8468192 | 0 | 8468192 |  |  | 8468192 | 0 | 0
40839051 | Whirlwind Generation Interconnect | Motley County, City of Matador | Modify Matador Substation to accept new 69 kV line from wind farm. Substation equipement upgrades at other local substations for increase power transfer requirement. | 2007-05-03 | 2007-09-01 |  |  | 3597100 |  |  |  | 69 | 69 | [7 empty] | 25.83 (a)(3) |  | 3597100 | 0 | 3597100 |  |  | 3597100 | 0 | 0
40833618 | Yellow Jacket Sub | Menard Co. | Construct new transmission substation - Add two 90 MVA autos 69/138kV LTC with cap banks & SCADA. | 2007-04-03 | 2008-05-01 |  |  | 7945000 |  |  |  | 138 | 138 | [7 empty] | 25.83 (a)(3) |  | 7945000 | 0 | 7945000 |  |  | 7945000 | 0 | 0
40872056 | N. Angelo to College Hills 138kV Cut-in | Tom Green County, City of San Angelo | Modify 138kV line to enter and exit new Bluffs distribuition substation | 2007-07-31 | 2007-10-15 |  |  | 412236 |  |  |  | 138 | 138 |  | 795 Drake | Single pole steel | on utility propery | .1 mi. | center line | 0.15 | 25.101(c)(5)(A) | TNC owns property. | 412236 | 0 | 412236 |  |  | 412236 | 0 | 0
40906389 | S. Abilene to Putnam 138kV line capacity upgrade | Taylor, Callahan Counties | Replace approximately 35% of existing wood H-frame structures with taller H-frame steel structures and add some additional dead ends | 2007-10-01 | 2008-09-01 |  |  | 4096800 |  |  |  | 138 |  | 36.4 | 4/0 ACSR | Steel H-Frame | Centerline defined | 36.4 |  |  | 25.101 (c)(5) (B) | No new ROW required. Increases loading capacity and improves reliablity. | 4096800 | 0 | 4096800 |  |  | 4096800 | 0 | 0
40917769 | Eden-Menard Hwy 83 Line Relocation for TXDOT | Concho County | Reroute for Highway 83 expansion, providing two new perpendicular crossings | 2007-09-13 | 2007-11-10 |  |  | 1576000 |  |  |  | 69 |  | 0.6 | 336 ACSR | Steel Single Pole |  |  | 60 | 0.6 | 25.101 (c)(5) (F) | Consent obtained and responsive to TXDOT request. | 1576000 | 0 | 1576000 |  |  | 0 | 0 | 0
40772038 | Rebuild and Reconductor Clyde to Putnam 69kV line | Callahan | Rebuild and Reconductor of 69kV line from Clyde to Putnam (capable of double circuit 138kV operation) | 2007-11-12 | 2008-04-11 |  |  | 21218766 |  |  |  | 69kV |  | 19.6 | 795 ACSR | Single pole steel | centerline | 3.08 | 100 | 16.52 | 25.101(c)(5)(B) | Consent obtained from majority of landowners to supplement existing easement. Where consent not obtained the structure will not be upgradable to 138 kV. | 21218766 | 0 | 21218766 |  |  | #N/A | #N/A | #N/A
40765392 | Rebuild and Reconductor Elm Creek to Shelton St. 69kV line | Taylor | Rebuild and Reconductor of 69kV line from Abilene Elm Creek to Shelton St(capable of single ckt 138 kV operation) | 2007-10-15 | 2007-12-31 |  |  | 5152300 |  |  |  | 69kV |  | 2.62 | 795 ACSR | Single pole steel | centerline | 2.62 | n/a | 2.62 | 25.101(c)(5)(B) | City of Abilene ROW. City Noticed. | 5152300 | 0 | 5152300 |  |  | #N/A | #N/A | #N/A
40769903A | Rebuild and Reconductor Abilene Plant to Elmdale 69kV line | Taylor, Callahan | Rebuild and Reconductor of 69kV line from Abilene Plant to Elmdale (Capable of double circuit 138kV) | 2007-10-15 | 2008-02-01 |  |  | 2589000 |  |  |  | 69kV |  | 4.9 | 795 ACSR | Single pole steel | centerline | 2.59 | 100 | 2.31 | 25.101(c)(5)(B) | Majority of rebuild/reconductor is in existing City of Abilene ROW and where consent from landowners to supplement easement has been obtained.Where consent not obtained the structure will not be upgradable to 138 kV. | 2589000 | 0 | 2589000 |  |  | #N/A | #N/A | #N/A
| 28960066 | [21 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | Actual Cost of Projects Completed This Month (Will Not Appear on Next Month Report): | Estimated Cost of Projects Completed This Month: | Estimated Cost of Projects Remaining Active This Month: | Total Estimated Cost of Projects Appearing in This Report:
[23 empty] | 0 | 0 | 74603662 | 74603662
[24 empty] | 0 | 23 | 23 | Project Count
[24 empty] | Completed | Active | Total
Note on A25: Allen Steven Boling: STAFF MODIFIED PROJECT NUMBER TO ALLOW ERROR CHECKING. (DUPLICATE PROJECT NUMBER)
Note on H1: aboling: Please enter only a single integer, if possible.
Note on I1: aboling: Please enter only a single integer, if possible.
Note on M1: aboling: If applicable.
Note on N1: aboling: If applicable.
Note on AD3: Allen Steven Boling: FORMULA DELETED TO ALLOW CHECKING PROJECT INCLUDED IN MUNDAY-THROCKMORTON PROJECT NO 40385791
Note on AD17: Allen Steven Boling: FORMULA DELETED TO ALLOW NEW PROJECT OR NAME REVISION
Note on AE3: Allen Steven Boling: FORMULA DELETED TO ALLOW CHECKING PROJECT INCLUDED IN MUNDAY-THROCKMORTON PROJECT NO 40385791
Note on AE17: Allen Steven Boling: FORMULA DELETED TO ALLOW NEW PROJECT OR NAME REVISION
Note on AF3: Allen Steven Boling: FORMULA DELETED TO ALLOW CHECKING PROJECT INCLUDED IN MUNDAY-THROCKMORTON PROJECT NO 40385791
Note on AF17: Allen Steven Boling: FORMULA DELETED TO ALLOW NEW PROJECT OR NAME REVISION

## BEPC
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost (Total) | Final Estimated Project Cost (Total) | Final Actual Project Cost (Total) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS | Estimated OR Actual Project Cost (SUBSTATION) |  | Last Month: | Current minus last month: | Cumulative Sum
00002 | Booneville to Hearne | Robertson & Brazos County | Rebuilding of approx. 23 miles of 138 kV 795 MCM line from existing Booneville sub. to existing Hearne sub. | 2003-06-01 | 2003-08-15 |  | 7989950 |  |  |  | 0% | 138 |  | 23 | 795 MCM | Single Pole Concrete | 60 | 23 |  |  | 25.101(c)(2)(C)(ii) | Affidavit attached with filing (April 2007). | 7989950 | 0 | 7989950 |  |  | 7989950 | 0 | 0
01006 | North Texas - Cottondale | Parker & Wise County | Rebuild approx. 26.8 miles of existing H-frame 4/0 ACSR 69 kV line with single pole 138 kV, 795 MCM ACSR construction. In addition, BEPC's Willow substation will be converted to 138 kV operation. | 2004-03-01 | 2004-06-01 |  | 7081200 |  |  |  | 100% | 69 | 138 | 26.8 | 795 MCM | Single Pole Concrete or Steel | 60 | 26.8 |  |  | 25.101(c)(2)(C)(ii) |  | 7081200 | 0 | 7081200 |  |  | 7081200 | 0 | 0
02012 | Fairview - Aledo | Hood & Parker County | Construct approximately 26 miles of new single-pole 138 kV 795 MCM transmission line from the existing radial fed BEPC Fairview substation to the existing radial fed BEPC Aledo substation. In addition, this project will include rebuilding approximately 5.8 miles of existing transmission line from the BEPC Waples substation to the BEPC Fairview substation. Also, included in the project is the construction of a switching station at Dicey and the addition of a 138 kV breaker at Waples substation. | 2005-06-15 | 2006-02-15 |  | 10752500 |  |  |  | 0% | NA | 138 | 26 | 795 MCM | Single Pole Concrete or Steel | NA | NA | 70 | 26 | 28254 | CCN Application Filed on August 15, 2003 | 10752500 | 0 | 10752500 |  |  | 10752500 | 0 | 0
0207420 | Jessica Loop | Johnson | Construct 3 miles of double circuit line from tap to Jessica Sub. | 2005-11-01 | 2005-02-05 |  | 2413000 |  |  |  | 100% | 138 | 138 | 2.75 mi. | 795 ACSR | Single Pole Concrete or Steel | NA | 2.75 mi. | 70 | 2.75 mi. | Docket No. 30365 | CCN Filed Nov. 8, 2004 | 2413000 | 0 | 2413000 |  |  | 2413000 | 0 | 0
0302021 | Whitney to Covington | Bosque, Hill & Johnson | Rebuild 27.85 miles of line from Whitney to Covington with 1033 ASCR | 2006-02-01 | 2006-06-01 |  | 5000000 |  |  |  | 35% | 138 | 138 | 27.85 mi | 1033 ACSR | Single Pole Concrete or Steel | 100 | 27.85 mi | 100 | 27.85 mi | 25.101(c)(5)(B) | Affidavit attached with filing. | 5000000 | 0 | 5000000 |  |  | 5000000 | 0 | 0
0301921 | Poage to Santa Fe | Bosque, Hill & Johnson | Rebuild 24.01 miles of line from Poage to Leon Junction with 795 ASCR | 2006-03-01 | 2006-07-01 |  | 4250000 |  |  |  | 100% | 69 | 138 | 24.01 mi | 795 ACSR | Single Pole Concrete or Steel | NA | 24.01 mi | 70 | 24.01 mi | 25.101(c)(5)(B) | Affidavit attached with filing. | 4250000 | 0 | 4250000 |  |  | 4250000 | 0 | 0
0302521 | Prairie Hill to Purdon | Limestone , Navarro | Rebuild 24.28 miles of line from Prairie Hill to Purdon with 795 ASCR | 2006-10-01 | 2006-01-01 |  | 7250000 |  |  |  | 100% | 138 | 138 | 24.28 mi | 795 ACSR | Single Pole Concrete or Steel | NA | 24.28 mi | 60 | 24.28 mi | 25.101(c)(5)(B) | Affidavit attached with filing. | 7250000 | 0 | 7250000 |  |  | 7250000 | 0 | 0
0203022 | Peoria - Forreston | Ellis, Hill | Rebuild 30.94 miles of line from Peoria to Itasca with 795 ASCR | 2006-05-01 | 2006-10-01 |  | 9250000 |  |  |  | 100% | 138 | 138 | 30.94 mi | 795 ACSR | Single Pole Concrete or Steel | 100 | 30.94 mi | 100 | 30.94 mi | 25.101(c)(5)(B) | Affidavit attached with filing. | 9250000 | 0 | 9250000 |  |  | 9250000 | 0 | 0
0401320 | Frisco - Krugerville Rebuild | Denton | Rebuild 8.0 miles of line from Frisco to Krugerville with 1590 ASCR | 2006-11-15 | 2007-02-15 |  | 3560000 |  |  |  | 0% | 138 | 138 | 8.0 mi. | 1590 ACSR | Single Pole Concrete or Steel | 100 | 8.0 mi. | 100 | 8.0 mi. | 25.101(c)(5)(B) | Affidavit at a later date closer to scheduled construction start | 3560000 | 0 | 3560000
4076 | Branchville - Silver City | Milam, Robertson | Rebuild 9.90 miles of line from Branchville to Silver City with 795 ASCR | 2006-12-01 | 2007-05-15 |  | 3712500 |  |  |  | 100% | 138 | 138 | 9.9 | 795 ACSR | Single Pole Concrete or Steel | 60 | 9.9 | 60 | 9.9 | 25.101(c)(5)(B) | Affidavit attached with filing. (6/1/06) | 3712500 | 0 | 3712500
303020 | Hood - De Cordova - Spunky | Hood, Somerville, Johnson | Rebuild 11.69 miles of line from Hood to Spunky with 795 ASCR | 2007-04-01 | 2007-07-01 |  | 4383750 |  |  |  | 5% | 138 | 138 | 11.69 | 795 ACSR | Single Pole Concrete or Steel | 60 | 11.69 | 60 | 11.69 | 25.101(c)(5)(B) | Affidavit attached with filing. | 4383750 | 0 | 4383750
302620 | Hilltop Lakes - Petteway | Robertson & Leon | Construct 8.28 miles of single circuit line from Hilltop Lake to Petteway | 2007-02-08 | 2007-06-08 |  | 2732400 |  |  |  | 15% | 69 | 138 | 8.28 mi. | 795 ACSR | Single Pole Concrete or Steel | 60 | 8.28 mi. | 60 | 8.28 mi. | 25.101(c)(5)(B) | Affidavit attached with filing. | 2732400 | 0 | 2732400
600820 | Granbury - Stephenville | Erath, Hood | Rebuild 26.16 miles of line from Granbury to Stephenvillewith 795 ASCR | 2007-02-15 | 2007-08-10 |  | 8632800 |  |  |  | 45% | 69 | 138 | 26.16 mi | 795 ACSR | Single Pole Concrete or Steel | 60 | 26.16 mi | 60 | 26.16 mi | 25.101(c)(5)(B) | Affidavit attached with filing. | 8632800 | 0 | 8632800
607210 | Wildcat | Johnson, Hood | Construct 8.5 miles of new 138 kV single circuit transmission from Wildcat Tap to Wildcat Sub | 2008-07-07 | 2009-01-01 |  | 3655000 |  |  |  | 0% | 138 | 138 | 8.5 mi | 795 ACSR | Single Pole Concrete or Steel | NA | 8.5 mi. | 70 | 8.5 mi. | 33800 | CCN Filed 01/30/07 | 3655000 | 0 | 3655000 |  |  | 3655000 | 0 | 0
303611 | Mustang Loop | Denton | Construct 8.0 miles of new 138 kV double circuit transmission from Mustang Tap to Mustang Sub | 2007-11-07 | 2008-01-01 |  | 4482450 |  |  |  | 0% | 138 | 138 | 17.0 mi | 1590 ACSR | Single Pole Concrete or Steel | NA | 8.0 mi. | 70 | 8.0 mi. | 32871 | CCN Filed 07/06/06 | 4482450 | 0 | 4482450
302722 | Olney - Shannon | Archer, Clay & Young | Rebuild 28.53 miles of line from Olney to Shannon with 1033 ACSR | 2008-02-08 | 2008-06-06 |  | 10841400 |  |  |  | 0% | 69 | 138 | 28.63 mi | 1033 ACSR | Single Pole Concrete or Steel | NA | 28.63 mi | 70 | 28.63 mi | 25.101(c)(5)(B) | Affidavit attached with filing. | 10841400 | 0 | 10841400 |  |  | 10841400 | 0 | 0
407420 | Pancake - Gatesville | Coryell | Rebuild 3.98 miles of line from Pancake to Gatesville with 795 ACSR | 2007-10-15 | 2008-02-15 |  | 1592000 |  |  |  | 0% | 69 | 138 | 3.98 mi | 795 ACSR | Single Pole Concrete or Steel | NA | 3.98 mi | 60 | 3.98 mi | 25.101(c)(5)(B) | Affidavit attached with filing. | 1592000 | 0 | 1592000
500820 | Gatesville - Santa Fe Sw. | Coryell | Rebuild 11.43 miles of line from Gatesville to Santa Fe Switch with 795 ACSR | 2007-10-15 | 2008-02-15 |  | 4572000 |  |  |  | 0% | 69 | 138 | 11.43 mi | 795 ACSR | Single Pole Concrete or Steel | NA | 11.43 mi | 60 | 11.43 mi | 25.101(c)(5)(B) | Affidavit attached with filing. | 4572000 | 0 | 4572000
400720 | Hasse - Downing | Comanche | Rebuild 7.34 miles of line from Hasse - Downing with 795 ACSR | 2007-11-15 | 2008-03-15 |  | 2936000 |  |  |  | 0% | 69 | 138 | 7.34 mi | 795 ACSR | Single Pole Concrete or Steel | NA | 7.34 mi | 60 | 7.34 mi | 25.101(c)(5)(B) | Affidavit attached with filing. | 2936000 | 0 | 2936000
[23 empty] | 0 | 0 | 0
| 9100000 | [21 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | Actual Cost of Projects Completed This Month (Will Not Appear on Next Month Report): | Estimated Cost of Projects Completed This Month: | Estimated Cost of Projects Remaining Active This Month: | Total Estimated Cost of Projects Appearing in This Report:
[23 empty] | 0 | 0 | 105086950 | 105086950
[24 empty] | 0 | 19 | 19 | Project Count
[24 empty] | Completed | Active | Total
Note on H1: aboling: Please enter only a single integer, if possible.
Note on I1: aboling: Please enter only a single integer, if possible.
Note on M1: aboling: If applicable.
Note on N1: aboling: If applicable.
Note on AD10: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AD11: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AD12: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AD13: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AD14: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AD16: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AD18: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AD19: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AD20: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AD21: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AD27: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AD29: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AD30: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AE10: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AE11: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AE12: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AE13: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AE14: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AE16: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AE18: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AE19: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AE20: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AE21: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AE27: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AE29: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AE30: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AF10: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AF11: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AF12: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AF13: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AF14: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AF16: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AF18: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AF19: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AF20: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AF21: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AF27: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AF29: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AF30: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.

## CNP
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost (Total) | Final Estimated Project Cost (Total) | Final Actual Project Cost (Total) | % Variance | Percent Complete | Existing Voltage | Upgraded or New Voltage | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS | Estimated OR Actual Project Cost (SUBSTATION) |  | Last Month: | Current minus last month: | Cumulative Sum
310 | I-10 Widening | Harris | Alteration of 138 kV Ckts. 73A and 81D within 200 feet of the existing facilities as requested by TxDOT for highway construction | 2003-10-10 | 2007-04-20 |  | 60590000 | 60590000 |  |  | 99% | 138 | NA | 11.6 | 3000 CU, 3500 CU | Steel Poles, Underground Cable | Street, 40 | 5.8 | 0-60 | 0.12 | 25.101(c)(2)(C)(v) | Construction Complete. Actual cost to be reimbursed by TxDOT. | 60590000 | 0 | 60590000 |  |  | 60590000 | 0 | 0
547 | Freeport LNG (QNTANA) | Freeport, Quintana, Brazoria | 69 kV Service to Customer-owned QNTANA Substation from Ckt. 47B | 2006-10-23 | 2007-08-31 | 2007-08-03 | 6395000 | 11200000 |  |  | 95% | 69 | NA | 7.8 | 1433.6 ACSS | Concrete Poles, Steel Poles, Steel Towers | NA | NA | 50-100 | 3.9 | Docket No. 30617 | Final Order signed 3/22/06. | 11200000 | 0 | 11200000 | 285000 |  | 11200000 | 0 | 0
573 | 345 kV Hillje Project | Thompsons, Fort Bend, Wharton, Matagorda and Brazoria Counties | Construct a new double-circuit 345 kV transmission line and install an additional 345 kV circuit on an existing transmission line | 2006-03-13 | 2007-08-31 | 2007-07-31 | 80050000 | 80050000 |  |  | 95% | NA | 345 | 117.2 | 2-1433.6 ACSS, 2-795 ACSR | Steel Towers | 200-400 | 46.3 | 90-125 | 22 | Docket No. 31591 | Final Order signed 2/13/06. | 80050000 | 0 | 80050000 |  |  | 80050000 | 0 | 0
622 | West Bay Substation | Galveston, Galveston | 138 kV Service to West Bay Substation within one mile of Ckt. 63Z | 2006-08-15 | 2007-03-31 |  | 970000 | 970000 | 896066 | -7.622% | 100% | 138 | NA | 1.6 | 266.8 ACSS | Concrete Poles | Street, 25 | 0.7 | 10-535 | 0.08 | 25.101(c)(5)(A) | Last time to report. Construction Complete. | 970000 | 970000 | 0 | 14765000 |  | 970000 | 0 | 0
622.1 | West Bay Corner - Stewart | Galveston, Galveston | Reconductor and Partial Rebuild of 138 kV Ckt. 63Z; Installation, on an existing transmission line, of an additional 138 kV circuit not previously certificated | 2006-10-02 | 2007-03-31 |  | 5860000 | 4658000 | 5042177.37 | 8.248% | 100% | 138 | NA | 26.4 | 266.8 ACSS | Wood Poles, Steel Poles | Street, 25 | 13.2 | NA | NA | 25.101(c)(5)(B); 25.101(c)(5)(C) | Last time to report. Construction Complete. | 4658000 | 4658000 | 0 |  |  | 4658000 | 0 | 0
642 | CANEY_ - South Lane City | Wharton, Wharton | Partial Reconductor and Partial Rebuild of 138 kV Ckt. 60B | 2006-09-11 | 2007-07-02 |  | 5720000 | 5720000 |  |  | 99% | 138 | NA | 13.4 | 927.2 ACAR, 2-959.6 ACSS | Steel Towers, Concrete Poles, Wooden H-Frames | 25-320 | 12.6 | NA | NA | 25.101(c)(5)(B) | Construction Complete. | 5720000 | 0 | 5720000 |  |  | 5720000 | 0 | 0
658 | Velasco Loop | Freeport, Brazoria | Partial Rebuild of 69 kV Ckts. 10B and 47B | 2007-07-09 | 2007-08-31 |  | 351000 | 400000 |  |  | 95% | 69 | NA | 11.4 | 795 AAC | Wooden H-Frames, Steel Towers, Concrete Poles | Street, 27-40 | 11.4 | NA | NA | 25.101(c)(5)(B) |  | 400000 | 0 | 400000 |  |  | 400000 | 0 | 0
2006.1 | LaMarque - Webster | Webster, Harris, League City, Dickinson, Texas City, LaMarque, Galveston | Routine maintenance of 69 kV Ckt. 13B | 2006-11-06 | 2007-11-10 |  | 350000 | 366000 |  |  | 85% | 69 | NA | 15.9 | 397 ACSR, 927 ACAR, 795 AAC | Wood Poles, Steel Towers, Steel Poles | 70-1220 | 15.9 | NA | NA | 25.83 (a)(3) |  | 366000 | 0 | 366000 |  |  | 366000 | 0 | 0
677 | Wharton - CANEY_ Corner | Wharton, Wharton | Reconductor and Rebuild of 138 kV Ckt. 60B; 138kV Service to CANEY_ Substation within one mile of Ckt. 60B | 2007-05-09 | 2007-11-30 |  | 569000 | 709000 |  |  | 94% | 138 | NA | 1 | 2-959.6 ACSS | Concrete Poles, Steel Towers | 80 | 0.5 | NA | NA | 25.101(c)(5)(B); 25.101(c)(5)(A) |  | 709000 | 0 | 709000 |  |  | 709000 | 0 | 0
642.1 | Dyann Substation | Wharton | 138 kV Service to Dyann Substation within one mile of Ckt. 60B | 2007-01-02 | 2007-05-01 |  | 970000 | 970000 | 791145 | -18.44% | 100% | 138 | NA | 0.97 | 2-959.6 ACSS | Concrete Poles, Steel Towers | NA | NA | 150 | 1.9 | 25.101(c)(5)(A) | Last time to report. Construction Complete. | 970000 | 970000 | 0 |  |  | 970000 | 0 | 0
677.1 | CANEY_ Corner - East Bernard | Wharton, East Bernard, Wharton | Reconductor and Rebuild of 138 kV Ckt. 60B | 2007-05-07 | 2007-12-31 |  | 6163000 | 8463000 |  |  | 20% | 138 | NA | 14.4 | 2-959.6 ACSS | Concrete Poles, Steel Towers | 80 | 14.4 | NA | NA | 25.101(c)(5)(B) |  | 8463000 | 0 | 8463000 |  |  | 8463000 | 0 | 0
2006.2 | Angleton - PETSON | Danbury, Alvin, Brazoria | Routine maintenance of 138 kV Ckt. 04C | 2007-11-01 | 2007-12-01 |  | 344000 | 414000 |  |  | 0% | 138 | NA | 15.7 | 795 ACSR, 795 AAC | Steel Towers, Wooden H-Frames, Wood Poles, Steel Poles | 60-145 | 15.7 | NA | NA | 25.83 (a)(3) |  | 414000 | 0 | 414000 |  |  | 414000 | 0 | 0
2 | 345 kV Emergency Restoration | Leon, Madison | Emergency restoration of 345 kV Ckts. 74C And 98D | 2006-12-29 | 2007-08-31 |  | 2500000 | 2500000 |  |  | 95% | 345 | NA | 2 | 2-795 ACSR | Steel Towers | 180 | 1 | NA | NA | 25.83(d) | Circuit 98D was temporarily restored on wood poles on 1/4/07. Circuit 74C was temporarily restored on wood poles on 1/6/07. | 2500000 | 0 | 2500000 |  |  | 2500000 | 0 | 0
271 | Stafford 35 kV Substation | Stafford, Fort Bend | 138 kV Service to Stafford 35 kV Substation within one mile of Ckts. 05G and 09A | 2007-04-24 | 2007-05-21 |  | 100000 | 101000 | 101413 | 0.4089% | 100% | 138 | NA | 0.1 | 795 ACSR, 795 AAC | Concrete Poles | 190 | 0.1 | NA | NA | 25.101(c)(5)(A) | Last time to report. Construction Complete. | 101000 | 101000 | 0 |  |  | 101000 | 0 | 0
670 | Pearland Town Center Relocation | Pearland, Brazoria | Relocation of a portion of 138 kV Ckt. 05B at the request of and expense of CBL & Associates Properties, Inc. | 2007-04-11 | 2007-06-14 |  | 302000 | 302000 |  |  | 99% | 138 | NA | 0.6 | 2-397 ACSR | Concrete Poles | 80 | 0.6 | NA | NA | 25.101(c)(5)(D) | Construction Complete. Actual cost to be reimbursed by CBL & Associates Properties, Inc. | 302000 | 0 | 302000 |  |  | 302000 | 0 | 0
515 | U.S. Highway 90E | Houston, Harris | Alteration of 69 kV Ckts. 17A, 20C, 38A, 38B; 138kV Ckts. 03F, 08E, 08F, 70D, 77A; and 345kV Ckts. 74F and 75C as requested by TxDOT for highway construction | 2007-08-20 | 2008-02-21 |  | 2161000 | 3191000 |  |  | 0% | 69, 138, 345 | NA | 2.8 | 795 AAC, 2-795 ACSR, 2-959 ACSS, 2-795 AAC, 2-2167 ACSR | Steel Towers, Steel Poles, Concrete Poles | 20-200, Street | 1 | NA | NA | 25.101(c)(5)(F) | Actual cost to be reimbursed by TxDOT. | 3191000 | 0 | 3191000 |  |  | 2883000 | 308000 | 308000
661 | Weingarten Relocation | Tomball, Harris | Relocation of a portion of 138 kV Ckt. 66B at the request of, expense of and on right-of-way provided by Weingarten Realty Investors | 2007-05-07 | 2007-08-01 |  | 570000 | 637000 |  |  | 99% | 138 | NA | 0.3 | 795 ACSR, 795 AAC | Steel Towers, Concrete Pole | 80 | 0.13 | 80 | 0.17 | 25.101(c)(5)(D) | Construction Complete. Actual cost to be reimbursed by Weingarten Realty Investors. | 637000 | 0 | 637000 |  |  | 637000 | 0 | 308000
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | Actual Cost of Projects Completed This Month (Will Not Appear on Next Month Report): | Estimated Cost of Projects Completed This Month: | Estimated Cost of Projects Remaining Active This Month: | Total Estimated Cost of Projects Appearing in This Report:
[23 empty] | 6830801.37 | 6699000 | 174542000 | 181241000
[24 empty] | 4 | 13 | 17 | Project Count
[24 empty] | Completed | Active | Total
Note on H1: aboling: Please enter only a single integer, if possible.
Note on H3: Allen Steven Boling: $6,395,000 TRANSMISSION LINE AND $190,000 SUBSTATION.
Note on H4: Allen Steven Boling: $80,050,000 TRANSMISSION LINE AND $14,765,000 SUBSTATION.
Note on I1: aboling: Please enter only a single integer, if possible.
Note on I3: Allen Steven Boling: FINAL ESTIMATED COST: $11,200,000 TRANS AND $285,000 SUBSTATION.
Note on I4: Allen Steven Boling: $80,050,000 TRANSMISSION LINE AND $14,765,000 SUBSTATION.
Note on M1: aboling: If applicable.
Note on N1: aboling: If applicable.

## DSEC
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost | Final Estimated Project Cost | Final Actual Project Cost | % Variance | Percent Complete | Existing Voltage | Upgraded or New Voltage | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS | Estimated OR Actual Project Cost (SUBSTATION) |  | Last Month: | Current minus last month: | Cumulative Sum
33755+ | Sub 22 transmission project | Castro, Parmer Counties | New 115 kv transmission line to existing Substation. Build new Station along Path and eventually convert existing station to 115 kv | 2006-03-15 |  |  | 3815000 | 3815000 |  |  | 50% | na | 115 | 18.3 | 397.5 kcmil 26/7 ACSR | wood poles, Concrete Poles | na | na | 20, 40 | 18.3 | 33000 |  | 3815000 | 0 | 3815000 | 1989000 |  | 3815000 | 0 | 0
33757 | Sub 23 | Deaf Smith County | Install new 12 mVa station along existing transmission line. | 2007-05-30 |  |  | na | 1280000 |  |  | 5% | 69 | na | na | na | na | na | na | na | na | 25.101(c)(2) | construction began | 1280000 | 0 | 1280000 |  |  | 1280000 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | Actual Cost of Projects Completed This Month (Will Not Appear on Next Month Report): | Estimated Cost of Projects Completed This Month: | Estimated Cost of Projects Remaining Active This Month: | Total Estimated Cost of Projects Appearing in This Report:
[23 empty] | 0 | 0 | 5095000 | 5095000
[24 empty] | 0 | 2 | 2 | Project Count
[24 empty] | Completed | Active | Total
Note on H2: Allen Steven Boling: $3,815,000 T-Line $2,005,000 Substations
Note on I2: Allen Steven Boling: $3,815,000 T-Line $1,989,000 Substations

## EGSI
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost (Total) | Final Estimated Project Cost (Total) | Final Actual Project Cost (Total) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS | Estimated OR Actual Project Cost (SUBSTATION) |  | Last Month: | Current minus last month: | Cumulative Sum
TL4500 | Dayton-Gordon Construct New 138kV transmission line. | Liberty County, TX | Construct new 138kV single pole single circuit transmission line for Coastal Water Authority to their Trinity River Pumping Station | 2005-12-15 | 2006-09-11 | 2006-09-25 | 10370000 | 11066747 | 8749000 | -16% | 100 | na | 138 | 11.4 | 666ACSR | Concrete and Steel Poles | na | na | 100 | 11.4 | 28938 | This project will be removed from the report next month. | 11066747 | 11066747 | 0 | 697000 |  | 11066747 | 0 | 0
TL4433 | Johnstown-Porter Construct New 230kV Transmission Line | Montgomery County, TX | Construct 4.9 miles of single pole double circuit designed 230kV transmission line from Porter Substation to the new Johnstown Substation | 2009-01-15 | na | na | 5332055 |  |  |  |  | na | 230 | 9.8 | Bundled 954 ACSR | Concrete or Steel | na | na | 100 | 4.9 | 29420 | This project was delayed as a result of Hurricane Rita and other mitigating steps taken by EGSI. | 5332055 | 0 | 5332055 |  |  | 5332055 | 0 | 0
TL9965 | Port Acres Bulk to Keith Lake 230kV Transmission Line Project | Jefferson County, Texas | Construct new 230Kv double circuit transmission line fron the existing Port Acres Bulk Substation to the new Keith Lake Substation at the new Golden Pass LNG Facility | 2008-03-01 | na | na | 21690000 |  |  |  |  | na | 230 | 22.4 | 666 ACSR | Single Pole & H-Frame Double Circuit | na | na | 100 | 11.2 | 31198 | Design has begun. R/W acquisition is ongoing. | 21690000 | 0 | 21690000
TL5400 | Proposed Merlin Substation to L-17 138kV Transmission Line | Orange County, Texas | Construct new 138kV single pole double circuit transmission line from the new proposed Merlin Substation to the existing line 17 | 2009-03-01 | na | na | 3142673 |  |  |  |  | na | 138 | 2.6 | Bundled 666 ACSR | Single Pole Steel & Concrete | na | na | 100 | 2.6 | 31241 | This project was delayed as a result of Hurricane Rita. R/W acquisition is ongoing. | 3142673 | 0 | 3142673 |  |  | 3142673 | 0 | 0
TL4530 | Jayhawker-Security: Reroute L-811 at Security Landfill | Montgomery County, TX | Construct 1.4 MI single pole single circuit reroute of 138kV L-811 at Waste Management's Security Landfill | 2007-10-29 | na | na |  | 1550000 |  |  |  | 138 | na | 1.4 | 666 ACSR | Simgle Pole Steel & Concrete | 100 | 0.7 | 100 | 1.4 | 25.101(c)(5)(D)(i)(ii) | Construction should begin August 13th. | 1550000 | 0 | 1550000 |  |  | 1550000 | 0 | 0
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | Actual Cost of Projects Completed This Month (Will Not Appear on Next Month Report): | Estimated Cost of Projects Completed This Month: | Estimated Cost of Projects Remaining Active This Month: | Total Estimated Cost of Projects Appearing in This Report:
[23 empty] | 8749000 | 11066747 | 31714728 | 42781475
[24 empty] | 1 | 4 | 5 | Project Count
[24 empty] | Completed | Active | Total
Note on H1: aboling: Please enter only a single integer, if possible.
Note on H2: Allen Steven Boling: From Application: T-Line: $10,370,000; Station: $697,000
Note on I1: aboling: Please enter only a single integer, if possible.
Note on I2: Allen Steven Boling: Final Estimated Cost: T-Line: $11,066,000; Station: $697,000
Note on J2: Allen Steven Boling: Final Cost: T-Line: $8,749,000; Station: $330,891
Note on M1: aboling: If applicable.
Note on N1: aboling: If applicable.
Note on AD4: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AE4: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AF4: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.

## EPE
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost ($) | Final Estimated Project Cost ($) | Final Actual Project Cost ($) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS | Estimated OR Actual Project Cost (SUBSTATION) |  | Last Month: | Current minus last month: | Cumulative Sum
TL145 | Montwood to Coyote 115kV Line (12600 Line) | El Paso, El Paso | As a part of the overall Eastside Expansion Plan, a new line is to be constructed between Montwood and Coyote Substations. The new line will be constructed utilizing single pole steel structures. The preferred route is approximately 7.8 miles in length. | 2008-01-02 |  |  | 1634174 | [5 empty] | 115 | 7.84 | 954 ACSR, single conductor, single circuit | 90' galvanized steel monopole structures. | Street ROW - franchise | 0.29 | 100, 15 overhang | 2.94, 4.61 | 24666 | This project is being planned for construction in early 2008 if Right of Way for TL102 can be obtained by mid '07. Otherwise, this will be built in '07 and TL102 will follow. | 1634174 | 0 | 1634174 | 1055289 |  | 1634174 | 0 | 0 | 2689462.61
TL102 | Santa Teresa - Montoya 115 kV Line | El Paso, El Paso | Construct approximately 7.19 miles of 115kV transmission line on single pole structures to complete an electrical loop between Santa Teresa Substation (Dona Ana County, NM.) and Montoya Substation (El Paso County, TX). The project is intended to improve service reliability and provide for future electrical load growth in the project area. | 2008-08-01 |  |  | 5335988 | [5 empty] | 115 | 7.19 | 954 ACSR, single conductor, single circuit | 95' galvanized steel monopole structures. | Street ROW - franchise | 2.29 | 25, 50, 100 | 2.29, 4.76, 0.14 | 26670 | Row acquisition continues. Completion expected by end of year. Materials will be ordered during first quarter, expected delivery in mid-year. | 5335988 | 0 | 5335988 | 568230 |  | 5335988 | 0 | 0
TL117 | SFPP - Proposed 115 kV Transmission Line | El Paso, El Paso | Construct approximately 9.5 miles of 115 kV transmission circuit to provide transmission service to a petroleum storage and pumping facility. The project will involve adding a second circuit to an existing line previously constructed for double circuit and constructing approximately 3.8 miles of new circuit on steel monopoles configured for double circuit. | 2007-09-04 |  |  | 3124268 | [5 empty] | 115 | 9.5 | 954 ACSR, single conductor, double circuit | 65' to 75' galvanized steel structures. Some will be H-Frame replacements, new construction will be monopole structures double circuit capable. | 100 | 5.7 | 50 | 3.8 | 33397 | ROW acquisition still not complete. Now anticipating starting after Labor Day. | 3124268 | 0 | 3124268 |  |  | 3124268 | 0 | 0
TL110 | Dyer - Leo 115 kV Upgrade | El Paso, El Paso | Rebuild approximately 4.4 miles of 69 kV transmission line. EPE will replace existing structures and conductor. Existing 336 ACSR conductor will be replaced with 954 MCM ACSR and re-insulated for future 115 kV operation. A portion of the line passing through Ft. Bliss property will be realigned to accommodate plans for new housing development on the base. Consent for the relocation has been provided by the Directorate of Public Works, Ft. Bliss, Texas. | 2007-05-25 |  |  | 1200000 | 2419277 |  |  | 10% | 69 |  | 4.37 | 954 ACSR, single conductor, single circuit | 65'-90' steel monopole structures | Street ROW - franchise, 50 | 3.25, 1.14 | 50 | 1.12 | 25.101(c)(5)(B) | EPE Crews will be returning to this project upon completion of Biggs Transmission In & Out | 2419277 | 0 | 2419277 | 2282101 |  | 2419277 | 0 | 0 |  | 3482101
TL107 | Dyer - Austin - 6400 Line 69 kV Rebuild | El Paso, El Paso | EPE will reconstruct and relocate approximately one mile of the existing Dyer - Austin 69 kV line. The line will be relocated to the existing 19400 Dyer-Austin 115 kV line which will be re-structured to accommodate the two circuits. Conductor on the existing 115 kV line will remain the same. 336 MCM ACSR conductor on the 69 kV line will be replaced with 954 MCM ACSR. The 69 kV line is being re-routed to minimize corners, guy poles and anchors in residential lots. The new route will also reduce interference with trees and improve reliability. System Planning has indicated the 69 kV line from Dyer - Austin will have to be reconductored by 2010 due to overloading. This project will complete approximately one-half of the required reconductor. | 2007-10-15 |  |  | 1057000 |  |  |  |  | 69 |  | 1 | 954 ACSR, single conductor, single circuit | one 105' steel H-Frame structure for freeway crossing, remaining structures are steel monopole double circuit tangents and self-supporting corner and dead-end structures. | 50 | 1 | n/a | n/a | 25.101(c)(5)(B), 25.101(c)(5)(C) | EPE crews will be rebuilding this facility. Construction will follow Dyer-Leo Rebuild, which is anticipated to be completed in September '07. Construction expected to begin mid-October. | 1057000 | 0 | 1057000 |  |  | 1057000 | 0 | 0
TL151 | Biggs In and Out Transmission Line | Ft. Bliss, El Paso | EPE will construct two new 115 kV lines to serve a new substation being constructed by Ft. Bliss. Ft. Bliss is providing the necessary rights of way for the new transmission facilities. The substation is being constructed to accommodate the relocation of 19,000 plus troops to Ft. Bliss. | 2007-06-11 |  |  | 1809020 | 2155583 |  |  | 90% |  | 115 | 3.02 | 954 ACSR, single conductor, single circuit | 70' Steel H-Frame, configured for double circuit |  |  | 150 | 1.51 | 25.101(c)(5)(A) |  | 1809020 | 0 | 1809020 |  |  | 1809020 | 0 | 0
0
CCNs 24666 and 26670 Initial Estimated Costs in Previous Reports Before 03-2007 Included Substation Costs as Well as T-Line.
[18 empty] | Actual Cost of Projects Completed This Month (Will Not Appear on Next Month Report): | Estimated Cost of Projects Completed This Month: | Estimated Cost of Projects Remaining Active This Month: |  |  | Actual Cost of Projects Completed This Month (Will Not Appear on Next Month Report): | Estimated Cost of Projects Completed This Month: | Estimated Cost of Projects Remaining Active This Month: | Total Estimated Cost of Projects Appearing in This Report:
[18 empty] | 14160450 | 250 | 6.43 |  |  | 0 | 0 | 15379727 | 15379727
[19 empty] | 3 | 3 |  |  |  | 0 | 6 | 6 | Project Count
[19 empty] | Completed | Active |  |  |  | Completed | Active | Total
Note on H1: aboling: Please enter only a single integer, if possible.
Note on H2: Allen Steven Boling: $1,634,174 T-Line; $1,055,289 Substation
Note on H3: Allen Steven Boling: $5,335,988 T-Line; $568,230 Substation
Note on H4: Allen Steven Boling: $3,124,268 T-Line; $2,282,101 Substation
Note on H7: Allen Steven Boling: $1,809,020 T-Line; $3,182,858 Substation
Note on H8: Allen Steven Boling: $1,809,020 T-Line; $3,182,858 Substation
Note on I1: aboling: Please enter only a single integer, if possible.
Note on I7: Allen Steven Boling: $2,155,583 T-Line; $3,430,000 Substation Final Estimated Cost
Note on I8: Allen Steven Boling: $2,155,583 T-Line; $3,430,000 Substation Final Estimated Cost
Note on M1: aboling: If applicable.
Note on N1: aboling: If applicable.
Note on AD3: Allen Steven Boling: FORMULA HAS BEEN REPLACED BY AN INTEGER TO ALLOW FIRST USE OF THIS NEW REPORT. FORMULA WILL BE RESTORED THE NEXT MONTH REPORT.
Note on AD4: Allen Steven Boling: FORMULA HAS BEEN REPLACED BY AN INTEGER TO ALLOW FIRST USE OF THIS NEW REPORT. FORMULA WILL BE RESTORED THE NEXT MONTH REPORT.

## FEC
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost (Total) | Final Estimated Project Cost (Total) | Final Actual Project Cost (Total) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS | Estimated OR Actual Project Cost (SUBSTATION) |  | Last Month: | Current minus last month: | Cumulative Sum
#67102705 | KIOWA-TNMPC 69F138kV Transmission Line | Rains, Hunt | Rebuild 69 kV single wood pole and reconductor with 795 ACSR from Kiowa Substation to TNMPC Substation | 2006-02-02 | 2006-05-31 | na | 1243000 | 1740500 |  |  | 100% | 69 | 69 | 5.1 | 795 kcmil ACSR "Drake" | Single steel pole | 60 | 5.1 | 0 | 0 | 25.101( c)(5)( B)(i) |  | 1740500 | 0 | 1740500 |  |  | 1740500 | 0 | 0
#67110105 | Forney - NW Terrell Transmission Line | Kaufman | New 138 kV transmission line from Windmill Farms Substation to TXU 138kV. | 2007-10-01 | 2008-07-01 |  | 2981000 |  |  |  | 0% | na | 138 | 5.06 | 795 kcmil ACSR "Drake" | Single steel pole | na | na | 80 | 5.06 | 28936 |  | 2981000 | 0 | 2981000 |  |  | 2981000 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | Actual Cost of Projects Completed This Month (Will Not Appear on Next Month Report): | Estimated Cost of Projects Completed This Month: | Estimated Cost of Projects Remaining Active This Month: | Total Estimated Cost of Projects Appearing in This Report:
[23 empty] | 0 | 0 | 4721500 | 4721500
[24 empty] | 0 | 2 | 2 | Project Count
[24 empty] | Completed | Active | Total
Note on H1: aboling: Please enter only a single integer, if possible.
Note on H2: Allen Steven Boling: "na" was originally entered, and Staff changed back to the values found in the December, 2006 report. Contacted Linda Milligan to attempt resolving.
Note on I1: aboling: Please enter only a single integer, if possible.
Note on I2: Allen Steven Boling: "na" was originally entered, and Staff changed back to the values found in the December, 2006 report. Contacted Linda Milligan to attempt resolving.
Note on M1: aboling: If applicable.
Note on N1: aboling: If applicable.

## LCRA
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost (Total) | Final Estimated Project Cost (Total) | Final Actual Project Cost (Total) | % Variance | Percent Complete | Existing Voltage | Upgraded or New Voltage | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS | Estimated OR Actual Project Cost (SUBSTATION) |  | Last Month: | Current minus last month: | Cumulative Sum
1001776, 1001840 | Kunitz-Wink | Culberson, Reeves, Loving, Winkler | New 138 kV transmission line from wind plant at Kunitz to TXU Wink Substation | 2009-06-05 | 2009-11-01 |  | 30212829 |  |  |  | 0% |  | 138 | 101.5 | 3x2-795 kcmil ACSR "Drake" | Single Pole & H-frame | na | 0 | 100 - 160 | 101.5 | CCN Docket No. 22762 approved 7/13/01 |  | 30212829 | 0 | 30212829 |  |  | 30212829 | 0 | 0
1005925 | Menger Creek Substation Addition Project (Cico-to-Helotes TL Addition T-244) | Kendall, Bexar, City of Boerne | Construct a new bundled 795 ACSR 138 kV transmission line approximately 4 miles in length from a tap point on the Boerne Cico-to-Helotes transmission line to the proposed Menger Creek Substation. | 2006-09-28 | 2007-06-22 | 2007-06-22 | 4551900 | 6569000 |  |  | 100% | na | 138 | 3.8 | 3x2-795 kcmil ACSR "Drake" | Single Pole, Steel or Prestressed Concrete | na | 0 | 80 | 3.8 | CCN Docket #29684 approved 3/22/06 |  | 6569000 | 0 | 6569000 |  |  | 6569000 | 0 | 0
1006431 | Bergheim-to-Boerne TL T228 Add | Kendall | Extend existing transmission line into new bay position to accommodate substation construction at Fairoaks Substation. | 2007-04-30 | 2007-05-11 | 2007-05-11 |  | 175000 |  |  | 100% | 138 | 138 | .1 mi | 3x1-795 kcmil ACSR "Drake" | Steel Single Poles | N/A | N/A | N/A | 0.1 | 25.101(C)(5)(A) |  | 175000 | 0 | 175000 |  |  | 175000 | 0 | 0
1006537 1006536 | Friendship-to-Escarpment T363 Add Escarpment-to-Manchaca T420 Add | Hays, Travis | Construct new 138 kV transmission line from Friendship to Manchaca Subs, New Substation near Highway 45 | 2007-02-16 | 2008-06-30 |  | 14954446 | 19489000 |  |  | 20% | NA | 138 | 7.8 | 3x1-795 kcmil ACSR | SINGLE POLE, STEEL OR CONCRETE | NA | NA | 80 | 7.8 | STM Docket #30833 approved 8/23/05 | 3700 FEET ACROSS CIRCLE C GOLF COURSE WILL BE UNDERGROUND. Tranferred from PEC Docket No. 18389 | 19489000 | 0 | 19489000 |  |  | 19489000 | 0 | 0
1005727 | Flatonia-to-Yoakum TL Add | Fayette, Gonzales | Modify existing transmission line by adding lightning arresters | 2006-07-26 | 2007-04-13 | 2007-04-13 | 1081200 | 564470 |  |  | 100% | 69 | 69 | 27.67 | 3x1-2/0 ACSR "Quail ". 3x1-4/0 ACSR "Penguin", 3x1-336 ACSR "Linnet" | H-frame, Single Pole | 100 ft, CL | 27.67 | 0 | 0 | 25.101(C)(5)(B) | 25.101(C)(5)(B) | 564470 | 0 | 564470 |  |  | 564470 | 0 | 0
1007490 | Flatonia-to-Harwood T145 Add | Fayette, Gonzales | Replace approximately 21 structures Flatonia-to-Waelder-to-Thompsonville-to-Harwood 69 kV TL, to raise height and increase the line-to-ground clearance and achieve higher ampacity rating, to the full rating of the existing 4/0 ACSR conductor. | 2006-12-06 | 2007-01-18 | 2007-01-18 | 414000 | 260812 |  |  | 100% | 69 | 69 | 24 | 3x1-4/0 ACSR "Penguin" | Wood H | Varies | 24 | 0 | 0 | 25.101(C)(5)(B) |  | 260812 | 0 | 260812 |  |  | 260812 | 0 | 0
1008036 | McNeil-to-Round Rock T136 Add | Travis, City of Austin | Extend existing line approximately 0.10 miles into the new Wells Branch Substation | 2007-01-16 | 2007-05-15 | 2007-05-15 | 400000 | 608000 |  |  | 100% | 138 | 138 | 0.1 | 6x2-795 ACSR "Drake" | Single Pole | 100 | 0 | 60 | 0.1 | 25.101(C)(5)(A) |  | 608000 | 0 | 608000 |  |  | 608000 | 0 | 0
1008038 | Howard Lane-to-Round Rock S T387 Add | Travis, City of Austin | Extend existing line approximately 0.10 miles into the new Wells Branch Substation, add approximately 1-mile of OPGW to existing line | 2007-01-10 | 2007-05-15 | 2007-05-15 | 580000 | 623000 |  |  | 100% | 138 | 138 | 0.1 | 6x2-795 ACSR "Drake" | Single Pole | 100 | 1 | 60 | 0.1 | 25.101(C)(5)(A) |  | 623000 | 0 | 623000 |  |  | 623000 | 0 | 0
1006778 | Barker Split-to-Kerrville Stadium T225 Add | Kerr | Reconductor from 336 to 795 ACSR between Barker and Kerrville Stadium | 2007-02-26 | 2007-04-16 | 2007-04-16 | 1500000 | 2340000 |  |  | 100% | 138 | 138 | 1.90 mi | 6x1-795 ACSR "Drake" | Lattice Towers & Steel Poles | varies, 85-ft to 100-ft | 1.9 | 0 | 0 | 25.101(C)(5)(B) |  | 2340000 | 0 | 2340000 |  |  | 2340000 | 0 | 0
1003547 | Medina Lake-to-CPS Anderson TL Add T-460 | Bandera, Medina | New 138 kV transmisison line from Medina Lake Substation through proposed Miico Substation to CPS Energy Tie | 2009-06-01 | 2009-12-31 |  | 13897000 |  |  |  | 0% | 0 | 138 | 9 | 3x1-795 ACSR "Drake" | Single Pole & Lattice Tower | 0 | 0 | Varies, 60, 80-170 | 9 | CCN Docket #32934 | CCN filed 8/2/06 | 13897000 | 0 | 13897000 |  |  | 13897000 | 0 | 0
1007722 | Dump Hill-to-Dale T125 Add | Caldwell | Overhaul existing transmission line | 2007-04-09 | 2007-06-13 | 2007-06-13 | 200000 | 328900 |  |  | 100% | 69 | 69 | 7.75 | 3x1-4/0 ACSR "Penguin" | Single Pole & Wood H | Varies | 7.75 | 0 | 0 | N/A (Overhaul) |  | 328900 | 0 | 328900 |  |  | 328900 | 0 | 0
1006645 | Luling-to-Waelder TL Add | Gonzales | Modify existing transmission line to accommodate addition of breakers and other improvements at Waelder Substation. | 2007-02-15 | 2007-05-21 | 2007-05-21 | 241155 | 130000 |  |  | 100% | 69 | 69 | 0.1 | 3x1-4/0 ACSR "Penguin" | Single Pole | Varies | 0.1 | 0 | 0 | 25.101(C)(5)(B) |  | 130000 | 0 | 130000 |  |  | 130000 | 0 | 0
1006643 | Waelder-to-Flatonia TL Add | Gonzales | Modify existing transmission line to accommodate addition of breakers and other improvements at Waelder Substation. | 2007-02-15 | 2007-05-21 | 2007-05-21 | 241923 | 130000 |  |  | 100% | 69 | 69 | 0.1 | 3x1-4/0 ACSR "Penguin" | Single Pole | Varies | 0.1 | 0 | 0 | 25.101(C)(5)(B) |  | 130000 | 0 | 130000 |  |  | 130000 | 0 | 0
1003538 | Rim Rock-to-Goat Creek TL Add | Kerr County | New 138 kV transmisison line, single circuit between the existing Rim Rock Substation and the proposed Goat Creek Substation and double circuit between the proposed Goat Creek Substation and the existing Harper Road to Ingram transmission line. | 2009-06-01 | 2009-12-31 |  | 11740000 |  |  |  | 0% | 0 | 138 | 9 | 3x1 & 6x1-336 ACSR "Linnet" | Single Pole & Lattice Tower | 0 | 0 | Varies, 60-130 | 8 | CCN Docket #33844 | Filed at the PUC on 2/20/07. | 11740000 | 0 | 11740000 |  |  | 11740000 | 0 | 0
1006620 1006621 1006622 1007498 1008225 1008226 | Clear Spring/Zorn-to-Hutto TL Add | Guadalupe, Caldwell, Travis and Williamson counties, alternate routes include Hays County; municipalities potentially affected include Hutto, Pflugerville, Austin, Mustang Ridge, Niederwald, Lockhart and Martindale | New 345 kV double-circuit transmission line; Clear Springs/Zorn to Gilleland Creek to Hutto | 2010-03-01 | 2011-08-31 |  | 151500000 |  |  |  | 0% | 0 | 345 | 170 | 6x2-959 ACSS/TW "Suwannee" | Lattice Towers & Other | 0 | 0 | Varies, 100-160 | 85 | CCN Docket #33978 | Filed at the PUC on 3/20/07 | 151500000 | 0 | 151500000 |  |  | 151500000 | 0 | 0
1008610 | Sandy Creek-to-Pittsburg T515 Add | Llano County | Overhaul existing transmission line | 2007-03-19 | 2007-05-18 | 2007-05-18 | 278500 | 278500 |  |  | 100% |  | 138 | 18.9 | 3x1-795 Drake | H-Frame | 100 | 18.9 | 0 | 0 | na (Overhaul) |  | 278500 | 0 | 278500 |  |  | 278500 | 0 | 0
1008508 | Lampasas-to-Adamsville-to-Evant TL Add | Lampasas and Coryell counties | Reconductor the portion of the existing 138 kV transmission line T-128 connecting the Lampasas, Adamsville, and Evant substations (approximately 26 miles) from 4/0 ACSR (84 MVA) to 795 ACSR (220 MVA). | 2007-10-01 | 2008-03-31 |  | 7830000 |  |  |  | 0% | 138 | 138 | 26 | 3 x 1-795 26/7 ACSR "Drake" | H-Frames | Varies; 100', CL | 26 | 0 | 0 | 25.101(C)(5)(B) |  | 7830000 | 0 | 7830000 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 | 5578000 |  | #N/A | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 | 24267000 |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A |  | 1005709
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A |  | 745822
[23 empty] | 0 | 0 | 0 | 5578000 |  | #N/A | #N/A | #N/A |  | 259887 | Difference
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[28 empty] | #N/A | #N/A | #N/A
[28 empty] | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | Actual Cost of Projects Completed This Month (Will Not Appear on Next Month Report): | Estimated Cost of Projects Completed This Month: | Estimated Cost of Projects Remaining Active This Month: | Total Estimated Cost of Projects Appearing in This Report:
[23 empty] | 0 | 0 | 246676511 | 246676511
[24 empty] | 0 | 17 | 17 | Project Count
[24 empty] | Completed | Active | Total
Note on H1: aboling: Please enter only a single integer, if possible.
Note on H15: Allen Steven Boling: $ 11,740,000 T Line; $5,578,000 Station
Note on H16: Allen Steven Boling: $ 151,500,000 T Line; $ 24,267,000 Station
Note on H25: Allen Steven Boling: $ 11,740,000 T Line; $5,578,000 Station
Note on H26: Allen Steven Boling: $ 151,500,000 T Line; $ 24,267,000 Station
Note on H36: Allen Steven Boling: $ 11,740,000 T Line; $5,578,000 Station
Note on I1: aboling: Please enter only a single integer, if possible.
Note on M1: aboling: If applicable.
Note on N1: aboling: If applicable.

## MVEC
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost | Final Estimated Project Cost | Final Actual Project Cost | % Variance | Percent Complete | Existing Voltage | Upgraded or New Voltage | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS | Estimated OR Actual Project Cost (SUBSTATION) |  | Last Month: | Current minus last month: | Cumulative Sum
801145 | North Edinburg to West Edinburg 138kV Line Rebuild and Second Circuit | Hidalgo | 9.1 Miles 138kv Transmission Line | 2007-02-19 | 2007-07-05 | 2007-07-06 | 2600000 |  |  |  | 100% | 138 |  | 9.1 | 795 ACSS | Single pole - concrete pole | 25 | 5.5 |  |  | 29225 | Construction Complete | 2600000 | 0 | 2600000 |  |  | 2600000 | 0 | 0
1972336 | Kenaf Plant | Willacy | 6.5 Miles 138kv Transmission Line | Delayed - May not be built | Delayed - May not be built |  | 1550000 |  |  |  | 0% |  |  | 6.5 | 795 ACSR | Single pole - concrete pole with steel davit arms |  |  | 25 | 0.68182 | 19577 | Project inactive and closed. | 1550000 | 0 | 1550000 |  |  | 1550000 | 0 | 0
50000 | FM 106 Relocation | Cameron | TXDOT Project-Relocate 1.8 Miles 138kv Transmission Line further into easement- 5-10 feet | 14/11/05 | 20/01/06 |  | 1000000 | 1000000 |  |  | 100% | 138 |  | 1.8 | 559 AAAC | Single pole - concrete pole | 26 | 1.8 | 28 | 1.7932 | 25.101(c)(5)(F) | Project complete. Awaiting final costs. Landowner consent obtained pursuant to SubR 25.101(c)(5)(F) | 1000000 | 0 | 1000000 |  |  | 1000000 | 0 | 0
50001 | Doedyns to Gandy- New 138kV Line | Hidalgo | 10.67 Miles 138kv Transmission Line | 2007-01-08 | 31/12/07 |  | 7137500 | 7109500 |  |  | 0% | 138 |  | 10.67 | 795 ACSS | Single pole - concrete pole |  |  | 50 | 12 | 32775 | CCN Approved, Substation Cost:$3,562,000 | 7109500 | 0 | 7109500 |  |  | 7109500 | 0 | 0
50002 | West Edinburg to Palmhurst 138kV Line Rebuild | Hidalgo | 3.5 Miles 138kv Transmission Line | 15/09/07 | 31/12/07 |  | 1575000 |  |  |  | 0% | 138 |  | 3.5 | 795 ACSS | Single pole - concrete pole | 25 | 3.5 |  |  | 25.101(c)(5)(B) | Upgrading conductor from 559 AAAC-795ACSS | 1575000 | 0 | 1575000 |  |  | 1575000 | 0 | 0
50003 | Palmhurst to Merett 138kV Line Rebuild | Hidalgo | 4.2 Miles 138kv Transmission Line | 2008-01-02 | 2008-01-04 |  | 2205000 |  |  |  | 0% | 138 |  | 4.2 | 795 ACSS | Single pole - concrete pole | 25 | 4.2 |  |  | 25.101(c)(5)(B) | Upgrading conductor from 559 AAAC-795ACSS | 2205000 | 0 | 2205000 |  |  | 2205000 | 0 | 0
50004 | Merett to Pharr 138kV Line Rebuild | Hidalgo | 1.8 Miles 138kv Transmission Line | 2008-01-04 | 31/05/08 |  | 945000 |  |  |  | 0% | 138 |  | 1.8 | 795 ACSS | Single pole - concrete pole | 25 | 1.87 |  |  | 25.101(c)(5)(B) | Upgrading conductor from 559 AAAC-795ACSS | 945000 | 0 | 945000 |  |  | 945000 | 0 | 0
7137500
1 new project
[23 empty] | Actual Cost of Projects Completed This Month (Will Not Appear on Next Month Report): | Estimated Cost of Projects Completed This Month: | Estimated Cost of Projects Remaining Active This Month: | Total Estimated Cost of Projects Appearing in This Report:
[23 empty] | 0 | 0 | 16984500 | 16984500
[24 empty] | 0 | 7 | 7 | Project Count
[24 empty] | Completed | Active | Total
Note on H17: Allen Steven Boling: MVEC revised the cost ($6.6 MM) in the original application to $7.137500 MM in the Amended Application. Following the initial entry of $6.6 MM on the first report (T-Line only), MVEC entered $7.109,500 as the NEW Initial Estimated Project Cost. However, this would correctly be the cost in the Amedned Application, and not the new cost after routing adjustments had been made as a result of settlement. STAFF HAS THEREFORE CHANGED THE COST BACK TO $7.137500 AS STATED IN THE AMENDED APPLICATION.

## PEC
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost (Total) | Final Estimated Project Cost (Total) | Final Actual Project Cost (Total) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS | Estimated OR Actual Project Cost (SUBSTATION) |  | Last Month: | Current minus last month: | Cumulative Sum
02-WO8784 | BUDA TO LEHIGH REBUILD | BUDA,HAYS COUNTY | UPGRADE THE 69KV LINE TO 69/138KV FROM BUDA SUBSTATION TO THE NEW LEHIGH SUBSTATION | 2007-03-15 | NA | NA | 2270000 | 2800000 |  |  | 75% | 69 | 69, 138 | 7.00 mi | 795 ACSR DRAKE, SINGLE AND BUNDLE | SINGLE POLE, STEEL OR CONCRETE | 40, 60, 80 | 3.5 | 150 | 0.057 | 25.101(C)(5)(B), 25.101(C)(5)(C) |  | 2800000 | 0 | 2800000 |  |  | 2800000 | 0 | 0
02-WO8776 | LEHIGH TO KYLE REBUILD | KYLE, HAYS COUNTY | UPGRADE THE 69KV LINE TO 138KV FROM THE NEW LEHIGH SUBSTATION TO THE KYLE SUBSTATION | 2007-08-01 | NA | NA | 4035000 |  |  |  | 0% | 69 | 138 | 5.80 mi | 795 ACSR DRAKE, BUNDLE | SINGLE POLE, STEEL OR CONCRETE | 20 - 60 | 5.8 | NA | NA | 25.101(C)(5)(B) |  | 4035000 | 0 | 4035000 |  |  | 4035000 | 0 | 0
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | Actual Cost of Projects Completed This Month (Will Not Appear on Next Month Report): | Estimated Cost of Projects Completed This Month: | Estimated Cost of Projects Remaining Active This Month: | Total Estimated Cost of Projects Appearing in This Report:
[23 empty] | 0 | 0 | 6835000 | 6835000
[24 empty] | 0 | 2 | 2 | Project Count
[24 empty] | Completed | Active | Total
Note on H1: aboling: Please enter only a single integer, if possible.
Note on I1: aboling: Please enter only a single integer, if possible.
Note on M1: aboling: If applicable.
Note on N1: aboling: If applicable.

## SPS
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost ($) | Final Estimated Project Cost ($) | Final Actual Project Cost ($) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS | Estimated OR Actual Project Cost (SUBSTATION) |  | Last Month: | Current minus last month: | Cumulative Sum
10632305, 10761041, 10772756, 10772728 | Amarillo South to Spring Draw 115 kV project | Randall County, Texas | Aproximately 6 miles of new 115 kV transmission line from Amarillo South Interchange to a new 25 MVA distribution substation to be named Spring Draw, with a breaker terminal at Amarillo South Interchange | 2008-02-01 | 2008-06-01 |  | 5713557 |  |  |  | 20% |  | 115 | 6 | 397.5 MCM ACSR | Single-Pole Steel | NA | NA | 60 | 6 | 33602 |  | 5713557 | 0 | 5713557 |  |  | 5713557 | 0 | 0
10458573, 10497800, 10497813 | Cox Interchange to Floyd County Interchange 115 kV Transmission Project | Floyd & Hale County, Texas | Approximately 20 miles of new 115 kV transmission line from Cox Interchange to Floyd County Interchange, with a breaker terminal at Cox Interchange | 2007-11-01 | 2008-06-01 |  | 9898838 |  |  |  | 25% |  | 115 | 18.6 to 21.2 | 397.5 MCM ACSR | Single-Pole Steel or Concrete | 30 | 18.6 | 70 | 18.6 to 21.2 | 33456 |  | 9898838 | 0 | 9898838 |  |  | 9898838 | 0 | 0
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[20 empty] | 0 |  |  | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[20 empty] | 0 |  |  | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[20 empty] | 0 |  |  | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[20 empty] | 0 |  |  | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
0
123
[23 empty] | Actual Cost of Projects Completed This Month (Will Not Appear on Next Month Report): | Estimated Cost of Projects Completed This Month: | Estimated Cost of Projects Remaining Active This Month: | Total Estimated Cost of Projects Appearing in This Report:
[23 empty] | 0 | 0 | 15612395 | 15612395
[24 empty] | 0 | 2 | 2 | Project Count
[24 empty] | Completed | Active | Total
Note on H1: aboling: Please enter only a single integer, if possible.
Note on I1: aboling: Please enter only a single integer, if possible.
Note on M1: aboling: If applicable.
Note on N1: aboling: If applicable.

## STEC
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost (Total) | Final Estimated Project Cost (Total) | Final Actual Project Cost (Total) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS | Estimated OR Actual Project Cost (SUBSTATION) | sort | Last Month: | Current minus last month: | Cumulative Sum
700.2393 8002392 | Nursery Breakers | Victoria | Install 2 69 kV Breakers and Comm. | 12/2000 | 9/2006 |  | 400000 | 400000 |  |  | 100% | 69 | [8 empty] | 25.83(a)(3) | Waiting on accounting for close out. | 400000 | 0 | 400000 |  | 1 | 400000 | 0 | 0
705.2026 | Red Bluff 138/12 kV Substation | Jackson | Build 138/12 kV Substation | 7/2005 | 9/2006 |  | 1477000 |  |  |  | 100% | 138 | [8 empty] | 25.101 (c)(2) | Waiting on accounting to close out. | 1477000 | 0 | 1477000 |  | 2 | 1477000 | 0 | 0
704.2056 | Verdi 69/12 kV Substation | Wilson | Build 69/12 kV Substation | 7/2005 | 12/2007 |  | 330000 |  |  |  | 16% | 69 | [8 empty] | 25.101 (c)(2) | On hold until after summer load analysis. | 330000 | 0 | 330000 |  | 3 | 330000 | 0 | 0
705.1150, 705.6148, 702.2151 | Clay West 69/12 kV Substation | Live Oak | Build 69/12 kV Substation | 2007-02-01 | 7/2007 | 2007-07-10 | 390000 |  |  |  | 100% | 69 | [8 empty] | 25.101 (c)(2) | Waiting on accounting for close out. | 390000 | 0 | 390000 |  | 4 | 390000 | 0 | 0
705.2194 | Hilje 69/12 kV Substation | Wharton | Build 69/12 kV Substation | 11/2005 | 9/2007 |  | 330000 |  |  |  | 15% | 69 | [8 empty] | 25.101 (c)(2) | Pad is finished, Fence is complete, Foundation work has started. | 330000 | 0 | 330000 |  | 5 | 330000 | 0 | 0
706.4067, 706.1069 | Botines 138/24 kV Substation | Webb | Build 138/24 kV Substation | 2006-07-01 | 2007-12-01 |  | 1480000 |  |  |  | 7% |  | 138 | [7 empty] | 25.101 (c)(2) | Site has been surveyed | 1480000 | 0 | 1480000 |  | 6
706-2068 | Botines 138 kV Transmission Line | Webb | Build 138 kV Transmissin Line to Botines Sub from AEP Laredo Switching Station | 2006-07-01 | 2007-12-01 |  | 1640000 |  |  |  | 4% |  | 138 | 0.9 | Single 795 ACSR | Wood or concrete pole |  |  | 80 | 0.9 | 25.101(c)(5)(A)(I) | Survey of easement has been completed. Easements have not been transferred as yet. | 1640000 | 0 | 1640000 |  | 7
705.203 | San Miguel to Lobo 345 kV Line | Atascosa, LaSalle, McMullen, Webb | Build 345 kV Line from San Miguel switching station to new Lobo switching station | 2/2007 | 4/2010 | 4/30/2010 | 48015600 |  |  |  | 16% |  |  | 42.4 | Two 1590 kcmil ACSR, bundle | Steel Monopole |  |  | 150 | 42.6 | 33033 | Engineering has begun. Coordination meeting has been held. | 48015600 | 0 | 48015600 |  | 8 | 48015600 | 0 | 0
799.2089, 799.2087, 899.2088 | Pt. O'Connor to Union Carbide 69 kV Line | Calhoun | Build 69 kV line to Loop Pt. O'Connor and Seadrift Substations | 1/2007 | 08/2007 |  | 7440812 |  |  |  | 21% |  | 69 | 23.96 | Single 795 ACSR | Concrete pole | 50 | 4.22 | 50 | 19.74 | 32406 | Coordination meeting has been held. Engineering has begun. Easement Acquisition has started. | 7440812 | 0 | 7440812 |  | 9 | 7440812 | 0 | 0
707.222 | Palo Duro Substation | Frio | Build 138/12.kV Substation | 7/2007 | 12/2008 |  | 2200000 |  |  |  | 1% |  | 138 | [7 empty] | 25.101( c )(2) | Negotiation of site | 2200000 | 0 | 2200000 |  | 10 | 2200000 | 0 | 0
707.2219 | Palo Duro to Dilley 138 kV Line | Frio | Build 69 kV & 138 kV double circuit line existing Dilley 138 kV Sub to new Palo Duro Sub | 7/2007 | 12/2008 |  | 4800000 |  |  |  | 1% |  | 138 | 13 | Single 795 ACSR (new) and single #4/0 ACSR (old) | Concrete pole | 40 | 13 | 100 | 13 | 25.101( c ) 5( C ) | Identifying landowners | 4800000 | 0 | 4800000 |  | 11 | 4800000 | 0 | 0
[23 empty] | 0 | 0 | 0 |  | 12 | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  | 13 | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  | 14 | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  | 15 | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  | 16 | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  | 17 | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  | 18 | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  | 19 | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  | 20 | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  | 21 | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[6 empty] | 0 | 0 | [15 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | Actual Cost of Projects Completed This Month (Will Not Appear on Next Month Report): | Estimated Cost of Projects Completed This Month: | Estimated Cost of Projects Remaining Active This Month: | Total Estimated Cost of Projects Appearing in This Report:
[23 empty] | 0 | 0 | 68503412 | 68503412
[24 empty] | 0 | 11 | 11 | Project Count
[24 empty] | Completed | Active | Total
Note on H1: aboling: Please enter only a single integer, if possible.
Note on I1: aboling: Please enter only a single integer, if possible.
Note on M1: aboling: If applicable.
Note on N1: aboling: If applicable.
Note on AD7: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AD8: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AE7: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AE8: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AF7: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AF8: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.

## SULP
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost (Total) | Final Estimated Project Cost (Total) | Final Actual Project Cost (Total) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS | Estimated OR Actual Project Cost (SUBSTATION) |  | Last Month: | Current minus last month: | Cumulative Sum
PR.04.05067.CAP | Sharyland HVDC Interconnect | Hidalgo County | Install 150 MVA back to back HVDC interconnection with CFE at SU's Railroad Substation. | 2005-04-01 | 2007-07-31 |  | 39000000 |  |  |  | 88 | na | 138 kV | 0.8 | 795 acss single conductor | Concrete or Steel Poles | na | na | 80 | 0.8 | 28834 |  | 39000000 | 0 | 39000000 |  |  | 39000000 | 0 | 0
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[25 empty] | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | Actual Cost of Projects Completed This Month (Will Not Appear on Next Month Report): | Estimated Cost of Projects Completed This Month: | Estimated Cost of Projects Remaining Active This Month: | Total Estimated Cost of Projects Appearing in This Report:
[23 empty] | 0 | 0 | 39000000 | 39000000
[24 empty] | 0 | 1 | 1 | Project Count
[24 empty] | Completed | Active | Total
Note on H1: aboling: Please enter only a single integer, if possible.
Note on I1: aboling: Please enter only a single integer, if possible.
Note on M1: aboling: If applicable.
Note on N1: aboling: If applicable.

## SWEPCO
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost (Total) | Final Estimated Project Cost (Total) | Final Actual Project Cost (Total) | % Variance | Percent Complete | Existing Voltage | Upgraded or New Voltage | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS | Estimated OR Actual Project Cost (SUBSTATION) |  | Last Month: | Current minus last month: | Cumulative Sum
40030820 | Winnsboro to N. Mineola | Wood | Construct approximately 25 miles of new 138kV transmission line using single pole with davit arm construction. | 2007-01-08 | 2007-12-31 | na | 9963000 | 17744565 |  |  | 70 | na | 138 | 25 | 1590 ACSR with Static | single pole steel or concrete with davit arms | na | na | 100 | 25 | 30128 & 31427 | Docket No. 31427 approved Preferred Route 9/8/05. | 17744565 | 0 | 17744565 |  |  | 17744565 | 0 | 0
TP-2006-130 | NW Texarkana to Bann Rebuild and Reconductor | Bowie | Reconductor and rebuild approximately 2.7 miles of the existing 4.3-mile 138KV transmisison line using single pole davit arm construction | 2007-11-15 | 2008-05-01 |  |  | 3344000 |  |  |  | 138 | 138 | 2.7 | 1590 ACSR with Static | single pole steel or concrete with davit arms | 100 | 2.7 | 0 | 0 | SUB.Rule 25.101 (c) (5) (B) |  | 3344000 | 0 | 3344000 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | Actual Cost of Projects Completed This Month (Will Not Appear on Next Month Report): | Estimated Cost of Projects Completed This Month: | Estimated Cost of Projects Remaining Active This Month: | Total Estimated Cost of Projects Appearing in This Report:
[23 empty] | 0 | 0 | 21088565 | 21088565
[24 empty] | 0 | 2 | 2 | Project Count
[24 empty] | Completed | Active | Total
Note on H1: aboling: Please enter only a single integer, if possible.
Note on I1: aboling: Please enter only a single integer, if possible.
Note on M1: aboling: If applicable.
Note on N1: aboling: If applicable.

## TNMP
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost (Total) | Final Estimated Project Cost (Total) | Final Actual Project Cost (Total) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS | Estimated OR Actual Project Cost (SUBSTATION) | REQUESTED ADDITIONAL INFORMATION | Last Month: | Current minus last month: | Cumulative Sum
GCEC26510 | Freeway Park to Dickinson 138kv line rebuild | Texas City, Texas | Rebuild existing 138kv line to account for load growth. | 2006-10-31 | 2007-04-30 | 2007-05-01 | 5800000 | 3400000 |  |  | 100% | 138KV | 138KV | 6.17 | 636 ACSS | Concrete | 35-100 | 6.17 | na | na | Rule 25.83(c)(3), 25.101(C)(5) | Construction is complete. Awaiting final contractor charges. | 3400000 | 0 | 3400000 |  |  | 3400000 | 0 | 0
NTE07507 | County Road 101 | Reeves County, Texas | Build radial 138 kV line to serve Enterprise Products Operating L.P. | 2007-07-23 | 2007-11-01 |  | 722000 |  |  |  | 0% | 138 | 138 | 1.23 | 477 ACSR | Wooden H-Frame | na | na | 100 | 1.23 | Docket 34294 | Awaiting PUCT approval | 722000 | 0 | 722000 |  |  | 722000 | 0 | 0
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[28 empty] | #N/A | #N/A | #N/A
[23 empty] | Actual Cost of Projects Completed This Month (Will Not Appear on Next Month Report): | Estimated Cost of Projects Completed This Month: | Estimated Cost of Projects Remaining Active This Month: | Total Estimated Cost of Projects Appearing in This Report:
[23 empty] | 0 | 0 | 4122000 | 4122000
[24 empty] | 0 | 2 | 2 | Project Count
[24 empty] | Completed | Active | Total
Note on H1: aboling: Please enter only a single integer, if possible.
Note on I1: aboling: Please enter only a single integer, if possible.
Note on M1: aboling: If applicable.
Note on N1: aboling: If applicable.

## TXU
Utility Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | InitialEstimatedProjectCost | FinalEstimatedProjectCost | FinalActualProjectCost | % Variance | Percent Complete | Existing Voltage | Upgraded or New Voltage | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS | Estimated OR Actual Project Cost (SUBSTATION) |  | Sort | Last Month: | Current minus last month: | Cumulative Sum
00T64047 WB | North Herty-East Lufkin 138 kV: Reconductor Project | City of Lufkin, Angelina County | Reconductor 138 kV circuit from North Herty Switch Station to East Lufkin Substation with 1590 kcmil ACSR. Replace steel poles with hybrid concrete/steel poles. Wood H-frame portion will be rebuilt with single pole concrete construction. Steel tower portion of the line will be analyzed for the addition of a second circuit | 2008-03-01 | 2008-05-15 |  | 2498000 | 2498000 |  |  | 0 | 138 | na | 9.5 | 1590 kcmil ACSR | Concrete Poles | 100 | 9.5 | na | na | 25.101(c)(5)(B) | Project has been deferred. | 2498000 | 0 | 2498000 |  |  | 1 | 2498000 | 0 | 0
04T62069 JB/EH | Euless - Bedford 138kV: Rebuild | City of Keller, Tarrant County | Rebuild 3.0 miles of existing double circuit 1033.5 kcmil ACSR conductor on steel poles and steel towers with bundled 1033.5 kcmil ACSR on steel poles. | 2006-05-17 | 2007-12-15 |  | 1350000 | 1350000 |  |  | 95 | 138 | na | 6 | 1926.9 kcmil ACSS/TW | Steel Poles | 100 | 3 | na | na | 25.101(c)(5)(B) |  | 1350000 | 0 | 1350000 |  |  | 2 | 1350000 | 0 | 0
05T62155 DRC | Alvarado-Hillsboro 69 kV Line: Replace Structures 132 and 133 | Hill County | Remove two existing 69 kV steel towers and install two 138 kV single poles due to severe erosion at Structure 133 | 2007-09-01 | 2007-09-30 |  | 90000 | 90000 |  |  | 0 | 69 | na | 0.4 | #1 Copper | Steel or Concrete Poles | 100 | 0.4 | na | na | 25.101(c)(5)(B) |  | 90000 | 0 | 90000 |  |  | 3 | 90000 | 0 | 0
05T65181 MH | Payne - Denison Dam 138 kV Line: Upgrade Switches with 2000A Switches | Grayson County | Replace one tap and two switch structures and replace existing 1200 A switches with 2000 A switches. | 2007-02-26 | 2007-03-03 | 2007-03-03 | 225000 | 225000 |  |  | 100 | 138 | N/A | 0.1 | 795 kcmil ACSR and 336.4 kcmil ACSR | Wood H-Frame | 100 | 0.1 | na | na | 25.101(c)(5)(B) | Final costs accumulating. | 225000 | 0 | 225000 |  |  | 4 | 225000 | 0 | 0
05T62145 JB/EH | Bedford - Colleyville Tap 138 kV: Rebuild | City of Fort Worth, Tarrant County | Rebuild 3.4 miles of existing double circuit 1033 kcmil ACSR conductor on steel towers and steel poles with 1926.9 kcmil ACSS/TW on steel poles. | 2006-06-19 | 2007-02-01 | 2006-11-29 | 5362000 | 5362000 |  |  | 100 | 138 | na | 6.8 | 1926.9 kcmil ACSS/TW | Steel Poles | 100 | 3.4 | na | na | 25.101(c)(5)(B) | Final costs accumulating. | 5362000 | 0 | 5362000 |  |  | 5 | 5362000 | 0 | 0
05T62149 JB/EH | Colleyville Tap - Keller South (BEC) 138 kV: Rebuild | City of Fort Worth, Tarrant County | Rebuild 3.0 miles of existing double circuit 1033 kcmil ACSR conductor on steel towers and steel poles with 1926.9 kcmil ACSS/TW on steel poles. | 2006-06-19 | 2007-09-01 |  | 4132000 | 4132000 |  |  | 95 | 138 | na | 6 | 1926.9 kcmil ACSS/TW | Steel Poles | 100 | 3 | na | na | 25.101(c)(5)(B) |  | 4132000 | 0 | 4132000 |  |  | 6 | 4132000 | 0 | 0
05T62150 JB/EH | Keller South (BEC) - Keller Magnolia Tap 138 kV: Rebuild | City of Fort Worth, Tarrant County | Rebuild 2.3 miles of existing double circuit 1033 kcmil ACSR conductor on steel towers and steel poles with 1926.9 kcmil ACSS/TW on steel poles. | 2006-06-19 | 2007-10-01 |  | 2989000 | 2989000 |  |  | 95 | 138 | na | 4.6 | 1926.9 kcmil ACSS/TW | Steel Poles | 100 | 2.3 | na | na | 25.101(c)(5)(B) |  | 2989000 | 0 | 2989000 |  |  | 7 | 2989000 | 0 | 0
06T61001 SEI/BW | Sulphur Springs Switch-Sulphur Springs Substation 138 kV: Relocate structure 2/7 | City of Sulphur Springs, Hopkins County | Replace and relocate existing single circuit 138 kV concrete pole structure 60' north of the present location. | 2007-10-01 | 2007-10-15 |  | 72659 | 72659 |  |  | 0 | 138 | na | 0.18466 | 1590 kcmil ACSR | Concrete Pole | 100 | 0.18466 | na | na | 25.101(c)(5)(F) | Relocation is at the request of TxDOT and is 100% reimbursable by TxDOT. | 72659 | 0 | 72659 |  |  | 8 | 72659 | 0 | 0
06T61002 SEI/BW | Liggett-Norwood 138 kV: Relocate structures 1/5, 1/6, 1/7 & 1/8 | City of Irving, Dallas County | Replace and relocate existing double circuit 138 kV steel towers with steel towers. | 2007-02-07 | 2007-03-11 | 2007-03-11 | 550524 | 550524 |  |  | 100 | 138 | na | 1.14 | 959.6 kcmil ACSS | Steel Towers | 100 | 0.56629 | na | na | 25.101(c)(5)(F) | Relocation is at the request of TxDOT and is 100% reimbursable by TxDOT. Final costs accumulating. | 550524 | 0 | 550524 |  |  | 9 | 550524 | 0 | 0
05T64193 JE/BW | Temple - Troy 69 kV: Rebuild | City of Temple, Bell County | Rebuild 6.1 miles of the 9.3 mile Temple-Troy 69 kV line section with double circuit structures and with one circuit in place for operation at elevated temperature | 2007-01-22 | 2007-05-24 | 2007-05-24 | 4200000 | 4200000 |  |  | 100 | 69 | na | 6.1 | 795 kcmil ACSR | Steel Pole | Varies | 6.1 | na | na | 25.101(c)(5)(B) | Line work complete. Switches at Troy will be replaced in the fall completing the construction. Final costs accumulating. | 4200000 | 0 | 4200000 |  |  | 10 | 4200000 | 0 | 0
05T65310 JO/SEI | Payne-Gainesville 138kV: Connect GCEC Whitesboro SE Substation | City of Whitesboro, Grayson County | This project consists of installing line sectionalizing switches in the Whitesboro - Payne 138 kV Transmission Line to provide a point of interconnection (POI) for Grayson - Collin Electric Cooperative (GCEC) adjacent to the Oncor Electric Delivery's Whitesboro Southeast Substation | 2007-10-01 | 2007-12-15 |  | 174943 | 174943 |  |  | 0 | 138 | na | na | 1233 kcmil ACSS/TW | Steel H-Frame | na | na | na | na | 25.101(c)(5)(A) |  | 174943 | 0 | 174943 |  |  | 11 | 174943 | 0 | 0
06T64021 MK/BW | Temple-Lampasas 138 kV: Rebuild the Belton to Nolanville Section | City of Belton, Bell County | This project consists of rebuilding 5.1 miles between Belton and Nolanville with 1590 kcmil ACSR on new double circuit steel pole structures with one circuit in place. | 2006-02-16 | 2007-03-23 | 2007-03-23 | 2165692 | 3000000 |  |  | 100 | 138 | na | 5.1 | 1590 kcmil ACSR | Steel Pole | na | 5.1 | na | na | 25.101(c)(5)(B) | Final costs accumulating. | 3000000 | 0 | 3000000 |  |  | 12 | 3000000 | 0 | 0
06T64022 MK/BW | Belton-Ft. Hood 138 kV Line: Rebuild the Belton-South Harker Heights section | City of Belton and City of Harker Heights, Bell County | This project consists of rebuilding 11.9 miles between Belton and South Harker Heights with 1590 kcmil ACSR on new double circuit steel pole structures with one circuit in place. | 2007-03-29 | 2007-12-15 |  | 6024455 | 6024455 |  |  | 59 | 138 | na | 11.9 | 1590 kcmil ACSR | Steel Pole | na | 11.9 | na | na | 25.101(c)(5)(B) |  | 6024455 | 0 | 6024455 |  |  | 13 | 6024455 | 0 | 0
05T61026 MK/BW | Balch Springs 138 kV: Relocate Structure 2/7 | City of Mesquite, Dallas County | Replace and relocate existing double circuit wood pole structure with a concrete H-frame. | 2007-10-01 | 2007-11-01 |  | 191497 | 191497 |  |  | 0 | 138 | na | 0.7 | 795 kcmil ACSR | Concrete Pole | 100 | na | na | na | 25.101(c)(5)(F) | Relocation is at the request of TxDOT and is 100% reimbursable by TxDOT. | 191497 | 0 | 191497 |  |  | 14 | 191497 | 0 | 0
04T65177 ME/MM | Venus - Midlothian TXI 138 kV: Elevated Temperature | City of Midlothian, Ellis County | Raise selected existing towers to allow the line to be operated at an elevated temperature. | 2007-04-16 | 2007-06-27 | 2007-06-27 | 620000 | 620000 |  |  | 100 | 138 | na | 6.4 | 795 kcmil ACSR | Steel Towers | 100 | 3.2 | na | na | 25.101(c)(5)(B) | Final costs accumulating. | 620000 | 0 | 620000 |  |  | 15 | 620000 | 0 | 0
06T65018 BM/WB | Forney - Lake Hubbard 138 kV: Raise Span for High Temp Operation | Kaufman County | The project scope is to upgrade the 7.5-mile Forney – Lake Hubbard 138 kV Transmission Line for high temperature operation. This work will be done in two phases. The first phase will include replacing existing dead-ends with new compression dead-ends and installing one new concrete pole and the second phase will include replacing two existing 1200 Amp switches and switch structures. New 'H" frame type switch structures will also be installed. No new ROW will be required. | 2006-04-06 | 2007-12-15 |  | 412179 | 412179 |  |  | 70 | 138 | na | 7.58 | 795 kcmil ACSR 1431 kcmil ACSR | Steel Towers, Steel Poles and Concrete Poles | 175 | 7.58 | na | na | 25.101(c)(5)(B) | The Final Estimated Project Cost for this project will be updated when cost information for the second phase of the project becomes available later this year. | 412179 | 0 | 412179 |  |  | 16 | 412179 | 0 | 0
05T65379 BJP/BW | Parkdale-Medill St. 138 kV:DART SE-2 Relocation | City of Dallas, Dallas County | This project consists of relocating seven existing steel tower structures with seven self-supporting steel poles in order to accommodate DART's proposed SE-2 railway project. | 2007-06-01 | 2007-07-30 | 2007-07-30 | 700402 | 700402 |  |  | 100 | 138 | na | 1 | 795 kcmil ACSR | Steel Poles | na | na | na | 0.5 | 25.101(c)(5)(F) | The existing transmission line is in DART right-of-way and will remain in DART right-of-way after the relocation. Final costs accumulating. | 700402 | 0 | 700402 |  |  | 17 | 700402 | 0 | 0
07T64028 MK/BW | Lake Creek-West Waco 138 kV: Install New Northwest Robinson Substation | City of Robinson, McLennan County | This project consists of replacing one existing wood H-frame and transferring conductors and shield wires in order to accommodate the installation of the Northwest Robinson Substation. | 2008-03-19 | 2008-04-01 |  | 50000 | 50000 |  |  | 0 | 138 | na | na | 336.4 kcmil ACSR Bundled | Concrete H-Frame | 100 | na | na | na | 25.101(c)(5)(A) | Project has been deferred. | 50000 | 0 | 50000 |  |  | 18 | 50000 | 0 | 0
06T65196 JOA | Anna Switch - Anna Tap 138 kV: Provide a 138 kV Point of Interconnect for the Grayson Collin Electric Cooperative Melissa East Substation | City of Melissa, Collin County | Install one single steel pole switch structure with three sectionalizing switches in place and remove one existing steel tower. | 2007-01-08 | 2007-01-20 | 2007-01-20 | 555006 | 555006 |  |  | 100 | 138 | na | 0.01 | 795 kcmil ACSR | Steel Pole | 100 | 0.01 | na | na | 25.101(c)(5)(A) | Final costs accumulating. | 555006 | 0 | 555006 |  |  | 19 | 555006 | 0 | 0
06T65197 MM/BP | Parkdale-Medill 138 kV: Relocate Structure T-310 | City of Dallas, Dallas County | Relocating structure T-310 in the Parkdale-Medill 138 kV Transmission Line due to an erosion problem. | 2007-06-11 | 2007-08-05 | 2007-08-05 | 131000 | 131000 |  |  | 100 | 138 | na | 0.01 | 400 kcmil Copper | Steel Towers | 100 | 0.01 | na | na | 25.101(c)(5)(E) | Final costs accumulating. | 131000 | 0 | 131000 |  |  | 20 | 131000 | 0 | 0
06T62044 MM | Benbrook-Bowman 345 kV: Structure Reinforcement | Tarrant County, Parker County, Wise County, Jack County, Montague County and Wichita County | This project involves the installation of reinforcing kits on the existing lattice H-frame structures and the replacement of six lattice H-frame structures will full tension deadend structures. | 2007-02-01 | 2007-05-06 | 2007-05-06 | 2769070 | 2565300 |  |  | 100 | 345 | na | 93 | 795 kcmil ACSR Bundled | Lattice Steel H-frames | 150 | 93 | na | na | 25.101(c)(5)(B) | Final costs accumulating. | 2565300 | 0 | 2565300 |  |  | 21 | 2565300 | 0 | 0
06T63016 MM | Morgan Creek-Midland East 345 kV: Structure Reinforcement | Mitchell County, Howard County, Martin County, and Midland County | This project involves the installation of reinforcing kits on the existing lattice H-frame structures and the replacement of two lattice H-frame structures with full tension deadend structures. | 2006-08-16 | 2007-02-15 | 2007-02-15 | 2210206 | 1522800 |  |  | 100 | 345 | na | 71 | 795 kcmil ACSR Bundled | Lattice Steel H-frames | 150 | 71 | na | na | 25.101(c)(5)(B) | Final costs accumulating. | 1522800 | 0 | 1522800 |  |  | 22 | 1522800 | 0 | 0
06T65105 MH/BW | Allen Switch - Lavon 138 kV: Northwest Wylie Substation Line Switch Replacement Project | City of Wylie, Collin County | Replace the existing 138kV transmission line switch structure located at the Northwest Wylie Substation. | 2007-04-16 | 2007-04-27 | 2007-04-27 | 450000 | 450000 |  |  | 100 | 138 | na | na | 1926.9 kcmil ACSS/TW | Steel Pole | 150 | na | na | na | 25.101(c)(5)(B) | Final costs accumulating. | 450000 | 0 | 450000 |  |  | 23 | 450000 | 0 | 0
06T62073 DRC/EB | Venus-Sherry 345 kV: Rebuild | City of Arlington, Tarrant County | Add a second circuit of 959.6 ACSS/TW bundled conductor to the existing steel towers on the Cedar Hill - Venus 345 kV Transmission Line between the Webb Substation and the Century Tap. Remove the existing Century Tap and reconfigure to complete a 345 kV circuit between the Venus Switching Station and the Sherry Switching Station. | 2007-01-02 | 2007-04-14 | 2007-04-14 | 1330000 | 1330000 |  |  | 100 | 345 | na | 1.4 | 959.6 ACSS/TW Bundled | Steel Poles and Steel Towers | 150 | 1.4 | na | na | 25.101(c)(5)(B) | Final costs accumulating. | 1330000 | 0 | 1330000 |  |  | 24 | 1330000 | 0 | 0
06T65307 06T65308 JB/TW | Royse Switching Station - Terrell Switching Station 69kV/138kV Rebuild | City of Terrell and City of Royse City, Rockwall County, Hunt County and Kaufman County | Rebuild 16.0 miles of existing single circuit single 4/0 ACSR conductor on steel poles with single 1590 kcmil ACSR on steel poles. This new construction will be insulated for 138 kV. One circuit will operate at 69 kV and a new second circuit will operate at 138 kV. | 2006-05-30 | 2007-06-01 | 2007-06-01 | 9736464 | 10000000 |  |  | 100 | 69/138 | na | 33 | 1590 kcmil ACSR | Steel Poles | 100 | 16.5 | na | na | 25.101(c)(5)(B) | This project has been divided into two new WA's, 06T65307 and 06T65308. Final costs accumulating. | 10000000 | 0 | 10000000 |  |  | 25 | 10000000 | 0 | 0
06T61007 SEI/BW | Royse Switching Station-Terrell Substation138/69 kV: Relocate structures 18/2 and 18/3 | City of Terrell, Kaufman County | Replace H-frame bottom section and relocate existing steel pole triple circuit H-frame structures. | 2007-08-01 | 2007-10-01 |  | 376885.8 | 376885.8 |  |  | 10 | 69/138 | na | 0.60985 | 1590 kcmil ACSR | Steel H-Frame | 100 | 0.30492 | na | na | 25.101(c)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by the Texas Department of Transportation. | 376885.8 | 0 | 376885.8 |  |  | 26 | 376885.8 | 0 | 0
06T61012 SEI/BW | Gainesville-Montague 69 kV: Relocate Existing Structures 2/16 &2/17 | City of Gainesville, Cooke County | Replace single circuit, single wood pole tangent structures with single concrete pole structures. | 2007-05-18 | 2007-06-01 | 2007-06-01 | 108431 | 108431 |  |  | 100 | 69 | na | 0.15985 | #2AWG-7 HD CU | Concrete Poles | 100 | 0.15985 | na | na | 25.101(c)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by the Texas Department of Transportation. Final costs accumulating. | 108431 | 0 | 108431 |  |  | 27 | 108431 | 0 | 0
06T61009 SEI/BW | Norwood-Denton-Bowie 138 kV: Relocate Structures 2/8, 3/1, 3/2, and 3/3 | City of Irving, Dallas County | Replace double circuit lattice towers with double circuit lattice towers and double circuit steel poles with anchor bolt foundations. | 2007-11-01 | 2007-11-15 |  | 721679 | 721679 |  |  | 0 | 138 | na | 1.5765 | 1033.5 kcmil ACSR | Steel Towers and Steel Poles | 100 | 0.78826 | na | na | 25.101(c)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by the Texas Department of Transportation. This project is deferred. | 721679 | 0 | 721679 |  |  | 28 | 721679 | 0 | 0
04T64129 EH/RG | Stryker Creek-Jacksonville 138 kV: Rebuild Stryker Creek to Jacksonville | Cherokee County | Rebuild the 16 mile section of the Stryker Creek-Jacksonville 138 kV Line with 1590 kcmil ACSR conductor. | 2007-01-02 | 2007-05-31 |  | 7311000 | 7311000 |  |  | 100 | 138 | na | 6.6 | 1590 kcmil ACSR | Concrete Poles, Steel Poles and Concrete H-Frames | 100 | 6.6 | na | na | 25.101(c)(5)(B) | The Initial Estimated Project Cost was increased to reflect a change in the scope of the project. Final costs accumulating. | 7311000 | 0 | 7311000 |  |  | 29 | 7311000 | 0 | 0
06T64096 WB/RG | Temple Pecan Creek-Temple Switch 138 kV: Rebuild | City of Temple, Bell County | Rebuild the 4.4 mile Temple Pecan Creek-Temple Switch 138 kV Line with 1590 kcmil ACSR on new double circuit steel pole structures with one circuit in place. | 2007-01-08 | 2007-02-21 | 2007-02-21 | 3000000 | 3000000 |  |  | 100 | 138 | na | 4.4 | 1590 kcmil ACSR | Steel Poles | 100 | 4.4 | na | na | 25.101(c)(5)(B) | Final costs accumulating. | 3000000 | 0 | 3000000 |  |  | 30 | 3000000 | 0 | 0
06T62124 WB/RC | DeCordova-Everman 345 kV: Upgrade (345 kV Brazos River Crossing) | Hood County | Rebuild the existing double circuit 345/138 kV crossing span across the Brazos River (Lake Granbury) with single circuit 345 kV A-frame structures. | 2006-09-18 | 2007-04-04 | 2007-04-04 | 1687000 | 1687000 |  |  | 100 | 345 | na | 0.5 | 1590 kcmil SCACAR bundled | Steel Pole A-Frames | 600 | 0.5 | na | na | 25.101(c)(5)(B) | Final costs accumulating. | 1687000 | 0 | 1687000 |  |  | 31 | 1687000 | 0 | 0
06T62161 WB/RC | DeCordova-Everman 345 kV: Upgrade (138 kV Brazos River Crossing) | Hood County | Rebuild the existing double circuit 345/138 kV crossing span across the Brazos River (Lake Granbury) with single circuit A-frame structures. | 2006-09-18 | 2007-04-04 | 2007-04-04 | 1627000 | 1627000 |  |  | 100 | 138 | na | 0.5 | 1590 kcmil SCACAR bundled | Steel Pole A-Frames | 600 | 0.5 | na | na | 25.101(c)(5)(B) | Final costs accumulating. | 1627000 | 0 | 1627000 |  |  | 32 | 1627000 | 0 | 0
06T64185 TW/RC | Sandow Minerva 138 kV: Relocate 1/10A | Milam County | Replace Str. 1/10A on the Sandow Minerva 138 kV Line with two structures required as a result of the expansion of the Sandow Switch Station | 2007-01-15 | 2007-02-13 | 2007-02-13 | 96000 | 102000 |  |  | 100 | 138 | na | 0.1 | 959.6 kcmil ACSS/TW | Steel Poles | 100 | 0.1 | na | na | 25.101(c)(5)(B) | Final costs accumulating. | 102000 | 0 | 102000 |  |  | 33 | 102000 | 0 | 0
04T62108 ME/MM | Graham SES - Graham Switching Station 138 kV: Elevated Temperature | City of Graham, Young County | Replace selected existing wood H-frames with wood or concrete h-frames, and replace steel poles to allow the line to be operated at an elevated temperature. | 2007-03-01 | 2007-04-06 | 2007-04-06 | 495000 | 495000 |  |  | 100 | 138 | na | 7 | 636 kcmil ACSR | Wood H-Frames and Steel Poles | 100 | 5.5 | na | na | 25.101(c)(5)(B) | Final costs accumulating. | 495000 | 0 | 495000 |  |  | 34 | 495000 | 0 | 0
04T65181 ME/MM | Allen Switching Station - Plano Shiloh 138 kV: Elevated Temperature | City Plano, Collin County | Raise and relocate selected existing towers to allow the line to be operated at an elevated temperature. | 2007-02-19 | 2007-03-03 | 2007-03-03 | 273000 | 273000 |  |  | 100 | 138 | na | 5.5 | 1033.5 kcmil ACSR | Steel Towers | Varies 100 - 165 | 5.5 | na | na | 25.101(c)(5)(B) | Final costs accumulating. | 273000 | 0 | 273000 |  |  | 35 | 273000 | 0 | 0
04T62109 ME/MM | Handley Switching Station - Liggett 138 kV: Elevated Temperature | Fort Worth City, Richland Hills City, Hurst City and Grand Prairie City, Tarrant County and Dallas County | Raise and relocate selected existing towers and replace wood h-frames to allow the line to be operated at an elevated temperature. | 2007-02-05 | 2007-02-22 | 2007-02-22 | 453000 | 453000 |  |  | 100 | 138 | na | 17.5 | 795 kcmil ACSR | Wood H-Frames and Steel Towers | 100 | 17.5 | na | na | 25.101(c)(5)(B) | Final costs accumulating. | 453000 | 0 | 453000 |  |  | 36 | 453000 | 0 | 0
06T64146 BW/BM | Palestine-Palestine ALCOA 138 kV: Replace and Relocate | Anderson County | This project is to replace these two deteriorating wood H-frame structures with two direct embedded, concrete H-frames approximately 10' from their existing locations. The existing 1033 kcmil ACSR conductor and the double 3/8" EHS shield wire will be reused. | 2007-11-15 | 2007-11-30 |  | 151333 | 235000 |  |  | 0 | 138 | na | 0.1 | 1033.5 kcmil ACSR | Concrete H-Frames | 100 | 0.1 | na | na | 25.101(c)(5)(B) | Project has been deferred | 235000 | 0 | 235000 |  |  | 37 | 235000 | 0 | 0
06T64145 BW/BM | Jewett-Crockett-Lufkin 138 kV: Replace and Relocate | Houston County | This project is to replace these two wood H-frame structures with two direct embedded, concrete H-frames. One new concrete H-frame will be approximately 100' from the existing location in the lake and the other new concrete H-frame will be approximately 10' from it's existing location. The existing single circuit 4/0 ACSR conductor and double 3/8" EHS shield wire will be reused. | 2007-11-01 | 2007-11-15 |  | 160382 | 245000 |  |  | 0 | 138 | na | 0.1 | 4/0 ACSR | Concrete H-Frames | 100 | 0.1 | na | na | 25.101(c)(5)(B) | Project has been deferred | 245000 | 0 | 245000 |  |  | 38 | 245000 | 0 | 0
06T63050 06T63042 JM/JO | Wink - N. Andrews 138KV-Switch Replacement # 2813 - 2815 | Winkler County | This project will involve replacing two 138 kV 1200 amp type LD switches, with new 2000amp type LDS air switches for the Cheyenne tap. One existing wood H-frame type switch structure will be replaced with two new H-frame switch structures and two wood tangent H-frames will be replaced on the Wink-North Andrews 138 kV Transmission Line. Additionally one tangent wood H-frame will be replaced with a new steel H-frame on the Cheyenne Tap. | 2007-06-11 | 2007-07-31 | 2007-07-31 | 537434 | 1400000 |  |  | 100 | 138 | na | 0.32 | 795 kcmil ACSR and 556.5 kcmil ACSR | Wood H-Frames and Steel H-Frames | 50 | 0.32 | na | na | 25.101(c)(5)(B) |  | 1400000 | 0 | 1400000 |  |  | 39 | 1400000 | 0 | 0
06T42516 BM/BW | South Marlin Tap 69 kV: Replace Switches #2012 and 2013 | City of Marlin, Falls County | This project will consist of removing three 69 kV 600 amp type LD switches and replacing them with two 1200 amp 69 kV switches. Also, included in this project will be to replace the existing motor operators with new self contained motor operators. The existing switch structure will be utilized although some modification will be required on the switch platform. | 2008-02-15 | 2008-03-01 |  | 199000 | 265000 |  |  | 0 | 69 | na | 0.01 | 336.4 kcmil ACSR | Steel Tower | 50 | 0.01 | na | na | 25.101(c)(5)(B) | This project has been deferred. | 265000 | 0 | 265000 |  |  | 40 | 265000 | 0 | 0
06T64214 TW/RC | Sandow-Taylor 138 kV: Relocate 3/2 | Milam County | Relocate Structure 3/2 on the Sandow-Taylor 138 kV Transmission Line to accommodate the expansion of the Sandow Switching Station | 2007-02-20 | 2007-02-23 | 2007-02-23 | 156000 | 224000 |  |  | 100 | 138 | na | 0.1 | 1926.9 kcmil ACSS/TW | Steel Poles | 100 | 0.1 | na | na | 25.101(c)(5)(B) | Final costs accumulating. | 224000 | 0 | 224000 |  |  | 41 | 224000 | 0 | 0
05T64098 BW/JM | Marlin-Groesbeck 69 kV: Relocate for Marllin Lake | City of Marlin, Falls County | A section of the Marlin - Grosbeck 69 kV line is currently running through Old Mill Lake with three wood H-frame structures within the lake boundaries. Five existing wood H-frame structures will be removed and four new structures will be installed such that all structures will be located outside of the lake. Two of the new structures will be direct embedded, concrete H-frames and two of the structures will be anchor bolt foundation, steel H-frames. This project will include removing approximately 2100' of single circuit 336.4 kcmil ACSR conductor and replacing with approximately 2100' of 795 kcmil ACSR. Also approximately 2100' of 3/8" EHS double shield wire will be replaced with 2100' of 7/16 EHS double shield wire. | 2007-03-19 | 2007-10-30 |  | 290951 | 290951 |  |  | 70 | 69 | na | 0.3977 | 795 kcmil ACSR | Concrete H-Frames and Steel H-Frames | 50 | 0.3977 | na | na | 25.101(c)(5)(B) |  | 290951 | 0 | 290951 |  |  | 42 | 290951 | 0 | 0
06T61018 SEI/BW | Benbrook-Mistletoe 138 kV: Relocate Structures 7/4 and 7/5 | City of Fort Worth, Tarrant County | Replace double circuit steel poles with double circuit steel poles supported by anchor bolt foundations. | 2007-11-01 | 2007-11-15 |  | 261484 | 261484 |  |  | 0 | 138 | na | 0.73097 | 1926.9 kcmil ACSS /TW | Steel Poles | 100 | 0.36549 | na | na | 25.101(c)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by TxDOT. This project is deferred. | 261484 | 0 | 261484 |  |  | 43 | 261484 | 0 | 0
06T61021 SEI/BW | Malakoff-Mabank 138 kV: Relocate Structures 12/1 and 12/2 | Henderson County | Replace wood single circuit H-frames structures with concrete single circuit H-frames structures. | 2007-04-10 | 2007-04-12 | 2007-04-12 | 158277 | 158277 |  |  | 100 | 138 | na | 0.35871 | 336.4 kcmil ACSR | Concrete H-Frames | 100 | 0.35871 | na | na | 25.101(c)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by TxDOT. Final costs accumulating. | 158277 | 0 | 158277 |  |  | 44 | 158277 | 0 | 0
06T65278 JO 06T65299 JO | Watermill - West Levee 345 kV Mitigation | Dallas County | This project includes installation of additional overhead and some underground sections of ground wires. | 2007-01-08 | 2007-04-29 | 2007-04-29 | 3953042 | 5246000 |  |  | 100 | 345 | na | 9 | 740 kcmil ACAR Grounded Shield wire | Steel Poles | 100 | na | na | na | 25.101(c)(5)(B) | Final costs accumulating. | 5246000 | 0 | 5246000 |  |  | 45 | 5246000 | 0 | 0
06T65280 JO | Rockhill Substation Brazos Electric Power cooperative Point of interconnect | Collin County | Construct point of interconnection to Brazos Electric Power Cooperative Rockhill Substation in Collin County. | 2007-05-07 | 2007-05-18 | 2007-05-18 | 460000 | 460000 |  |  | 100 | 138 | na | 0.5 | 795 kcmil ACAR | Steel and Concrete Poles | 100 | na | na | na | 25.101(c)(5)(A) | Final costs accumulating. | 460000 | 0 | 460000 |  |  | 46 | 460000 | 0 | 0
06T65140 MH/BW | Denison North - Denison Tap 138 kV Line: Upgrade | City of Denison, Grayson County | Upgrade the 2.05 mile Denison North -Denison Tap 138 kV Transmission Line. Using a single conductor 795 kcmil ACSR . | 2007-03-01 | 2007-03-03 | 2007-03-03 | 593142 | 593142 |  |  | 100 | 138 | na | 2.05 | 795 kcmil ACSR | Concrete Poles | 100 | 2.05 | na | na | 25.101(c)(5)(B) | Final costs accumulating. | 593142 | 0 | 593142 |  |  | 47 | 593142 | 0 | 0
06T65253 BJP/BW | East Levee-Amelia 138 kV Line: DART NW1-B Relocation at Oaklawn | City of Dallas, Dallas County | This project consists of relocating one existing steel guy stub pole structure with one self-supporting steel guyed pole in order to accommodate DART's proposed NW1-B railway project at Oak Lawn Avenue. | 2007-07-13 | 2007-07-20 | 2007-07-20 | 220204 | 220204 |  |  | 100 | 138 | na | na | na | Steel Pole | na | na | na | na | 25.101(c)(5)(F) | The existing guy pole is in DART right-of-way and will remain in DART right-of-way after the relocation. | 220204 | 0 | 220204 |  |  | 48 | 220204 | 0 | 0
06T61029 MK/BW | E.Waco-W.Waco M&M 138kV Tap Line | City of Waco, McLennan County | This project consists of installing two single concrete poles and removing two single wood poles to increase the vertical clearance required over a new railroad spur to be constructed by a developer. | 2007-02-21 | 2007-03-02 | 2007-03-02 | 79085 | 79085 |  |  | 100 | 138 | na | 0.17 | 795 kcmil ACSR | Concrete Pole | na | na | na | na | 25.101(c)(5)(D) | This project is completely reimbursable. Final costs accumulating. | 79085 | 0 | 79085 |  |  | 49 | 79085 | 0 | 0
06T63025 DRC/EB | Midessa-Midland Airport 138 kV: Rebuild and Upgrade Capacity | Midland County | Rebuild the existing 138 kV circuit from Midessa Substation to Midland Airport Substation with 1590 kcmil ACSR, a distance of approximately 7.2 miles. Replace existing wood H-Frame structures with concrete H-Frames. | 2007-01-02 | 2007-12-15 |  | 2900000 | 3175000 |  |  | 5 | 138 | na | 7.2 | 1590 kcmil ACSR | Concrete Poles | 75 | 7.2 | na | na | 25.101(c)(5)(B) | Construction on hold pending resolution of permits. | 3175000 | 0 | 3175000 |  |  | 50 | 3175000 | 0 | 0
06T63083 DRC/EB | Odessa EHV-Odessa 138 kV: Reconductor | City of Odessa, Odessa County | Reconductor 138 kV circuit from Odessa EHV Switching Station to Odessa #2 Substation with 1590 kcmil ACSR, a distance of approximately 2.3 miles. | 2007-09-15 | 2007-12-15 |  | 350000 | 350000 |  |  | 0 | 138 | na | 2.3 | 1590 kcmil ACSR | Steel and Concrete Poles | Varies: 75/50 | 2.3 | na | na | 25.101(c)(5)(B) |  | 350000 | 0 | 350000 |  |  | 51 | 350000 | 0 | 0
06T65294 DRC/YB | Commerce Sw.-Wolfe City 138 kV: Rebuild and Upgrade Capacity | City of Commerce, City of Wolfe City, Hunt County | Rebuild the existing 138 kV circuit from Commerce Switching Station to Wolfe City Substation with 795 kcmil ACSR, a distance of approximately 12.7 miles. Replace existing wood H-Frame structures with concrete and steel poles. | 2007-01-02 | 2007-05-20 | 2007-05-20 | 3000000 | 3100000 |  |  | 100 | 138 | na | 12.7 | 795 kcmil ACSR | Concrete and Steel Poles | 100 | 12.7 | na | na | 25.101(c)(5)(B) | Final costs accumulating. | 3100000 | 0 | 3100000 |  |  | 52 | 3100000 | 0 | 0
06T61024 SEI/BW | Payne-Gainesville 69 kV: Relocate Structures 5/1, 5/2, 5/3 & 5/4 | City of Sherman, Grayson County | Replace single circuit wood H-frame structures with single circuit concrete H-frame structures. | 2007-05-21 | 2007-06-14 | 2007-06-14 | 266853 | 266853 |  |  | 100 | 69 | na | 0.47348 | 3/0 ACSR | Concrete H-frames | 100 | 0.47348 | na | na | 25.101(c)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by TxDOT. Final costs accumulating. | 266853 | 0 | 266853 |  |  | 53 | 266853 | 0 | 0
06T61023 SEI/BW | Payne-Gainesville 138 kV: Relocate Structure 5/2 | City of Sherman, Grayson County | Replace single circuit concrete H-frame structure with single circuit concrete H-frame structure. | 2007-06-18 | 2007-06-15 | 2007-06-15 | 104139 | 104139 |  |  | 100 | 138 | na | 0.17704 | 1233.6 kcmil ACSS | Concrete H-frames | 100 | 0.17704 | na | na | 25.101(c)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by TxDOT. Final costs accumulating. | 104139 | 0 | 104139 |  |  | 54 | 104139 | 0 | 0
06T61027 SEI/BW | E. Richardson-N. Mesquite 138 kV, PGBT @ Liberty Grove Rd.: Relocate Structures 14/3 & 14/4 | City of Rowlett, Dallas County | Relocate existing single circuit steel poles to new anchor bolt foundations. | 2007-10-01 | 2007-10-20 |  | 190920 | 190920 |  |  | 0 | 138 | na | 0.28277 | 1033.5 kcmil ACSR | Steel poles | 100 | 0.28277 | na | na | 25.101(c)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by TxDOT. This project is deferred. | 190920 | 0 | 190920 |  |  | 55 | 190920 | 0 | 0
06T61028 SEI/BW | E. Richardson-N. Mesquite 138 kV, PGBT @ Miller Rd.: Relocate Structures 15/8, 15/9, 15/10 & 16/1 | City of Rowlett, Dallas County | Replace single circuit steel tangent & deadend poles with new single circuit tangent & deadend steel poles with anchor bolt foundations. | 2007-10-22 | 2007-11-10 |  | 477933 | 477933 |  |  | 0 | 138 | na | 0.50379 | 795 kcmil ACSR | Steel poles | 100 | 0.50379 | na | na | 25.101(c)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by TxDOT. This project is deferred. | 477933 | 0 | 477933 |  |  | 56 | 477933 | 0 | 0
04T65157 BW/RC | Forney Switch Station-East Mesquite Switch Station 138 kV Rebuild | Dallas County Kaufman County | Rebuild the double circuit 138 kV Forney Switch Station-East Mesquite Switch Station line. | 2007-02-16 | 2007-06-12 | 2007-06-12 | 5165000 | 5165000 |  |  | 100 | 138 | na | 10.6 | 1926.9 kcmil ACSS/TW | Steel Poles | 100 | 5.3 | na | na | 25.101(c)(5)(B) | Final costs accumulating. | 5165000 | 0 | 5165000 |  |  | 57 | 5165000 | 0 | 0
06T65142 TW/JE | Upgrade East Mesquite - West Mesquite 138 kV Line Section | Mesquite, Dallas County, TX | Reconductor using existing structures. Replace insulators, shield wire and conductors for operation at elevated temperature. | 2008-01-15 | 2008-03-01 |  | 753368 | 753368 |  |  | 0 | 138 | na | 2.7 | 1926.9 kcmil ACSS/TW | Steel Poles | 100 | 2.7 | na | na | 25.101(c)(5)(B) | This project has been deferred. | 753368 | 0 | 753368 |  |  | 58 | 753368 | 0 | 0
06T64080 MK/BW | Temple-Lampasas 138 kV Line (Nolanville-Harker Heights Section) | City of Harker Heights, Bell County | This project consists of rebuilding 7 miles between Nolanville and Harker Heights 138 kV line with 1590 MCM ACSR on new double circuit steel pole structures with one circuit in place. | 2008-01-15 | 2008-05-15 |  | 3300000 | 3300000 |  |  | 0 | 138 | na | 7 | 1590 kcmil ACSR | Steel Poles | 100 | 7 | na | na | 25.101(c)(5)(B) | This project has been deferred. | 3300000 | 0 | 3300000 |  |  | 59 | 3300000 | 0 | 0
07T64027 MK/BW | Belton-Ft. Hood 138 kV Line (Killeen Switch-South Harker Heights Section) | City of Killeen, Bell County | This project consists of rebuilding 5.3 miles between Killeen Switch and South Harker Heights 138 kV line with 1590 MCM ACSR on new double circuit steel pole structures with one circuit in place. | 2008-01-15 | 2008-05-15 |  | 2400000 | 2400000 |  |  | 0 | 138 | na | 5.3 | 1590 kcmil ACSR | Steel Poles | 100 | 5.3 | na | na | 25.101(c)(5)(B) | This project has been deferred. | 2400000 | 0 | 2400000 |  |  | 60 | 2400000 | 0 | 0
07T62021 MK/BW | Wichita Falls Switch-Wichita Falls Basin Tap 69 kV Line | City of Wichita Falls, Wichita County | This project consists of rebuilding 1 mile between Wichita Falls Switch and Wichita Falls Basin Tap line with 795 MCM ACSR conductor on new single circuit concrete poles. | 2008-02-13 | 2008-05-15 |  | 860000 | 860000 |  |  | 0 | 69 | na | 1 | 795 kcmil ACSR | Concrete Poles | na | na | na | na | 25.101(c)(5)(B) | This project has been deferred. | 860000 | 0 | 860000 |  |  | 61 | 860000 | 0 | 0
07T64025 07T64026 MK/BW | Athens-Tyler West 69 kV Line, Elkton-Forest Grove 138kV Line | City of Athens, Henderson County | This project consists of rebuilding 1 mile between Athens Sub and Trinidad-Elkton 69 kv line with 795 MCM ACSR on new double circuit steel pole structures and adding a 138kv circuit extension. | 2008-01-01 | 2008-05-15 |  | 750000 | 750000 |  |  | 0 | 69 | 69 138 | 2 | 795 kcmil ACSR | Steel Poles | 100 | 1 | na | na | 25.101(c)(5)(B) 25.101(c)(5)(C) | This project has been deferred. | 750000 | 0 | 750000 |  |  | 62 | 750000 | 0 | 0
05T65418 TW/FC | Gainesville-Muenster 69kV: Rebuild | City of Muenster, City of Gainesville, Cooke County. | This project consists of rebuilding 13.8 miles between Gainesville Dixon Street substation and Muenster substation 69 kV line with 336 kCMIL ACSR conductor on single circuit concrete poles. | 2008-01-01 | 2008-06-15 |  | 9717669 | 9717669 |  |  | 0 | 69 | na | 13.8 | 336 MCM ACSR | Concrete Poles | na | na | na | na | 25.101(c)(5)(B) | This project has been deferred. | 9717669 | 0 | 9717669 |  |  | 63 | 9717669 | 0 | 0
06T65310 TW/FC | NW Carrollton-Gainesville 138 kV: Replace two structures | City of Gainesville, Cooke County. | This project consists of replacing two wood H-frame structures with taller concrete H-frame structures on the NW Carrollton-Gainesville 138 kV line. This is needed for clearance on the Gainesville-Montague Co 69 kV line rebuild. | 2008-03-01 | 2008-05-01 |  | 100000 | 100000 |  |  | 0 | 138 | na | na | 795 kcmil ACSR | Concrete H-frames | na | na | na | na | 25.101(c)(5)(B) | Project built in conjunction with 05T65418 rebuild Gainesville-Muenster 69 kV line section. Project has been deferred. | 100000 | 0 | 100000 |  |  | 64
06T61003 BW/BM | Hutto - Pflugerville 138 kV line: SH-130 Relocate @ HWY 79 | City of Hutto, Williamson County | LSI an agent of TXDOT has requested that a section of the 138 kV Hutto-Pflugerville Loop line be relocated to accommodate the widening of US HWY 79. Along with the relocation for TXDOT a private developer has requested that the line mentioned above be relocated an additional distance from the previous parameters requested by TXDOT. This relocation will involve removing (6) existing structures and the addition of five (5) new structures. All associated project cost and Right of Way will be paid by the requesting parties. | 2007-04-16 | 2007-06-01 | 2007-06-01 | 950000 | 1100000 |  |  | 100 | 138 | na | 0.574 | 795 kcmil ACSR | Steel poles | 70 | 0.4344 | 70 | 0.46 | 25.101(c)(5)(F) 25.101(c)(5)(D) | Final costs accumulating. | 1100000 | 0 | 1100000 |  |  | 65 | 1100000 | 0 | 0
06T62208 WB/JM | Lingleville-Stephenville 138 kV Line Rebuild | Erath County Texas | This project will rebuild the existing Lingleville-Stephenville 138 kV line to accommodate double circuit 959.6 ACSS/TW. This will include installing new double circuit structures. The new structures are as follows: 1 steel pole, 113, 0-1 degree concrete poles and 2 concrete H-frame structures. The new line will be approximately 14.4 miles in length per circuit. Only one circuit of the new 959.6 ACSS/TW will be installed at this time. Additionally, all existing wood H-frames and the existing 4/0 conductor will be removed. | 2007-07-01 | 2007-12-15 |  | 8970483.2 | 8970483.2 |  |  | 10 | 138 | na | 14.4 | 959.6 kcmil ACSS/TW | Concrete poles, Steel poles and Steel H-frames | 100 | 14.4 | 0 | 0 | 25.101(c)(5)(B) |  | 8970483.2 | 0 | 8970483.2 |  |  | 66 | 8970483.2 | 0 | 0
06T63086 WB/JM | Sun - Brand 138 kV: Tap line into new Golden Switching Station | Scurry County, Texas | This project is in response to a new wind generation plant outside of Snyder, Texas. The project will involve removing 3 existing wood structures and the addition of one (1) steel small angle "H" frame, one 3 pole dead end structure and one tangent wood "H" frame to dead end the existing line into the new Golden Switching station. | 2007-03-15 | 2007-04-18 | 2007-04-18 | 452934.81 | 452934.81 |  |  | 100 | 138 | na | 0.22 | 636 ACSR | Steel and Wood H-Frames | 75 | 0.22 | 0 | 0 | 25.101(c)(5)(A) | Final costs accumulating. | 452934.81 | 0 | 452934.81 |  |  | 67 | 452934.81 | 0 | 0
06T63084 WB/JM | Odessa EHV - Morgan Creek 345 kV: Loop Line Quail Switch | City of Odessa, Ector County Texas | This project is in response to a new generation plant in Odessa, Texas. The general scope of the project will involve looping the existing 345 kV line into the new Quail switching station. This work will involve relocating one lattice tower and the addition of two self supporting steel tap poles, and the installation of approximately 400' linear feet of 795 ACSR to the new station dead end. Additionally approximately .5 miles of new OPGW will be installed from Odessa EHV to the new Quail switching station. | 2007-01-29 | 2007-04-13 | 2007-04-13 | 452934.81 | 452934.81 |  |  | 100 | 345 | na | 0.7 | 795 kcmil ACSR bundled | Steel Towers and Steel Poles | 150 | 0.6 | 150 | 0.1 | 25.101(c)(5)(A) | Final costs accumulating. | 452934.81 | 0 | 452934.81 |  |  | 68 | 452934.81 | 0 | 0
06T64076 BW/MH | Upgrade Seaway Teague - W. Fairfield 138kV line. | City of Teague, City of Fairfield, Freestone County | Upgrade the 13.0 mile Seaway Teague - W. Fairfield 138kV line. Using a single conductor 795 ACSR "Drake" conductor. | 2008-09-15 | 2008-12-15 |  | 8921916 | 8921916 |  |  | 0 | 138 | na | 13 | 795 kcmil ACSR | Steel Poles | 100 | 13 | na | na | 25.101(c)(5)(B) | Project has been deferred | 8921916 | 0 | 8921916 |  |  | 69 | 8921916 | 0 | 0
06T64226 BW/MH | Upgrade Jewett-Seaway Teague 138kv line | City of Jewett, Leon County City of Teague, Freestone County | Upgrade the 10.75 mile Jewett - Seaway Teague 138kV line. Using a single conductor 795 ACSR "Drake". | 2008-01-08 | 2008-05-15 |  | 9060498 | 9060498 |  |  | 0 | 138 | na | 10.75 | 795 kcmil ACSR | Steel Poles | 100 | 10.75 | na | na | 25.101(c)(5)(B) |  | 9060498 | 0 | 9060498 |  |  | 70 | 9060498 | 0 | 0
05T61024 06T64228 WB/JM | E Tyler-NE Tyler 138 kV Tap for Delek POI & East Tyler-SE Tyler 138 kV: Tap for Delek | City Of Tyler, Smith County, Texas | Delek Refinery in Tyler Texas has requested a double circuit tap be constructed to feed new substation. This work will consist of two new circuits of 795 ACSR conductor for a length of approximately 2200'. These new circuits will tap the existing East-Tyler NE Tyler 138 kV lines and the East Tyler SE Tyler 138 kV lines. All new Right of Way required has been provided by Delek. | 2007-04-23 | 2007-06-04 | 2007-06-04 | 1300000 | 1300000 |  |  | 100 | 138 | na | 0.43 | 795 kcmil ACSR | Steel Poles and H-Frames | 150 | 0.16 | 120 | 0.43 | 25.101(c)(5)(A) | Final costs accumulating. | 1300000 | 0 | 1300000 |  |  | 71 | 1300000 | 0 | 0
06T61008A SEI/BW | Irving N.E.-Las Colinas 138 kV: Relocate Structures 1/1, 1/2, 1/3 and 1/4 | City of Irving, Dallas County | Replace double circuit steel poles and lattice towers with double circuit steel poles with anchor bolt foundations. | 2007-11-01 | 2007-11-15 |  | 344328 | 344328 |  |  | 0 | 138 | na | 0.78674 | 1033.5 kcmil ACSR | Steel Poles | 100 | 0.39337 | na | na | 25.101(c)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable. | 344328 | 0 | 344328 |  |  | 72 | 344328 | 0 | 0
07T61002 SEI/BW | N.E. Irving Tap 138 kV: Relocate Structure 1/10 | City of Irving, Dallas County | Replace existing double circuit steel pole with new double circuit steel poles with anchor bolt foundations. | 2007-11-01 | 2007-11-15 |  | 110769 | 110769 |  |  | 0 | 138 | na | 0.36894 | 1033.5 kcmil ACSR | Steel Poles | 100 | 0.18447 | na | na | 25.101(c)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable. | 110769 | 0 | 110769 |  |  | 73 | 110769 | 0 | 0
06T62077 JO | Forest Hill-Texas Steel 138kV: TRWD Substation (POI) | City of Fort Worth, Tarrant County | Installing line sectionalizing switches in the Rolling Hills Tap line to provide a Point of Interconnection (POI) for Tarrant Regional Water District (TRWD) Substation. | 2007-08-27 | 2007-10-15 |  | 203994.38 | 203994.38 |  |  | 0 | 138 | na | na | 336 kcmil ACSR | Steel H-Frame | 100 | 0.96 | na | na | 25.101(c)(5)(A) |  | 203994.38 | 0 | 203994.38 |  |  | 74 | 203994.38 | 0 | 0
06T64128 JO | Jewett-Stryker Creek 138kV: Stryker POI | Cherokee County | Installing line sectionalizing switches in the Jewett-Stryker Creek 138kV Line to provide a Point of Interconnection (POI) for Energy Transfer. | 2007-03-05 | 2007-04-13 | 2007-04-13 | 422288 | 422288 |  |  | 100 | 138 | na | na | 795 kcmil ACSR | Steel H-Frame | 100 | na | na | na | 25.101(c)(5)(A) | Final costs accumulating. | 422288 | 0 | 422288 |  |  | 75 | 422288 | 0 | 0
06T65296 JO | Valley-Wolfe City 138kV: Connect FCEC Wolfe City Sub POI | Fannin County | Provide a point of interconnection for the Fannin County Electric Coop (FCEC) Wolfe City Substation. This station will be located north of the TXU Electric Delivery Wolfe City Substation on the Valley-Wolfe City 138kV line. | 2007-03-01 | 2007-04-05 | 2007-04-05 | 337398 | 337398 |  |  | 100 | 138 | na | na | 795 kcmil ACSR | Steel H-Frame | 100 | na | na | na | 25.101(c)(5)(A) | Final costs accumulating. | 337398 | 0 | 337398 |  |  | 76 | 337398 | 0 | 0
07T61004 BW/MK | Rivercrest-Sulphur Springs 138kV Line | City of Sulphur Springs, Hopkins County | This project consists of replacing and raising three H-frame structures for the Thermo Mining operations at Monticello to allow sufficient clearance for hauling equipment. | 2008-05-01 | 2008-05-15 |  | 130000 | 130000 |  |  | 0 | 138 | na | 0.42 | 636 kcmil ACSR | Concrete H-Frame | na | na | na | na | 25.101(c)(5)(D) | This project is 100% reimbursable. Project deferred by Thermo Mining. | 130000 | 0 | 130000 |  |  | 77 | 130000 | 0 | 0
06T62200 EH | Oran-Graham 138 kV Line- Modify for Barton Switching Station | Young County | Remove one existing wood H-frame, and install concrete deadend angle structures to connect to new switching station. | 2007-04-27 | 2007-05-04 |  | 160000 | 160000 |  |  | 100 | 138 | na | 7 | 636 kcmil ACSR | Concrete Poles | 50 | 0.05 | na | 0.05 | 25.101(c)(5)(A) | Final costs accumulating. | 160000 | 0 | 160000 |  |  | 78 | 160000 | 0 | 0
07T63037 EH | Nylon Tap-Olefin-General Tire 138kV Line Re-build | Odessa, Ector County | Upgrade the Nylon Tap-Olefin-General Tire 138kV line from Olefin Tap to Olefin and from Olefin to General Tire (1.4 miles) to obtain a summer rating of 897 amperes. | 2007-10-08 | 2007-11-30 |  | 352222 | 352222 |  |  | 0 | 138 | na | 1.4 | 795 kcmil ACSS | Concrete Poles and Steel Towers | Centerline | 1.4 | na | na | 25.101(c)(5)(B) | Project Deferred | 352222 | 0 | 352222 |  |  | 79 | 352222 | 0 | 0
07T61005 SEI/BW | Calmont-Mineral Wells 69kv:Relocate Structures 2/18, 2/19, and 2/20 | City of White Settlement, Tarrant County | Relocate and replace single circuit wood poles with single circuit concrete poles with direct embed foundations. | 2007-08-13 | 2007-11-30 |  | 206339 | 206339 |  |  | 0 | 69 | na | 0.19697 | 3/8-7 EHS Shield, 556.5 ACSR Phase | Concrete Poles | Centerline Easement | 0.19697 | 100 | 0.30189 | 25.101(c)(5)(F) | Relocation is at the request of the White Settlement ISD and is 100% reimbursable by the White Settlement ISD. | 206339 | 0 | 206339 |  |  | 80 | 206339 | 0 | 0
07T61008 SEI/BW | Poage-Seaton 69kV:Relocate Structure 8/4 | City of Temple, Bell County | Replace existing single circuit wood H-frame structure with new single circuit wood H-frame structure with direct embed foundations. | 2007-10-01 | 2007-10-05 |  | 45000 | 45000 |  |  | 0 | 69 | na | 0.2197 | 3/8-7 HS Shield, 2/0 Type F, Copperweld-CU Phase | Wood H-frame | 100 | 0.2197 | na | na | 25.101(c)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by the Texas Department of Transportation. | 45000 | 0 | 45000 |  |  | 81 | 45000 | 0 | 0
07T61003 SEI/BW | Coppell-Apollo 69kV:Relocate Structure 14N-1W-172 and 14N-1W-173 | City of Dallas, Dallas County | Replace existing wood single circuit, single pole structures with new concrete single circuit, single pole structures with direct embed foundations. | 2007-11-01 | 2007-11-15 |  | 128505 | 128505 |  |  | 0 | 69 | na | 0.1178 | 3/8-7 EHS Shield, 4/0 ACSR Phase | Concrete Poles | 50 | 0.1178 | 50 | 0.13239 | 25.101(c)(5)(D) | Relocation is at the request of the property owner and is 100% reimbursable by the property owner. | 128505 | 0 | 128505 |  |  | 82 | 128505 | 0 | 0
06T61015 SEI/BW | Wichita Falls-Dundee-Bomarton 69kV:Install 80 Structures and Remove 98 Structures | City of Seymour, Baylor County | Replace existing wood single circuit, single pole structures with new wood, concrete and steel single circuit, single pole structures with direct embed foundations. | 2007-07-16 | 2007-12-15 |  | 976518 | 976518 |  |  | 1 | 69 | na | 5.3284 | 1/0 ACSR, 4/0 ACSR | Wood, Concrete and Steel Poles | Centerline Easement | 5.3284 | Centerline Easement | 5.3937 | 25.101(c)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by the Texas Department of Transportation. | 976518 | 0 | 976518 |  |  | 83 | 976518 | 0 | 0
07T63046 DRC | Morgan Creek-Graham 345 kV Line - Changes for Tonkowa Sw. Station | Scurry County | This project covers the required transmission line changes required to connect the new Tonkowa Switching Station to the 345 kV grid. Tonkowa Sw. Station will be the interconnect point between Oncor Electric Delivery and AirTricity's Roscoe Wind Farm merchant generation facility near Roscoe, Texas. The general scope of the project will involve looping the existing 345 kV line into the new Tonkowa switching station. This work will involve relocating one lattice tower and the addition of two self supporting lattice steel tower structures, and the installation of approximately 400' linear feet of 2-1590 ACSR to the new station dead end structure. | 2007-10-22 | 2007-12-01 |  | 400000 |  |  |  | 0 | 345 | na | 0.2 | 1590 kcmil ACSR Bundled | Steel Towers | 140 | 0.2 | na | na | 25.101(c)(5)(A) |  | 400000 | 0 | 400000 |  |  | 84 | 400000 | 0 | 0
07T63050 DRC | Midland East - Big Spring West 138 kV Line - Changes for Stanton East Sw. Station | Martin County | This project covers the required transmission line changes required to connect the new Stanton East Switching Station to the 138 kV grid. Stanton East Sw. Station will be the interconnect point between Oncor Electric Delivery and Stanton Invenergy Wind Generation merchant facility near Stanton, Texas. The general scope of the project will involve looping the existing 138 kV line into the new Stanton East switching station. This work will involve relocating one wood H-frame and the addition of two self supporting lattice steel tower structures, and the installation of approximately 400' linear feet of 795 ACSR to the new station dead end structure. | 2007-11-01 | 2007-12-01 |  | 335000 |  |  |  | 0 | 138 | na | 0.2 | 795 kcmil ACSR | Steel Towers | 140 | 0.2 | na | na | 25.101(c)(5)(A) |  | 335000 | 0 | 335000 |  |  | 85 | 335000 | 0 | 0
06T62202 WB/JM | Decordova-Decordova Dam 138 kV: Reconductor with 959.6 ACSS | City of Granbury, Hood County | The Project consists of reconductoring the existing Decordova-Decordova Dam 138 kV transmission line. Two new E3A towers will be required along with raising 2 tangent towers and moving one super long span tower. New AGS units and compression Deadends will be installed. New installation will be designed and built to 138 kV standards. The existing 138 kV line currently consists of tangent lattice towers with two circuits of 795 ACSR and two (2) 3/8” EHS overhead shield wires. One circuit of the 795 ACSR will be removed. The new construction will consist of the installation of a single circuit of new 959.6 ACSS/TW and a section approximately 3,200’ in length of line over Lake Granbury will have a second 804.5 ACSR installed to create a 2-conductor bundle. | 2007-09-13 | 2007-11-15 |  | 1047782 |  |  |  | 0 | 138 | na | 3.3 miles | 959.6 kcmil ACSS/TW, 804.5 kcmil ACSR | Steel towers | 50 | 3.3 | na | na | 25.101(c)(5)(B) |  | 1047782 | 0 | 1047782 |  |  | 86 | 1047782 | 0 | 0
05T61023A WB/JM | Martin Lake-Elkton and Martin Lake-Tri-Corner 345 kV double Circuit tower line Relocate for Grande Blvd. | City of Tyler, Smith County | This Project is in response to a request by the City of Tyler to relocate the existing 345 kV facilities to accommodate the 2nd phase of Grande Boulevard Road Extension. This project will consist of removing four (4) existing 345 kV Lattice Structures and the installation of five (5) new double circuit 345 kV single poles. The existing 345 kV line will remain in its existing centerline. The new single pole structures will be re-spanned along the existing centerline to accommodate the new roadway. No new Right of Way will be required. | 2007-08-20 | 2007-10-31 |  | 998097.25 |  |  |  | 0 | 345 | na | 0.76 | 1590 kcmil ACSR | Steel towers and poles | 150 | 0.76 | na | na | 25.101(c)(5)(F) | All associated project costs will be reimbursed by the City of Tyler. | 998097.25 | 0 | 998097.25 |  |  | 87 | 998097 | 0.25 | 0.25
07T61013 WB/JM | Trinidad-Overton 138kV: Relocate for Grande Blvd. | City of Tyler, Smith County | This project is in response to a request by the City of Tyler to relocate a section of the Trinidad - Overton 138 kV line section from structure #48/9 to 49/7. The City of Tyler is in planning to begin their construction of Phase II extension of Grande Boulevard in the Fall of 2007.This project will involve removing ten (10) existing wood "H" frame structures and installing seventeen (17) steel self supporting single pole structures. The existing 1750 aac will be removed and replaced with 1590 ACSR. All new poles will be installed within the existing 138 kV easement or fee owned property. As part of the roadway construction the City of Tyler will be purchasing the existing fee owned property from ONCOR and will be granting ONCOR an easement for the existing line on this property. The City of Tyler and ONCOR signed a relocation agreement for this work in May of 2007. | 2007-09-15 | 2007-12-15 |  | 1591165 |  |  |  | 0 | 138 | na | 0.78 | 1750 kcmil AAC, 1590 kcmil ACSR | Steel Poles | 100 | 0.78 | na | na | 25.101(c)(5)(F) | All associated project costs will be reimbursed by the City of Tyler. | 1591165 | 0 | 1591165 |  |  | 88 | 1591165 | 0 | 0.25
07J64002 WB/JM | Grande Temporary for 345 kV Martin Lake – Elkton Circuit | City of Tyler, Smith County | This is for the 345 kV temporary by-pass line section for the Martin Lake – Elkton 345 kV Circuit. The by-pass is being constructed in order to allow for the reconstruction of an approximate .5 mile section of the Martin Lake-Elkton and Martin Lake-Tri-Corner 345 kV double Circuit tower line. | 2007-08-20 | 2007-10-31 |  | 1000000 |  |  |  | 0 | 345 | na | 0..98 | 1590 kcmil ACSR | Steel Towers and Steel Poles | 150 | 0.98 | na | na | 25.101(c)(5)(F) | All associated project costs will be reimbursed by the City of Tyler. | 1000000 | 0 | 1000000 |  |  | 89 | 1000000 | 0 | 0.25
07T61001 SEI/BW | Brownwood-Blanket 69kv:Relocate Structures 46/14, 46/15, 46/16 & 46/17 | City of Brownwood, Brown County | Replace single circuit wood poles with single circuit wood and concrete poles with direct embed foundations. | 2007-12-03 | 2007-12-14 |  | 148699 |  |  |  | 0 | 69 | na | 0.3161 | 3/8-7 EHS Shield, 4/0 ACSR | Single Wood and Concrete Poles | Centerline Easement | 0.3161 | na | na | 25.101(c)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by the Texas Department of Transportation. | 148699 | 0 | 148699 |  |  | 90 | 148699 | 0 | 0.25
07T61010 SEI/BW | N.W. Carrollton-Gainesville 138kV:Relocate Structure 28/8 | City of Valley View, Cooke County | Replace existing wood single circuit, 5-pole deadend structure with new wood single circuit, 5-pole deadend structure with direct embed foundations. | 2007-08-15 | 2007-08-31 |  | 101126 | 101126 |  |  | 0 | 138 | na | 0.14356 | 3/8-7 EHS Shield, 795 kcmil ACSR | 5-Pole Wood Deadend Structure | 100 | 0.14356 | na | na | 25.101(c)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by the Texas Department of Transportation. | 101126 | 0 | 101126 |  |  | 91 | 101126 | 0 | 0.25
07T62096 SEI/JO | White Settlement-Lockheed 69KV: Lockheed North POI | City of Fort Worth, Tarrant County | Provide a POI for a new Lockheed substation which is going to be located on the north side of their property. The circuit will be on single circuit steel poles up to the new substation location. | 2007-07-09 | 2007-08-20 |  | 595000 | 595000 |  |  | 95 | 69 | na | na | 795 kcmil ACSR | Steel Pole Single Circuit Structures | na | na | 50 | 0.7 | 25.101(c)(5)(A) |  | 595000 | 0 | 595000 |  |  | 92 | 595000 | 0 | 0.25
07T61006 BJP/BW | E. Levee-Amelia St. 138 kV Line: DART NW1-B Relocation @ Market Center | City of Dallas, Dallas County | This project consists of relocating three self-supporting steel poles - structures T225, T226 and T227 - in order to accommodate DART's proposed NW1-B railway project at Market Center. | 2007-11-01 | 4/31/2008 |  | 185000 |  |  |  | 0 | 138 | na | 0.3 | 795 kcmil ACSR | Steel Pole | na | na | na | na | 25.101(c)(5)(F) | The existing transmission line is in DART right-of-way and will remain in DART right-of-way after the relocation. This project is 100% reimbursable. | 185000 | 0 | 185000 |  |  | 93 | 185000 | 0 | 0.25
07T64064 JO/RC | Sandow (Alcoa) Substation - Sandow Switch Station 138 kV: Install second 3000A circuit | Milam County | Construct a second 138 kV 3000A circuit from Sandow (Alcoa) Substation to Sandow Switch Station to accommodate the expansion of the Sandow Switch Station and connect Sandow 5. | 2007-10-15 | 2008-02-29 |  | 1223000 |  |  |  |  | na | 138 | 0.87 | Bundled 959.6 kcmil ACSS/TW | Steel Poles | 100 | 0.87 (on existing Sandow-Taylor ROW) | na | na | 25.101(c)(5)(C) |  | 1223000 | 0 | 1223000 |  |  | 94
07T64065 JO/RC | Sandow (Alcoa) Substation - Sandow Switch Station 138 kV Circuit #1: Relocate and Terminate at Sandow Switch Station | Milam County | Relocate and terminate the existing 138 kV 3000A circuit (Ckt. #1) from Sandow (Alcoa) Substation to Sandow Switch Station into a different bay at Sandow Switch Station to accommodate the expansion of the Sandow Switch Station and connect Sandow 5. | 2007-10-15 | 2008-02-29 |  | 452000 |  |  |  |  | 138 | na | 0.08 | Bundled 959.6 kcmil ACSS/TW | Steel Poles | 100 | 0.08 | na | na | 25.101(c)(5)(B) |  | 452000 | 0 | 452000 |  |  | 95
07T64066 JO/RC | Sandow SES Substation – Minerva Substation 138 kV: Cut-in and Terminate at Sandow Switch Station | Milam County | Cut-in the existing Sandow SES Substation – Minerva Substation 138 kV line into the Sandow Switch Station. Remove structures and wires from the cut-in location at Sandow Switch Station to the Sandow SES Substation to accommodate the expansion of the Sandow Switch Station and connect Sandow 5. | 2007-12-17 | 2008-03-28 |  | 385000 |  |  |  |  | 138 | na | 0.03 | 959.6 kcmil ACSS/TW | Steel Poles | 100 | 0.03 | na | na | 25.101(c)(5)(B) |  | 385000 | 0 | 385000 |  |  | 96
07T64070 JO/RC | Elgin Substation – Sandow SES Substation 138 kV: Cut-in and Terminate at Sandow Switch Station | Milam County | Cut-in the existing Elgin Substation – Sandow SES Substation 138 kV line into the Sandow Switch Station. Remove structures and wires from the cut-in location at Sandow Switch Station to the Sandow SES Substation to accommodate the expansion of the Sandow Switch Station and connect Sandow 5. | 2007-12-17 | 2008-03-28 |  | 362000 |  |  |  |  | 138 | na | 0.11 | 1926.9 kcmil ACSS/TW | Steel Poles | 100 | 0.11 | na | na | 25.101(c)(5)(B) |  | 362000 | 0 | 362000 |  |  | 97
07T64071 JO/RC | Sandow Autotransformer #1 - Sandow Switch Station 138 kV: Install 3000A Circuit | Milam County | Construct a new 138 kV tie line (3000A circuit) between the Sandow Autotransformer #1 and Sandow Switch Station to accommodate the expansion of the Sandow Switch Station and connect Sandow 5. | 2007-12-17 | 2008-03-28 |  | 1320000 |  |  |  |  | na | 138 | 0.78 | Bundled 959.6 kcmil ACSS/TW | Steel Poles | 100 | 0.78 (on existing Sandow-Minerva ROW) | na | na | 25.101(c)(5)(C) |  | 1320000 | 0 | 1320000 |  |  | 98
07T61019 BJP/BW | Lomo Alto 138 kV Tap Line: DART NW1-B Relocation @ Lucas Dr. | City of Dallas, Dallas County | This project consists of relocating, and raising in height, three self-supporting steel poles - structures T301, T302 and T303 - in order to accommodate DART's proposed NW1-B railway project at Lucas Drive. | 2007-11-01 | 4/31/2008 |  | 190000 |  |  |  |  | 138 | na | 0.33 | 795 kcmil ACSR | Steel Pole | na | na | na | na | 25.101(c)(5)(F) |  | 190000 | 0 | 190000 |  |  | 99
07T65125 | Jenkins-Royse City-Commerce 69 kV Line | City of Greenville, Hunt County Texas | This project consists of removing three (3) wood poles, installing two (2) wood poles and transferring conductors and shield wires in order to accommodate Texas Department of Transportation's proposed road modifications for Highway 380 near Highway 69 in Greenville Texas. | 2007-10-01 | 2007-12-15 |  | 36000 |  |  |  |  | 69 | na | 0.2 | 336.4 kcmil ACSR | Wood Poles | na | na | na | na | 25.101(c)(5)(F) | This project is non-reimbursable due to being in public right of way. | 36000 | 0 | 36000 |  |  | 100
07T6100 BW/JM | Wilmer-Parkdale 138 kV: Relocate for Wintergreen Road widening | City of Hutchins, Dallas County | Dallas County is widening Wintergreen Road and installing an overpass bridge in the location of the Wilmer-Parkdale 138 kV transmission line crossing. Two new steel poles will be required to raise the Watermill-Parkdale transmission line to go over the bridge. The total length of this project is approximately 1000'. Dallas County will reimburse the cost of this project. | 2007-09-01 | 2007-10-01 |  | 301809 |  |  |  | 0 | 138 | na | 0.19 | 1433 kcmil ACSR | Steel poles | 50' | 0.19 | na | na | 25.101(c)(5)(F) | This project is 100% reimbursable. | 301809 | 0 | 301809 |  |  | 101
07T6100 BW/JM | Sandow-Minerva 138 kV: Relocate for SH6 widening near Hearne | City of Hearne, Robertson County | TXDOT is widening SH6 which will impact the Sandow-Minerva transmission line pole location. One direct embed steel pole will require relocation. A new 5' longer pole bottom section will be purchased and the existing steel pole top section will be reused. | 2007-09-01 | 2007-10-01 |  | 86019 |  |  |  | 0 | 138 | na | 0.1 | 795 kcmil ACSR | Steel poles | 50' | 0.17 | na | na | 25.101(c)(5)(F) | This project is 100% reimbursable. | 86019 | 0 | 86019 |  |  | 102
07T61017 BW/JM | Sandow SES -Taylor relocate for US 79 near Taylor, TX | City of Taylor, Williamson County | TXDOT is widening US79 which will impact the Sandow SES-Taylor transmission line pole location. One - three wood pole angle structure will require relocation and one- wood pole H-frame will require relocation. They will be replaced with a three-pole direct embed concrete structure and a direct embed concrete H-frame structure. | 2007-10-01 | 2007-11-01 |  | 450266 |  |  |  | 0 | 138 | na | 0.1 | 795 kcmil ACSR | Wood and Concrete H Frames | 100' | 0.1 | na | na | 25.101(c)(5)(F) | This project is 100% reimbursable. | 450266 | 0 | 450266 |  |  | 103
07T63059 JO/JM | Morgan Creek-Odessa :345 kV wirework for Long Shore Switch Station | Howard County | This project covers the wirework to terminate the Morgan Creek-Odessa EHV 345 kV line at the proposed Long Shore Switching Station. The affected line section is approximately 1200' in length of two (2) circuits of lattice towers supporting bundled 795 ACSR "Drake". The final build will include installing twelve (12) new dead end insulator assemblies and associated jumpers at the newly erected Long Shore Switching Station dead ends. | 2007-10-01 | 2008-01-31 |  | 97677 |  |  |  | 0 | 345 | na | 0.22 | Double Circuit Bundled 795 kcmil ACSR | Lattice Towers | 150' | 0.22 | na | na | 25.101(c)(5)(A) |  | 97677 | 0 | 97677 |  |  | 104
07T62113 BW/KL | North Main – Duvall 69kV Structure #582 Relocation for TXDOT | City of Fort Worth, Tarrant County | The Texas Department of Transportation is expanding Rosedale near US 287. However, Oncor has a structure in TXDOT'S planned ROW. To accommodate the expansion of Rosedale, Oncor will relocate the structure approximately 40' south. | 2007-10-15 | 2007-12-31 | na | 31360 |  |  |  | 0 | 69 | na | na | Double Circuit 300 kcmil ACSR | Lattice Towers | Public Property | na | na | na | 25.101(c)(5)(F) | Relocation is being done at the request of the Texas Department of Transportation. Project is non-reimbursable. | 31360 | 0 | 31360 |  |  | 105
CCN APPLICATIONS - APPROVED
04T65160 TK/TW | Cedar Hill-DeSoto 138 kV: Reconstruct with Double Circuit | City of DeSoto, City of Glenn Heights, and the City of Cedar Hill, Dallas County | Remove existing single-circuit 138 kV line on wood H-frames and replace with new double circuit 138 kV line on steel or concrete poles | 2006-05-16 | 2007-03-05 | 2007-03-05 | 4532000 | 2000000 |  |  | 100 | 138 | na | 12.4 | 1590 kcmil ACSR | Steel Poles and Concrete Poles | 75 | 6.2 | na | na | 23604 | Notice of Approval 04/11/01. This project also complies with Substantive Rule 25.101(c)(5)(B). Final costs accumulating. | 2000000 | 0 | 2000000 |  |  | 106 | 2000000 | 0 | 0.25
04T64042 BW/RG | Copperas Cove-Ding Dong 138 kV: Construct New Line | Bell County, Coryell County | Construct 15.7 miles 138 kV single circuit single pole from TXU Electric Delivery Copperas Cove Substation to BEPC's Ding Dong Substation. Rebuild 7 poles exiting the Copperas Cove Substation on existing TXU easement during the fall of 2005 to accommodate a request by TXU Electric Delivery Distribution. | 2005-09-16 | 2008-12-31 |  | 7145776 | 10500000 |  |  | 5 | na | 138 | 15.7 | 795 kcmil ACSS | Steel and/or Concrete Poles | na | na | 70 | 15.7 | 27179 | Application filed 12/31/02. Application approved 01/29/2004. This project is to be completed in phases. | 10500000 | 0 | 10500000 |  |  | 107 | 10500000 | 0 | 0.25
06T65281 DRC | West Levee-Norwood 345 kV Line | City of Dallas, Dallas County | Construct 345 kV double-circuit line from West Levee Switch to junction point with the Norwood-NW Carrollton 345 kV line with one circuit installed initially and the 2nd circuit to be installed later as needed. The portion from the junction point with the Norwood-NW Carrollton 345 kV Line and Norwood Switch will use the vacant circuit position on double-circuit poles which has already been certificated. | 2008-02-01 | 2009-05-15 |  | 18100000 |  |  |  | 0 | na | 345 | 6.5 | 1590 kcmil ACSR Bundled | Double-circuit Steel Poles | na | na | 100 | 6.5 | 32455 | Application filed 3/10/2006. Final Order issued 6/07/07. | 18100000 | 0 | 18100000 |  |  | 108 | 18100000 | 0 | 0.25
| CCN APPLICATIONS - PENDING | [21 empty] | 0 | 0 | 0
05T64079 | Salado - Hutto 345kV Construct New Line | Bell County, Williamson County | Construct a 345kV double-circuit line from Salado Switch Station to Hutto Switch Station with two (2) circuits installed. | 2008-11-01 | 2010-05-15 |  | 69600000 |  |  |  | 0 | na | 345 | 36.4 | 1590 kcmil ACSR | Double Circuit Steel Poles and Steel Lattice Towers | na | na | 160 | 36.4 | 34440 | Application Filed 7/10/2007. | 69600000 | 0 | 69600000 |  |  | 109 | 69600000 | 0 | 0.25
| COMPLETED PROJECTS REMOVED FROM 07/15/2007 REPORT. | [21 empty] | 0 | 0 | 0 | [9 empty] | COPY OF CLOSED OUT PROJECTS INCLUDING VALUES
05T62227 06T62201 JO | White Settlement-Lockheed 69 kV: Rebuild tap line to Lockheed | City of White Settlement, Tarrant County | Rebuild the 0.59 mile White Settlement - Lockheed 69 kV line section with single 795 kcmil ACSR conductor. The 0.59 mile section is made up of double circuit steel structures with two circuits in place. | 2006-11-01 | 2006-12-01 | 2006-11-24 |  |  |  |  | 100 | 69 | na | 0.59 | 795 kcmil ACSR | Steel Poles | Varies | 0.59 | na | na | 25.101(c)(5)(B) 25.101(c)(5)(C) | Change in Project Description reflects change in scope of project to accommodate Lockheed production schedule. | 0 | 0 | 0 | [6 empty] | 05T62227 06T62201 JO | White Settlement-Lockheed 69 kV: Rebuild tap line to Lockheed | City of White Settlement, Tarrant County | Rebuild the 0.59 mile White Settlement - Lockheed 69 kV line section with single 795 kcmil ACSR conductor. The 0.59 mile section is made up of double circuit steel structures with two circuits in place. | 2006-11-01 | 2006-12-01 | 2006-11-24 | 340420 | 340240 | 582673 |  | 100 | 69 | na | 0.59 | 795 kcmil ACSR | Steel Poles | Varies | 0.59 | na | na | 25.101(c)(5)(B) 25.101(c)(5)(C) | Change in Project Description reflects change in scope of project to accommodate Lockheed production schedule. | 340240
06T64122 TW | Sandow Switching Station - Temple 138kV: Rebuild Section for 3000A Capacity. | Milam County | Rebuild 0.9 miles of the existing Sandow SES-Temple 138kV line for 3000A operation. Terminals will be Sandow SES and Sandow Switching Station 138kV. | 2006-09-18 | 2006-12-31 | 2006-12-12 |  |  |  |  | 100 | 138 | na | 0.9 | 959.6 kcmil ACSS/TW Bundle | Steel Poles | 75 | 0.9 | na | na | 25.101(c)(5)(B) |  | 0 | 0 | 0 | [6 empty] | 06T64122 TW | Sandow Switching Station - Temple 138kV: Rebuild Section for 3000A Capacity. | Milam County | Rebuild 0.9 miles of the existing Sandow SES-Temple 138kV line for 3000A operation. Terminals will be Sandow SES and Sandow Switching Station 138kV. | 2006-09-18 | 2006-12-31 | 2006-12-12 | 1500000 | 1240000 | 1340462 |  | 100 | 138 | na | 0.9 | 959.6 kcmil ACSS/TW Bundle | Steel Poles | 75 | 0.9 | na | na | 25.101(c)(5)(B) |  | 1240000
06T61010 MK/BW | South Cliff Pump-Camp Wisdom 138 Kv Line: Relocate for the City of Dallas | City of Dallas, Dallas County | This project consists of relocating eight existing steel poles and replacing conductors and transferring shield wires in order to accommodate the City of Dallas's proposed road widening modifications for Houston School Road near Camp Wisdom Road. | 2006-11-01 | 2006-12-31 | 2006-12-08 |  |  |  |  | 100 | 138 | na | na | 795 kcmil ACSR | Concrete Pole | na | na | na | na | 25.101(c)(5)(F) | This project is reimbursable because the City of Dallas has agreed to raise structures in order to accommodate distribution underbuild in conjunction with the University of North Texas. | 0 | 0 | 0 | [6 empty] | 06T61010 MK/BW | South Cliff Pump-Camp Wisdom 138 Kv Line: Relocate for the City of Dallas | City of Dallas, Dallas County | This project consists of relocating eight existing steel poles and replacing conductors and transferring shield wires in order to accommodate the City of Dallas's proposed road widening modifications for Houston School Road near Camp Wisdom Road. | 2006-11-01 | 2006-12-31 | 2006-12-08 | 450000 | 450000 | 354634 |  | 100 | 138 | na | na | 795 kcmil ACSR | Concrete Pole | na | na | na | na | 25.101(c)(5)(F) | This project is reimbursable because the City of Dallas has agreed to raise structures in order to accommodate distribution underbuild in conjunction with the University of North Texas. | 450000
06T62084 YB | White Settlement-Calmont 69kV: Replace Structures | City of White Settlement, Tarrant County | This project consists of replacing three wood structures with three self-supporting dead end structures to accommodate the rebuilt White Settlement Switching Station. | 2006-11-01 | 2006-12-01 | 2006-11-24 |  |  |  |  | 100 | 69 | na | na | 556.5 kcmil ACSR | Steel Poles | na | na | na | na | 25.101(c)(5)(A) |  | 0 | 0 | 0 | [6 empty] | 06T62084 YB | White Settlement-Calmont 69kV: Replace Structures | City of White Settlement, Tarrant County | This project consists of replacing three wood structures with three self-supporting dead end structures to accommodate the rebuilt White Settlement Switching Station. | 2006-11-01 | 2006-12-01 | 2006-11-24 | 271251 | 271251 | 197626 |  | 100 | 69 | na | na | 556.5 kcmil ACSR | Steel Poles | na | na | na | na | 25.101(c)(5)(A)
06T62083 YB | White Settlement-Mineral Wells 69kV: Replace Structures | City of White Settlement, Tarrant County | This project consists of replacing two wood h-frame structures with two self-supporting dead end structures to accommodate the rebuilt White Settlement Switching Station. | 2006-11-01 | 2006-12-01 | 2006-11-24 |  |  |  |  | 100 | 69 | na | na | 4/0 ACSR | Steel Poles | na | na | na | na | 25.101(c)(5)(A) |  | 0 | 0 | 0 | [6 empty] | 06T62083 YB | White Settlement-Mineral Wells 69kV: Replace Structures | City of White Settlement, Tarrant County | This project consists of replacing two wood h-frame structures with two self-supporting dead end structures to accommodate the rebuilt White Settlement Switching Station. | 2006-11-01 | 2006-12-01 | 2006-11-24 | 163544 | 163544 | 31587 |  | 100 | 69 | na | na | 4/0 ACSR | Steel Poles | na | na | na | na | 25.101(c)(5)(A)
06T63076 BM/WB | Morgan Creek - Spraberry 138KV: Loop Line for McDonald Road Substation | Glasscock County | This project involves looping the existing Sprayberry - Morgan Creek 138 kV Transmission Line into the new McDonald Road Substation. This will involve installing two new tap structures and two new tangent steel poles for the looped line and replacing two existing wood H-frames with two new steel H-frames in the existing 138 kV line . Approximately 980' of new 795 kcmil ACSR will be installed for each circuit of the looped line section (1960' total). Additionally one existing 600 amp and one 1200 amp 138 kV type LS air switch will be removed and two new 2000 amp type LD switches will be installed at the Forsan Tap. The existing structure at Forsan Tap will be reused. | 2006-11-01 | 2006-12-15 | 2006-11-20 |  |  |  |  | 100 | 138 | na | 0.15 | 636 kcmil ACSR and 795 kcmil ACSR | Wood H-Frames and Steel H-Frames | 100 | 0.15 | 300 | 0.17 | 25.101(c)(5)(A) |  |  | 0 | 0 | [6 empty] | 06T63076 BM/WB | Morgan Creek - Spraberry 138KV: Loop Line for McDonald Road Substation | Glasscock County | This project involves looping the existing Sprayberry - Morgan Creek 138 kV Transmission Line into the new McDonald Road Substation. This will involve installing two new tap structures and two new tangent steel poles for the looped line and replacing two existing wood H-frames with two new steel H-frames in the existing 138 kV line . Approximately 980' of new 795 kcmil ACSR will be installed for each circuit of the looped line section (1960' total). Additionally one existing 600 amp and one 1200 amp 138 kV type LS air switch will be removed and two new 2000 amp type LD switches will be installed at the Forsan Tap. The existing structure at Forsan Tap will be reused. | 2006-11-01 | 2006-12-15 | 2006-11-20 | 675000 | 675000 | 567301 |  | 100 | 138 | na | 0.15 | 636 kcmil ACSR and 795 kcmil ACSR | Wood H-Frames and Steel H-Frames | 100 | 0.15 | 300 | 0.17 | 25.101(c)(5)(A)
06T64215 TW/RC | Sandow-Temple Sw. 138 kV: Install Structure 2/1 | Milam County | Install Structure 2/1 on the Sandow-Temple Sw. 138 kV Transmission Line to accommodate the expansion of the Sandow Switching Station | 2006-10-18 | 2006-12-29 | 2006-12-12 |  |  |  |  | 100 | 138 | na | 0.1 | 1926.9 kcmil ACSS/TW | Steel Poles | 100 | 0.1 | na | na | 25.101(c)(5)(B) |  |  | 0 | 0 | [6 empty] | 06T64215 TW/RC | Sandow-Temple Sw. 138 kV: Install Structure 2/1 | Milam County | Install Structure 2/1 on the Sandow-Temple Sw. 138 kV Transmission Line to accommodate the expansion of the Sandow Switching Station | 2006-10-18 | 2006-12-29 | 2006-12-12 | 196000 | 227000 | 167203 |  | 100 | 138 | na | 0.1 | 1926.9 kcmil ACSS/TW | Steel Poles | 100 | 0.1 | na | na | 25.101(c)(5)(B)
06T64098 TW/YB | Southeast Nacogdoches-Lufkin 138 kV: Connect Nacogdoches Southwest Substation | City of Nacogdoches, Nacogdoches County | Connect the Southeast Nacogdoches - Lufkin 138kV Transmission Line to the new Nacogdoches Southwest Substation. | 2006-10-23 | 2006-12-15 | 2006-10-25 |  |  |  |  | 100 | 138 | na | 0.05 | 336.4 kcmil ACSR Bundled | Wood Poles | 100 | 0.05 | na | na | 25.101(c)(5)(A) |  |  | 0 | 0 | [6 empty] | 06T64098 TW/YB | Southeast Nacogdoches-Lufkin 138 kV: Connect Nacogdoches Southwest Substation | City of Nacogdoches, Nacogdoches County | Connect the Southeast Nacogdoches - Lufkin 138kV Transmission Line to the new Nacogdoches Southwest Substation. | 2006-10-23 | 2006-12-15 | 2006-10-25 | 5000 | 5000 | 63687 |  | 100 | 138 | na | 0.05 | 336.4 kcmil ACSR Bundled | Wood Poles | 100 | 0.05 | na | na | 25.101(c)(5)(A)
06T62170 WB/JM | Leon-Stephenville 138 kV Line: Loop Line into New Flat Creek Switch | Ector County | This project will loop the existing Leon-Stephenville 138 kV Transmission Line into the new Flat Creek Switching Station. This will include installing two new tap structures, two new tangent steel poles, and two new full tension deadend structures outside of the station. Additionally, two existing wood H-frames will be replaced with steel H-frames in the Leon-Stephenville 138 kV Transmission Line to accommodate the new section of line. | 2006-11-20 | 2006-12-30 | 2006-12-20 |  |  |  |  | 100 | 138 | na | 0.23 | 795 kcmil ACSR | Concrete Poles | 0 | 0 | 100-150 | 0.23 | 25.101(c)(5)(A) |  |  | 0 | 0 | [6 empty] | 06T62170 WB/JM | Leon-Stephenville 138 kV Line: Loop Line into New Flat Creek Switch | Ector County | This project will loop the existing Leon-Stephenville 138 kV Transmission Line into the new Flat Creek Switching Station. This will include installing two new tap structures, two new tangent steel poles, and two new full tension deadend structures outside of the station. Additionally, two existing wood H-frames will be replaced with steel H-frames in the Leon-Stephenville 138 kV Transmission Line to accommodate the new section of line. | 2006-11-20 | 2006-12-30 | 2006-12-20 | 905599 | 905599 | 277470 |  | 100 | 138 | na | 0.23 | 795 kcmil ACSR | Concrete Poles | 0 | 0 | 100-150 | 0.23 | 25.101(c)(5)(A)
05T62147 BW/JF | Pleasant Valley - Iowa Park Tap 69 kV: Construct New Line | Wichita County | Construct 4.5 miles 69 kV single circuit single pole on 138 kV structures from Pleasant Valley to Iowa Park Tap | 2006-03-20 | 2006-11-01 | 2006-11-01 |  |  |  |  | 100 | na | 69 | 4.5 | 795 kcmil ACSR | Steel Poles and Concrete Poles | na | na | 30 | 4.5 | 29768 | Application approved 09/28/2004. Justifications for final costs: 1) Right-of-way, routing and siting costs are included in the final costs, but not in the earlier estimates - this was transferred from another project number; 2) Actual costs for materials and construction labor were higher than estimated. |  | 0 | 0 | [6 empty] | 05T62147 BW/JF | Pleasant Valley - Iowa Park Tap 69 kV: Construct New Line | Wichita County | Construct 4.5 miles 69 kV single circuit single pole on 138 kV structures from Pleasant Valley to Iowa Park Tap | 2006-03-20 | 2006-11-01 | 2006-11-01 | 2857000 | 2586040 | 3279311 | 26.81% | 100 | na | 69 | 4.5 | 795 kcmil ACSR | Steel Poles and Concrete Poles | na | na | 30 | 4.5 | 29768 | Application approved 09/28/2004. Justifications for final costs: 1) Right-of-way, routing and siting costs are included in the final costs, but not in the earlier estimates - this was transferred from another project number; 2) Actual costs for materials and construction labor were higher than estimated.
05T65232 DRC/EB | Venus-Liggett 345 kV Line: Rebuild and Add Second Circuit | City of Grand Prairie, Dallas County, Ellis County, Johnson County and Tarrant county | Add a second circuit to the existing Venus-Liggett 345 kV line from the junction point with the Venus-Cedar Hill 138 kV line to the junction point with the Liggett-Norwood 345 kV line. Construct a 345 kV double circuit line from Venus Switch to the junction point with the Venus-Cedar Hill 138 kV Transmission Line and from the junction point with the Liggett-Norwood 345 kV Transmission Line to the Liggett Switch. The middle section of the line has already been certificated. | 2005-11-01 | 2006-12-29 | 2006-12-11 |  |  |  |  | 100 | 345 | na | 45.4 | 1590 kcmil ACSR Bundled | Steel Poles and Steel Towers | 100150 | 22 | 160 | 6.7 | 31011 32156 | CCN previously approved and one circuit constructed on the original CCN. This project complies with Substantive Rules 25.101(c)(5)(B) and 25.101(b)(3). The Final Order was issued 5/2/2006. | 0 | 0 | 0 | [6 empty] | 05T65232 DRC/EB | Venus-Liggett 345 kV Line: Rebuild and Add Second Circuit | City of Grand Prairie, Dallas County, Ellis County, Johnson County and Tarrant county | Add a second circuit to the existing Venus-Liggett 345 kV line from the junction point with the Venus-Cedar Hill 138 kV line to the junction point with the Liggett-Norwood 345 kV line. Construct a 345 kV double circuit line from Venus Switch to the junction point with the Venus-Cedar Hill 138 kV Transmission Line and from the junction point with the Liggett-Norwood 345 kV Transmission Line to the Liggett Switch. The middle section of the line has already been certificated. | 2005-11-01 | 2006-12-29 | 2006-12-11 | 32200000 | 32200000 | 31811070 | -1.208% | 100 | 345 | na | 45.4 | 1590 kcmil ACSR Bundled | Steel Poles and Steel Towers | 100150 | 22 | 160 | 6.7 | 31011 32156 | CCN previously approved and one circuit constructed on the original CCN. This project complies with Substantive Rules 25.101(c)(5)(B) and 25.101(b)(3). The Final Order was issued 5/2/2006.
05T62100 MM | Jacksboro - W. Denton 345 kV Construct new line | Wise, Jacksboro, and Denton Counties | Construct 72 miles of 345 kV double-circuit line from Jacksboro Switch to West Denton Switch with 1 circuit installed initially and 2nd circuit to be installed later as needed. | 2006-04-15 | 2006-12-31 | 2006-12-15 |  |  |  |  | 100 | na | 345 | 72 | 1590 kcmil ACSR Bundled | Steel Towers | na | na | 160 | 72 | 30168 | Final Order issued 10/12/2005. | 0 | 0 | 0 | [6 empty] | 05T62100 MM | Jacksboro - W. Denton 345 kV Construct new line | Wise, Jacksboro, and Denton Counties | Construct 72 miles of 345 kV double-circuit line from Jacksboro Switch to West Denton Switch with 1 circuit installed initially and 2nd circuit to be installed later as needed. | 2006-04-15 | 2006-12-31 | 2006-12-15 | 62023000 | 62023000 | 67545300 | 8.904% | 100 | na | 345 | 72 | 1590 kcmil ACSR Bundled | Steel Towers | na | na | 160 | 72 | 30168 | Final Order issued 10/12/2005.
06T61011 SEI/BW | Royse Switching Station-Terrell Substation138/69 kV: Relocate structures 18/2 and 18/3 | City of Terrell, Kaufman County | Replace H-frame bottom section and relocate existing steel pole triple circuit H-frame structures. | 2007-08-01 | 2007-10-01 | [5 empty] | 10 | 69 | na | 0.30492 | 1590 kcmil ACSR | Steel H-Frame | 100 | 0.30492 | na | na | 25.101(c)(5)(F) | This project removed from list because it was included in another project already on the list. | 0 | 0 | 0 | [6 empty] | 06T61011 SEI/BW | Royse Switching Station-Terrell Substation138/69 kV: Relocate structures 18/2 and 18/3 | City of Terrell, Kaufman County | Replace H-frame bottom section and relocate existing steel pole triple circuit H-frame structures. | 2007-08-01 | 2007-10-01 |  | 24940 | 24940 |  |  | 10 | 69 | na | 0.30492 | 1590 kcmil ACSR | Steel H-Frame | 100 | 0.30492 | na | na | 25.101(c)(5)(F) | This project removed from list because it was included in another project already on the list.
05T61023 WB/JM | Martin Lake Elkton 345 kV line: Grande Boulevard Phase II | City Of Tyler, Smith County, Texas | The City of Tyler has requested that a portion of the Martin Lake - Elkton 345 kV line be modified to accommodate the extension of Grande Boulevard. This work will involve removing 4 existing lattice structures and the addition of 5 new steel mono poles. No new Right of Way is required. All associated project cost is to be paid by the City of Tyler | 2007-10-01 | 2007-11-15 | [5 empty] | 0 | 345 | na | 0.54 | 1590 kcmil ACSR | Steel Towers and Steel Poles | 150 | 0.54 | 0 | 0 | 25.101(c)(5)(F) | This project removed from list because it a duplicate of another project on the list. | [9 empty] | 05T61023 WB/JM | Martin Lake Elkton 345 kV line: Grande Boulevard Phase II | City Of Tyler, Smith County, Texas | The City of Tyler has requested that a portion of the Martin Lake - Elkton 345 kV line be modified to accommodate the extension of Grande Boulevard. This work will involve removing 4 existing lattice structures and the addition of 5 new steel mono poles. No new Right of Way is required. All associated project cost is to be paid by the City of Tyler | 2007-10-01 | 2007-11-15 |  | 998097 | 998097 |  |  | 0 | 345 | na | 0.54 | 1590 kcmil ACSR | Steel Towers and Steel Poles | 150 | 0.54 | 0 | 0 | 25.101(c)(5)(F) | This project removed from list because it a duplicate of another project on the list.
|  | 12 | 4935131 | [19 empty] | 0 | 0 | 0
|  | NEW PROJECTS: | 4065000
6
0
[23 empty] | Actual Cost of Projects Completed This Month (Will Not Appear on Next Month Report): | Estimated Cost of Projects Completed This Month: | Estimated Cost of Projects Remaining Active This Month: | Total Estimated Cost of Projects Appearing in This Report:
[23 empty] | 0 | 0 | 250953914.25 | 250953914.25
[24 empty] | 0 | 109 | 109 | Project Count
[24 empty] | Completed | Active | Total
Note on A73: Allen Steven Boling: This appears to be a duplicate project. Staff will temporarily modify th project number to allow including it as a separate project, however, until verification is received by TXU that this is a legitimate project.
Note on A88: Allen Steven Boling: This appears to be a duplicate project. Staff revised project number to allow continuation of this project on next month's report following close out of the other, identically numbered project.
Note on H1: aboling: Please enter only a single integer, if possible.
Note on H112: Allen Steven Boling: T LINE: 69,600,000 STATION & OTHER: 22,500,000 TOTAL: 92,100,000
Note on I1: aboling: Please enter only a single integer, if possible.
Note on M1: aboling: If applicable.
Note on N1: aboling: If applicable.
Note on X107: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on Y107: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on Z107: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AD65: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AD95: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AD96: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AD97: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AD98: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AD99: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AD100: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AD101: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AD102: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AD103: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AD104: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AD105: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AD106: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AD107: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AD111: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AD113: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AD114: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AD117: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AD119: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AD120: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AD121: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AD122: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AD123: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AD124: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AE65: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AE95: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AE96: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AE97: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AE98: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AE99: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AE100: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AE101: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AE102: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AE103: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AE104: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AE105: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AE106: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AE107: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AE111: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AE113: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AE114: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AE117: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AE119: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AE120: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AE121: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AE122: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AE123: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AE124: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AF65: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AF95: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AF96: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AF97: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AF98: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AF99: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AF100: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AF101: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AF102: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AF103: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AF104: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AF105: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AF106: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AF107: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AF111: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AF113: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AF114: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AF117: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AF119: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AF120: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AF121: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AF122: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AF123: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.
Note on AF124: Allen Steven Boling: FORMULA DELETED TO ACCOMMODATE NEW PROJECT OR CHANGED PROJECT NUMBER.

## WCEC
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost | Final Estimated Project Cost | Final Actual Project Cost | % Variance | Percent Complete | Existing Voltage | Upgraded or New Voltage | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS | Estimated OR Actual Project Cost (SUBSTATION) |  | Last Month: | Current minus last month: | Cumulative Sum
1A | DWU 138kV Tap 69kV Loop | Wood | Dbl ckt / sgl pole - 138kV service to DWU, 69kV loop Yantis to Cathey | 6/25/2007 ROW 8/27 Const Start |  |  | 4200000 |  |  |  | 0% | NA | 138 / 69 | 6 dbl / 2.4 sgl | 795 ACSR "Drake" | Single Pole Concrete | 80 sgl ckt | 2.4 | 100 dbl ckt | 6 | 30254 | Project is dbl ckt 138/69kV for 6mi. At that point the 138kV ends and the 69kV continues for 2.4 miles. | 4200000 | 0 | 4200000 |  |  | 4200000 | 0 | 0
2A | Feed to Sand Springs Substation | Wood | Dbl ckt / sgl pole - 138kV service to Sand Springs Substation | 9/1/2007 Est. Start ROW Clr |  |  | 940000 |  |  |  | 0% | NA | 138 |  | 795 ACSR "Drake" | Single Pole Concrete | NA | NA | 100 |  | 32070 | CCN Filed April 7, 2006 Line length will depend on route approved. Request is dbl ckt (in & out from tap) | 940000 | 0 | 940000 |  |  | 940000 | 0 | 0
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | Actual Cost of Projects Completed This Month (Will Not Appear on Next Month Report): | Estimated Cost of Projects Completed This Month: | Estimated Cost of Projects Remaining Active This Month: | Total Estimated Cost of Projects Appearing in This Report:
[23 empty] | 0 | 0 | 5140000 | 5140000
[24 empty] | 0 | 2 | 2 | Project Count
[24 empty] | Completed | Active | Total
Note on A2: Allen Steven Boling: STAFF ASSIGNED ARBITRARY PROJECT NUMBER TO ALLOW CHECKING IN THIS SHEET.
Note on A3: Allen Steven Boling: STAFF ASSIGNED ARBITRARY PROJECT NUMBER TO ALLOW CHECKING IN THIS SHEET.
Note on H1: aboling: Please enter only a single integer, if possible.
Note on I1: aboling: Please enter only a single integer, if possible.
Note on M1: aboling: If applicable.
Note on N1: aboling: If applicable.

## RCEC (hidden)
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost | Final Estimated Project Cost | Final Actual Project Cost | % Variance | Percent Complete | Existing Voltage | Upgraded or New Voltage | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS | Estimated OR Actual Project Cost (SUBSTATION) |  | Last Month: | Current minus last month: | Cumulative Sum
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | Actual Cost of Projects Completed This Month (Will Not Appear on Next Month Report): | Estimated Cost of Projects Completed This Month: | Estimated Cost of Projects Remaining Active This Month: | Total Estimated Cost of Projects Appearing in This Report:
[23 empty] | 0 | 0 | 0 | 0
[24 empty] | 0 | 0 | 0 | Project Count
[24 empty] | Completed | Active | Total

## SHECO (hidden)
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost | Final Estimated Project Cost | Final Actual Project Cost | % Variance | Percent Complete | Existing Voltage | Upgraded or New Voltage | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS | Estimated OR Actual Project Cost (SUBSTATION) |  | Last Month: | Current minus last month: | Cumulative Sum
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | Actual Cost of Projects Completed This Month (Will Not Appear on Next Month Report): | Estimated Cost of Projects Completed This Month: | Estimated Cost of Projects Remaining Active This Month: | Total Estimated Cost of Projects Appearing in This Report:
[23 empty] | 0 | 0 | 0 | 0
[24 empty] | 0 | 0 | 0 | Project Count
[24 empty] | Completed | Active | Total

## TVEC (hidden)
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost | Final Estimated Project Cost | Final Actual Project Cost | % Variance | Percent Complete | Existing Voltage | Upgraded or New Voltage | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS | Estimated OR Actual Project Cost (SUBSTATION) |  | Last Month: | Current minus last month: | Cumulative Sum
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | Actual Cost of Projects Completed This Month (Will Not Appear on Next Month Report): | Estimated Cost of Projects Completed This Month: | Estimated Cost of Projects Remaining Active This Month: | Total Estimated Cost of Projects Appearing in This Report:
[23 empty] | 0 | 0 | 0 | 0
[24 empty] | 0 | 0 | 0 | Project Count
[24 empty] | Completed | Active | Total

## UPSHUR (hidden)
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost | Final Estimated Project Cost | Final Actual Project Cost | % Variance | Percent Complete | Existing Voltage | Upgraded or New Voltage | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS | Estimated OR Actual Project Cost (SUBSTATION) |  | Last Month: | Current minus last month: | Cumulative Sum
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | Actual Cost of Projects Completed This Month (Will Not Appear on Next Month Report): | Estimated Cost of Projects Completed This Month: | Estimated Cost of Projects Remaining Active This Month: | Total Estimated Cost of Projects Appearing in This Report:
[23 empty] | 0 | 0 | 0 | 0
[24 empty] | 0 | 0 | 0 | Project Count
[24 empty] | Completed | Active | Total

## NEW2 (hidden)
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost | Final Estimated Project Cost | Final Actual Project Cost | % Variance | Percent Complete | Existing Voltage | Upgraded or New Voltage | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS | Estimated OR Actual Project Cost (SUBSTATION) |  | Last Month: | Current minus last month: | Cumulative Sum
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | Actual Cost of Projects Completed This Month (Will Not Appear on Next Month Report): | Estimated Cost of Projects Completed This Month: | Estimated Cost of Projects Remaining Active This Month: | Total Estimated Cost of Projects Appearing in This Report:
[23 empty] | 0 | 0 | 0 | 0
[24 empty] | 0 | 0 | 0 | Project Count
[24 empty] | Completed | Active | Total

## NEW3 (hidden)
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost | Final Estimated Project Cost | Final Actual Project Cost | % Variance | Percent Complete | Existing Voltage | Upgraded or New Voltage | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS | Estimated OR Actual Project Cost (SUBSTATION) |  | Last Month: | Current minus last month: | Cumulative Sum
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | Actual Cost of Projects Completed This Month (Will Not Appear on Next Month Report): | Estimated Cost of Projects Completed This Month: | Estimated Cost of Projects Remaining Active This Month: | Total Estimated Cost of Projects Appearing in This Report:
[23 empty] | 0 | 0 | 0 | 0
[24 empty] | 0 | 0 | 0 | Project Count
[24 empty] | Completed | Active | Total

## NEW4 (hidden)
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost | Final Estimated Project Cost | Final Actual Project Cost | % Variance | Percent Complete | Existing Voltage | Upgraded or New Voltage | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS | Estimated OR Actual Project Cost (SUBSTATION) |  | Last Month: | Current minus last month: | Cumulative Sum
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | Actual Cost of Projects Completed This Month (Will Not Appear on Next Month Report): | Estimated Cost of Projects Completed This Month: | Estimated Cost of Projects Remaining Active This Month: | Total Estimated Cost of Projects Appearing in This Report:
[23 empty] | 0 | 0 | 0 | 0
[24 empty] | 0 | 0 | 0 | Project Count
[24 empty] | Completed | Active | Total

## NEW (hidden)
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost | Final Estimated Project Cost | Final Actual Project Cost | % Variance | Percent Complete | Existing Voltage | Upgraded or New Voltage | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS | Estimated OR Actual Project Cost (SUBSTATION) |  | Last Month: | Current minus last month: | Cumulative Sum
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | Actual Cost of Projects Completed This Month (Will Not Appear on Next Month Report): | Estimated Cost of Projects Completed This Month: | Estimated Cost of Projects Remaining Active This Month: | Total Estimated Cost of Projects Appearing in This Report:
[23 empty] | 0 | 0 | 0 | 0
[24 empty] | 0 | 0 | 0 | Project Count
[24 empty] | Completed | Active | Total